## operations_clean
Activity_ID | Department | Activity_Type | Description | Priority | Planned_Start | Planned_Finish | Actual_Start | Actual_Finish | Status | Progress_Pct | Responsible_Team | Revision_No | Approval_Status | Last_Update | Record ID | Planned_Date_Check | Actual_Date_Check | Update_Date_Check | Actual_Finish_Clean | Cycle_Time_Days | Delay_Days | Aging_Days | Is_Overdue | Schedule_Status | Data_Quality_Status | ID_Count | Duplicate_ID_Flag
ACT-0001 | Construction | Installation | Execute planned installation | Medium | 2026-03-03 | 2026-03-09 | 2026-03-03 | 2026-03-04 | Completed | 100 | CONST-A | 1 | N/A | 2026-03-04 | 1 | Valid | Valid | Valid | 46085 | 1 | -5 |  | No | On Time | Clean | 1 | Unique
ACT-0002 | QA/QC | Inspection | Conduct quality inspection | Medium | 2026-06-20 | 2026-07-09 | 2026-06-20 |  | In Progress | 25 | QA-B | 2 | N/A | 2026-06-30 | 2 | Valid | Incomplete | Valid |  |  |  | 63 | Yes | Overdue | Clean | 1 | Unique
ACT-0003 | Engineering | Technical Query | Resolve site technical query | Low | 2026-01-29 | 2026-02-11 | 2026-01-31 |  | In Progress | 95 | ENG-B | 1 | N/A | 2026-02-03 | 3 | Valid | Incomplete | Valid |  |  |  | 203 | Yes | Overdue | Clean | 1 | Unique
ACT-0004 | Engineering | Technical Query | Respond to engineering query | High | 2026-04-07 | 2026-04-27 | 2026-04-13 |  | In Progress | 30 | ENG-B | 3 | N/A | 2026-04-25 | 4 | Valid | Incomplete | Valid |  |  |  | 131 | Yes | Overdue | Clean | 1 | Unique
ACT-0005 | Construction | Site Preparation | Prepare work area | Medium | 2026-02-27 | 2026-03-09 | 2026-03-04 |  | On Hold | 60 | CONST-A | 0 | N/A | 2026-03-11 | 5 | Valid | Incomplete | Valid |  |  |  | 171 | Yes | Overdue | Clean | 1 | Unique
ACT-0006 | Construction | Site Preparation | Coordinate access preparation | High | 2026-03-02 | 2026-03-14 | 2026-03-05 | 2026-03-18 | Completed | 100 | CONST-A | 0 | N/A | 2026-03-26 | 6 | Valid | Valid | Valid | 46099 | 13 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0007 | QA/QC | NCR Follow-up | Follow up corrective action | High | 2026-04-16 | 2026-05-02 | 2026-04-22 | 2026-05-19 | Completed | 100 | QC-C | 2 | N/A | 2026-06-01 | 7 | Valid | Valid | Valid | 46161 | 27 | 17 |  | No | Late | Clean | 1 | Unique
ACT-0008 | QA/QC | Testing | Conduct functional test | Medium | 2026-01-28 | 2026-01-31 | 2026-01-31 |  | In Progress | 60 | QC-C | 1 | N/A | 2026-02-14 | 8 | Valid | Incomplete | Valid |  |  |  | 203 | Yes | Overdue | Clean | 1 | Unique
ACT-0009 | QA/QC | Inspection | Conduct quality inspection | High | 2026-06-28 | 2026-07-17 | 2026-07-02 |  | In Progress | 40 | QA-A | 1 | N/A | 2026-07-16 | 9 | Valid | Incomplete | Valid |  |  |  | 51 | Yes | Overdue | Clean | 1 | Unique
ACT-0010 | Document Control | Transmittal | Track transmittal response | High | 2026-05-14 | 2026-05-19 | 2026-05-14 |  | In Progress | 25 | DOC-A | 1 | Approved | 2026-05-30 | 10 | Valid | Incomplete | Valid |  |  |  | 100 | Yes | Overdue | Clean | 1 | Unique
ACT-0011 | Construction | Rework | Correct installation issue | Low | 2026-04-07 | 2026-04-18 | 2026-04-15 | 2026-04-25 | Completed | 100 | CONST-C | 2 | N/A | 2026-04-27 | 11 | Valid | Valid | Valid | 46137 | 10 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0012 | Procurement | Vendor Follow-up | Coordinate supplier action | Medium | 2026-05-25 | 2026-06-01 | 2026-05-28 |  | In Progress | 30 | PROC-B | 4 | N/A | 2026-06-03 | 12 | Valid | Incomplete | Valid |  |  |  | 86 | Yes | Overdue | Clean | 1 | Unique
ACT-0013 | QA/QC | NCR Follow-up | Verify NCR closure | High | 2026-04-30 | 2026-05-05 | 2026-05-03 | 2026-05-12 | Completed | 100 | QA-A | 1 | N/A | 2026-05-12 | 13 | Valid | Valid | Valid | 46154 | 9 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0014 | Planning | Schedule Update | Update activity schedule | Low | 2026-01-13 | 2026-01-25 |  |  | Not Started | 0 | PLAN-A | 0 | N/A | 2026-01-28 | 14 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0015 | Construction | Rework | Correct installation issue | High | 2026-04-19 | 2026-04-27 | 2026-04-20 | 2026-04-30 | Completed | 100 | CONST-C | 3 | N/A | 2026-05-01 | 15 | Valid | Valid | Valid | 46142 | 10 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0016 | Planning | Schedule Update | Update activity schedule | Medium | 2026-04-01 | 2026-04-06 | 2026-04-03 | 2026-04-17 | Completed | 100 | PLAN-A | 0 | N/A | 2026-04-24 | 16 | Valid | Valid | Valid | 46129 | 14 | 11 |  | No | Late | Clean | 1 | Unique
ACT-0017 | Construction | Installation | Complete field installation | High | 2026-05-23 | 2026-05-25 | 2026-06-02 | 2026-05-28 | Completed | 100 | CONST-B | 1 | N/A | 2026-06-03 | 17 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0018 | Document Control | Revision Control | Check revision history | Low | 2026-04-14 | 2026-04-24 | 2026-04-16 |  | In Progress | 75 | DOC-A | 2 | N/A | 2026-05-01 | 18 | Valid | Incomplete | Valid |  |  |  | 128 | Yes | Overdue | Clean | 1 | Unique
ACT-0019 | Engineering | Drawing Revision | Revise issued drawing | Medium | 2026-05-23 | 2026-05-26 | 2026-05-22 | 2026-05-23 | Completed | 100 | ENG-A | 3 | Approved | 2026-06-08 | 19 | Valid | Valid | Valid | 46165 | 1 | -3 |  | No | On Time | Clean | 1 | Unique
ACT-0020 | Procurement | Material Request | Coordinate material requirement | Low | 2026-03-06 | 2026-03-20 | 2026-03-07 |  | In Progress | 80 | PROC-B | 0 | Pending | 2026-03-25 | 20 | Valid | Incomplete | Valid |  |  |  | 168 | Yes | Overdue | Clean | 1 | Unique
ACT-0021 | Document Control | Revision Control | Maintain revision register | High | 2026-03-07 | 2026-03-17 | 2026-03-07 | 2026-03-16 | Completed | 100 | DOC-A | 2 | N/A | 2026-03-18 | 21 | Valid | Valid | Valid | 46097 | 9 | -1 |  | No | On Time | Clean | 1 | Unique
ACT-0022 | Construction | Installation | Complete field installation | Medium | 2026-05-14 | 2026-05-24 | 2026-05-16 | 2026-06-05 | Completed | 100 | CONST-C | 0 | N/A | 2026-06-19 | 22 | Valid | Valid | Valid | 46178 | 20 | 12 |  | No | Late | Clean | 1 | Unique
ACT-0023 | Planning | Schedule Update | Update milestone tracker | High | 2026-03-22 | 2026-03-27 | 2026-03-24 | 2026-04-01 | Completed | 100 | PLAN-B | 1 | N/A | 2026-04-09 | 23 | Valid | Valid | Valid | 46113 | 8 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0024 | Construction | Site Preparation | Prepare work area | High | 2026-03-13 | 2026-03-31 | 2026-03-22 | 2026-04-01 | Completed | 100 | CONST-A | 1 | N/A | 2026-04-09 | 24 | Valid | Valid | Valid | 46113 | 10 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0025 | Engineering | Drawing Revision | Prepare revised drawing | Critical | 2026-02-15 | 2026-03-03 | 2026-02-16 | 2026-03-08 | Completed | 100 | ENG-A | 3 | Pending | 2026-03-25 | 25 | Valid | Valid | Valid | 46089 | 20 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0026 | Procurement | Vendor Follow-up | Check vendor document status | Medium | 2026-03-24 | 2026-04-06 | 2026-03-30 |  | In Progress | 30 | PROC-B | 2 | N/A | 2026-04-10 | 26 | Valid | Incomplete | Valid |  |  |  | 145 | Yes | Overdue | Clean | 1 | Unique
ACT-0027 | Document Control | Revision Control | Update document revision | High | 2026-07-28 | 2026-08-04 | 2026-07-26 | 2026-08-07 | Completed | 100 | DOC-B | 4 | N/A | 2026-08-14 | 27 | Valid | Valid | Valid | 46241 | 12 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0028 | Engineering | Design Review | Check design compliance | High | 2026-05-05 | 2026-05-14 | 2026-05-04 |  | In Progress | 30 | ENG-B | 0 | Pending | 2026-05-16 | 28 | Valid | Incomplete | Valid |  |  |  | 110 | Yes | Overdue | Clean | 1 | Unique
ACT-0029 | QA/QC | Inspection | Verify completed installation | Medium | 2026-05-15 | 2026-05-29 | 2026-05-19 | 2026-05-30 | Completed | 100 | QA-A | 3 | N/A | 2026-06-07 | 29 | Valid | Valid | Valid | 46172 | 11 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0030 | Construction | Site Preparation | Prepare work area | Low | 2026-04-26 | 2026-05-09 | 2026-04-27 | 2026-05-29 | Completed | 100 | CONST-A | 1 | N/A | 2026-06-16 | 30 | Valid | Valid | Valid | 46171 | 32 | 20 |  | No | Late | Clean | 1 | Unique
ACT-0031 | QA/QC | Test Package Review | Review test package | Medium | 2026-05-22 | 2026-05-30 | 2026-05-29 | 2026-06-11 | Completed | 100 | QC-C | 0 | Approved | 2026-06-20 | 31 | Valid | Valid | Valid | 46184 | 13 | 12 |  | No | Late | Clean | 1 | Unique
ACT-0032 | QA/QC | Test Package Review | Check package completeness | Medium | 2026-03-21 | 2026-04-09 | 2026-03-19 |  | In Progress | 80 | QA-B | 1 | Pending | 2026-03-19 | 32 | Valid | Incomplete | Valid |  |  |  | 156 | Yes | Overdue | Clean | 1 | Unique
ACT-0033 | QA/QC | Test Package Review | Validate test records | High | 2026-03-28 | 2026-04-13 | 2026-04-03 |  | In Progress | 95 | QC-C | 0 | Pending | 2026-04-19 | 33 | Valid | Incomplete | Valid |  |  |  | 141 | Yes | Overdue | Clean | 1 | Unique
ACT-0034 | Construction | Site Preparation | Prepare work area | High | 2026-07-16 | 2026-07-25 | 2026-07-19 | 2026-08-09 | Completed | 100 | CONST-B | 0 | N/A | 2026-08-22 | 34 | Valid | Valid | Valid | 46243 | 21 | 15 |  | No | Late | Clean | 1 | Unique
ACT-0035 | Construction | Punch List | Resolve outstanding punch item | High | 2026-05-11 | 2026-05-25 | 2026-05-14 |  | In Progress | 20 | CONST-A | 2 | N/A | 2026-05-21 | 35 | Valid | Incomplete | Valid |  |  |  | 100 | Yes | Overdue | Clean | 1 | Unique
ACT-0036 | Procurement | Purchase Review | Review purchase requirement | Medium | 2026-02-05 | 2026-02-21 | 2026-02-08 | 2026-02-22 | Completed | 100 | PROC-B | 0 | Approved | 2026-03-08 | 36 | Valid | Valid | Valid | 46075 | 14 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0037 | Procurement | Purchase Review | Review purchase requirement | High | 2026-05-06 | 2026-05-22 | 2026-05-09 | 2026-05-25 | Completed | 100 | PROC-B | 1 | Approved | 2026-06-02 | 37 | Valid | Valid | Valid | 46167 | 16 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0038 | Engineering | Technical Query | Resolve site technical query | Medium | 2026-03-27 | 2026-04-15 | 2026-03-25 | 2026-04-16 | Completed | 100 | ENG-B | 0 | N/A | 2026-04-29 | 38 | Valid | Valid | Valid | 46128 | 22 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0039 | QA/QC | Test Package Review | Check package completeness | Low | 2026-04-22 | 2026-05-06 | 2026-04-25 | 2026-05-07 | Completed | 100 | QA-B | 2 | Approved | 2026-05-07 | 39 | Valid | Valid | Valid | 46149 | 12 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0040 | QA/QC | Test Package Review | Check package completeness | Medium | 2026-07-12 | 2026-07-31 | 2026-07-10 |  | In Progress | 40 | QC-C | 1 | Pending | 2026-07-20 | 40 | Valid | Incomplete | Valid |  |  |  | 43 | Yes | Overdue | Clean | 1 | Unique
ACT-0041 | Planning | Variance Review | Review delayed activity | Medium | 2026-05-04 | 2026-05-10 | 2026-05-02 | 2026-05-10 | Completed | 100 | PLAN-B | 2 | N/A | 2026-05-12 | 41 | Valid | Valid | Valid | 46152 | 8 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0042 | Engineering | Material Review | Review material submittal | Low | 2026-04-12 | 2026-04-24 | 2026-04-11 | 2026-05-10 | Completed | 100 | ENG-A | 2 | Approved | 2026-05-18 | 42 | Valid | Valid | Valid | 46152 | 29 | 16 |  | No | Late | Clean | 1 | Unique
ACT-0043 | Construction | Installation | Install project component | Medium | 2026-01-22 | 2026-01-25 | 2026-01-27 | 2026-02-02 | Completed | 100 | CONST-B | 0 | N/A | 2026-02-06 | 43 | Valid | Valid | Valid | 46055 | 6 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0044 | Planning | Progress Review | Validate reported progress | High | 2026-07-20 | 2026-08-02 | 2026-07-18 | 2026-07-28 | Completed | 100 | PLAN-A | 3 | N/A | 2026-08-06 | 44 | Valid | Valid | Valid | 46231 | 10 | -5 |  | No | On Time | Clean | 1 | Unique
ACT-0045 | Construction | Site Preparation | Coordinate access preparation | High | 2026-04-11 | 2026-04-25 | 2026-04-16 |  | In Progress | 95 | CONST-C | 2 | N/A | 2026-04-19 | 45 | Valid | Incomplete | Valid |  |  |  | 128 | Yes | Overdue | Clean | 1 | Unique
ACT-0046 | Procurement | Delivery Tracking | Update delivery schedule | Medium | 2026-04-09 | 2026-04-13 | 2026-04-18 | 2026-05-03 | Completed | 100 | PROC-B | 0 | N/A | 2026-05-14 | 46 | Valid | Valid | Valid | 46145 | 15 | 20 |  | No | Late | Clean | 1 | Unique
ACT-0047 | Planning | Variance Review | Analyze schedule variance | High | 2026-06-20 | 2026-06-30 | 2026-06-18 |  | In Progress | 70 | PLAN-B | 1 | N/A | 2026-07-06 | 47 | Valid | Incomplete | Valid |  |  |  | 65 | Yes | Overdue | Clean | 1 | Unique
ACT-0048 | QA/QC | Testing | Conduct functional test | Medium | 2026-04-30 | 2026-05-09 | 2026-04-28 | 2026-05-10 | Completed | 100 | QA-A | 1 | N/A | 2026-05-20 | 48 | Valid | Valid | Valid | 46152 | 12 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0049 | Construction | Site Preparation | Complete site readiness activity | Medium | 2026-06-06 | 2026-06-16 | 2026-06-06 | 2026-06-25 | Completed | 100 | CONST-A | 1 | N/A | 2026-07-12 | 49 | Valid | Valid | Valid | 46198 | 19 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0050 | Planning | Variance Review | Investigate progress variance | High | 2026-01-28 | 2026-02-08 | 2026-01-28 | 2026-02-05 | Completed | 100 | PLAN-B | 1 | N/A | 2026-02-21 | 50 | Valid | Valid | Valid | 46058 | 8 | -3 |  | No | On Time | Clean | 1 | Unique
ACT-0051 | Construction | Site Preparation | Complete site readiness activity | High | 2026-03-15 | 2026-03-26 | 2026-03-20 | 2026-04-08 | Completed | 100 | CONST-A | 1 | N/A | 2026-04-13 | 51 | Valid | Valid | Valid | 46120 | 19 | 13 |  | No | Late | Clean | 1 | Unique
ACT-0052 | QA/QC | Test Package Review | Check package completeness | High | 2026-07-18 | 2026-08-05 | 2026-07-27 | 2026-08-10 | Completed | 100 | QA-B | 1 | Approved | 2026-08-21 | 52 | Valid | Valid | Valid | 46244 | 14 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0053 | Engineering | Design Review | Review technical specification | Medium | 2026-02-06 | 2026-02-23 | 2026-02-10 | 2026-02-28 | Completed | 100 | ENG-B | 0 | Pending | 2026-03-08 | 53 | Valid | Valid | Valid | 46081 | 18 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0054 | Engineering | Design Review | Check design compliance | Medium | 2026-06-01 | 2026-06-04 | 2026-06-06 | 2026-05-22 | Completed | 100 | ENG-C | 0 | Approved | 2026-06-04 | 54 | Valid | Check | Check |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0055 | Construction | Punch List | Resolve outstanding punch item | Medium | 2026-04-28 | 2026-05-09 | 2026-05-04 |  | In Progress | 95 | CONST-C | 0 | N/A | 2026-05-10 | 55 | Valid | Incomplete | Valid |  |  |  | 110 | Yes | Overdue | Clean | 1 | Unique
ACT-0056 | QA/QC | Inspection | Perform site inspection | Unknown | 2026-05-26 | 2026-05-30 | 2026-05-28 | 2026-06-02 | Completed | 100 | QC-C | 0 | N/A | 2026-06-11 | 56 | Valid | Valid | Valid | 46175 | 5 | 3 |  | No | Late | Missing Priority | 1 | Unique
ACT-0057 | QA/QC | Test Package Review | Review test package | High | 2026-03-13 | 2026-04-02 | 2026-03-12 |  | In Progress | 75 | QA-A | 0 | Pending | 2026-03-20 | 57 | Valid | Incomplete | Valid |  |  |  | 163 | Yes | Overdue | Clean | 1 | Unique
ACT-0058 | Engineering | Drawing Revision | Update drawing comments | High | 2026-05-30 | 2026-06-10 | 2026-05-29 | 2026-06-16 | Completed | 100 | ENG-A | 0 | Approved | 2026-06-30 | 58 | Valid | Valid | Valid | 46189 | 18 | 6 |  | No | Late | Clean | 1 | Unique
ACT-0059 | Construction | Rework | Rectify field discrepancy | Medium | 2026-03-10 | 2026-03-12 | 2026-03-20 | 2026-03-18 | Completed | 100 | CONST-C | 4 | N/A | 2026-03-26 | 59 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0060 | Engineering | Drawing Revision | Update drawing comments | Medium | 2026-04-28 | 2026-05-08 | 2026-04-26 | 2026-05-08 | Completed | 100 | ENG-B | 0 | Approved | 2026-05-18 | 60 | Valid | Valid | Valid | 46150 | 12 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0061 | Planning | Progress Review | Validate reported progress | Medium | 2026-05-11 | 2026-05-22 | 2026-05-09 | 2026-06-01 | Completed | 100 | PLAN-B | 0 | N/A | 2026-06-09 | 61 | Valid | Valid | Valid | 46174 | 23 | 10 |  | No | Late | Clean | 1 | Unique
ACT-0062 | Engineering | Material Review | Check technical datasheet | High | 2026-01-05 | 2026-01-24 | 2026-01-11 |  | In Progress | 70 | ENG-A | 2 | Pending | 2026-01-28 | 62 | Valid | Incomplete | Valid |  |  |  | 223 | Yes | Overdue | Clean | 1 | Unique
ACT-0063 | Document Control | Approval Tracking | Update approval register | Medium | 2026-01-12 | 2026-01-21 | 2026-01-14 | 2026-02-02 | Completed | 100 | DOC-B | 0 | Approved | 2026-02-05 | 63 | Valid | Valid | Valid | 46055 | 19 | 12 |  | No | Late | Clean | 1 | Unique
ACT-0064 | Document Control | Revision Control | Check revision history | Critical | 2026-03-20 | 2026-04-07 | 2026-03-21 | 2026-04-03 | Completed | 100 | DOC-B | 1 | N/A | 2026-04-07 | 64 | Valid | Valid | Valid | 46115 | 13 | -4 |  | No | On Time | Clean | 1 | Unique
ACT-0065 | Engineering | Drawing Revision | Revise issued drawing | Medium | 2026-07-26 | 2026-08-10 | 2026-07-28 |  | In Progress | 10 | ENG-C | 0 | Pending | 2026-08-15 | 65 | Valid | Incomplete | Valid |  |  |  | 25 | Yes | Overdue | Clean | 1 | Unique
ACT-0066 | Document Control | Approval Tracking | Track pending approval | Medium | 2026-05-08 | 2026-05-21 | 2026-05-09 |  | In Progress | 95 | DOC-A | 0 | Pending | 2026-05-22 | 66 | Valid | Incomplete | Valid |  |  |  | 105 | Yes | Overdue | Clean | 1 | Unique
ACT-0067 | QA/QC | Test Package Review | Validate test records | Critical | 2026-04-12 | 2026-04-26 | 2026-04-11 |  | In Progress | 25 | QC-C | 1 | Pending | 2026-04-27 | 67 | Valid | Incomplete | Valid |  |  |  | 133 | Yes | Overdue | Clean | 1 | Unique
ACT-0068 | QA/QC | Inspection | Verify completed installation | Low | 2026-05-01 | 2026-05-03 | 2026-04-29 | 2026-05-16 | Completed | 100 | QA-B | 1 | N/A | 2026-05-24 | 68 | Valid | Valid | Valid | 46158 | 17 | 13 |  | No | Late | Clean | 1 | Unique
ACT-0069 | Construction | Rework | Rectify field discrepancy | Low | 2026-03-30 | 2026-04-18 | 2026-03-30 |  | In Progress | 10 | CONST-C | 1 | N/A | 2026-04-06 | 69 | Valid | Incomplete | Valid |  |  |  | 145 | Yes | Overdue | Clean | 1 | Unique
ACT-0070 | Planning | Lookahead Planning | Prepare lookahead plan | High | 2026-04-26 | 2026-05-01 | 2026-05-02 |  | In Progress | 25 | PLAN-A | 2 | N/A | 2026-05-02 | 70 | Valid | Incomplete | Valid |  |  |  | 112 | Yes | Overdue | Clean | 1 | Unique
ACT-0071 | QA/QC | Inspection | Verify completed installation | Medium | 2026-04-25 | 2026-05-01 | 2026-04-23 | 2026-05-14 | Completed | 100 | QC-C | 0 | N/A | 2026-05-26 | 71 | Valid | Valid | Valid | 46156 | 21 | 13 |  | No | Late | Clean | 1 | Unique
ACT-0072 | Planning | Variance Review | Review delayed activity | Medium | 2026-05-03 | 2026-05-13 | 2026-05-01 | 2026-05-02 | Completed | 100 | PLAN-A | 0 | N/A | 2026-05-19 | 72 | Valid | Valid | Valid | 46144 | 1 | -11 |  | No | On Time | Clean | 1 | Unique
ACT-0073 | Engineering | Technical Query | Respond to engineering query | Medium | 2026-04-23 | 2026-05-03 | 2026-04-21 |  | In Progress | 60 | ENG-B | 1 | N/A | 2026-05-09 | 73 | Valid | Incomplete | Valid |  |  |  | 123 | Yes | Overdue | Clean | 1 | Unique
ACT-0074 | Document Control | Transmittal | Prepare document transmittal | Critical | 2026-06-22 | 2026-07-06 | 2026-07-07 | 2026-07-05 | Completed | 100 | DOC-B | 0 | Approved | 2026-07-20 | 74 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0075 | Procurement | Vendor Follow-up | Coordinate supplier action | High | 2026-03-02 | 2026-03-10 | 2026-02-28 |  | In Progress | 90 | PROC-A | 2 | N/A | 2026-03-04 | 75 | Valid | Incomplete | Valid |  |  |  | 175 | Yes | Overdue | Clean | 1 | Unique
ACT-0076 | Document Control | Document Submission | Prepare document for submission | High | 2026-01-13 | 2026-02-02 | 2026-01-20 | 2026-02-18 | Completed | 100 | DOC-B | 1 | Approved | 2026-03-07 | 76 | Valid | Valid | Valid | 46071 | 29 | 16 |  | No | Late | Clean | 1 | Unique
ACT-0077 | Construction | Site Preparation | Prepare work area | Medium | 2026-05-08 | 2026-05-19 | 2026-05-10 |  | In Progress | 30 | CONST-C | 3 | N/A | 2026-05-22 | 77 | Valid | Incomplete | Valid |  |  |  | 104 | Yes | Overdue | Clean | 1 | Unique
ACT-0078 | QA/QC | Test Package Review | Review test package | Medium | 2026-02-05 | 2026-02-21 | 2026-02-09 |  | In Progress | 60 | QC-C | 3 | Rejected | 2026-02-12 | 78 | Valid | Incomplete | Valid |  |  |  | 194 | Yes | Overdue | Clean | 1 | Unique
ACT-0079 | QA/QC | Inspection | Conduct quality inspection | High | 2026-05-28 | 2026-06-09 | 2026-05-30 |  | In Progress | 40 | QA-A | 2 | N/A | 2026-06-02 | 79 | Valid | Incomplete | Valid |  |  |  | 84 | Yes | Overdue | Clean | 1 | Unique
ACT-0080 | Engineering | Design Review | Check design compliance | Critical | 2026-02-03 | 2026-02-08 | 2026-02-06 | 2026-02-08 | Completed | 100 | ENG-B | 4 | Approved | 2026-02-25 | 80 | Valid | Valid | Valid | 46061 | 2 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0081 | Construction | Punch List | Verify punch completion | High | 2026-05-10 | 2026-05-25 | 2026-05-15 | 2026-06-01 | Completed | 100 | CONST-B | 1 | N/A | 2026-06-08 | 81 | Valid | Valid | Valid | 46174 | 17 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0082 | Engineering | Technical Query | Respond to engineering query | Critical | 2026-06-19 | 2026-07-02 |  |  | Not Started | 0 | ENG-B | 0 | N/A | 2026-06-22 | 82 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0083 | Engineering | Drawing Revision | Prepare revised drawing | High | 2026-01-10 | 2026-01-13 | 2026-01-10 | 2026-01-25 | Completed | 100 | ENG-C | 0 | Approved | 2026-01-31 | 83 | Valid | Valid | Valid | 46047 | 15 | 12 |  | No | Late | Clean | 1 | Unique
ACT-0084 | QA/QC | Testing | Perform pressure test | High | 2026-07-25 | 2026-07-27 | 2026-07-31 |  | In Progress | 75 | QA-A | 0 | N/A | 2026-08-05 | 84 | Valid | Incomplete | Valid |  |  |  | 22 | Yes | Overdue | Clean | 1 | Unique
ACT-0085 | Planning | Schedule Update | Update activity schedule | Low | 2026-07-26 | 2026-08-04 | 2026-07-30 | 2026-08-07 | Completed | 100 | PLAN-A | 1 | N/A | 2026-08-10 | 85 | Valid | Valid | Valid | 46241 | 8 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0086 | Construction | Site Preparation | Coordinate access preparation | High | 2026-04-30 | 2026-05-18 | 2026-04-29 |  | In Progress | 40 | CONST-A | 1 | N/A | 2026-04-29 | 86 | Valid | Incomplete | Valid |  |  |  | 115 | Yes | Overdue | Clean | 1 | Unique
ACT-0087 | Document Control | Approval Tracking | Follow up document approval | High | 2026-05-10 | 2026-05-26 |  |  | Not Started | 0 | DOC-A | 0 | Pending | 2026-05-12 | 87 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0088 | QA/QC | NCR Follow-up | Verify NCR closure | Critical | 2026-05-20 | 2026-05-31 | 2026-05-19 |  | In Progress | 95 | QC-C | 0 | N/A | 2026-06-05 | 88 | Valid | Incomplete | Valid |  |  |  | 95 | Yes | Overdue | Clean | 1 | Unique
ACT-0089 | Document Control | Approval Tracking | Follow up document approval | High | 2026-04-20 | 2026-05-02 | 2026-04-18 | 2026-05-13 | Completed | 100 | DOC-B | 0 | Approved | 2026-05-17 | 89 | Valid | Valid | Valid | 46155 | 25 | 11 |  | No | Late | Clean | 1 | Unique
ACT-0090 | Engineering | Design Review | Review engineering drawing | Medium | 2026-07-14 | 2026-07-27 | 2026-07-12 | 2026-07-28 | Completed | 100 | ENG-C | 0 | Approved | 2026-08-08 | 90 | Valid | Valid | Valid | 46231 | 16 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0091 | Document Control | Approval Tracking | Update approval register | Low | 2026-03-19 | 2026-03-30 | 2026-03-18 |  | In Progress | 20 | DOC-B | 1 | Pending | 2026-03-21 | 91 | Valid | Incomplete | Valid |  |  |  | 157 | Yes | Overdue | Clean | 1 | Unique
ACT-0092 | Construction | Rework | Rectify field discrepancy | Critical | 2026-06-13 | 2026-07-02 |  |  | Not Started | 0 | CONST-A | 4 | N/A | 2026-06-21 | 92 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0093 | Engineering | Technical Query | Clarify design requirement | Medium | 2026-02-20 | 2026-02-26 | 2026-02-20 | 2026-03-10 | Completed | 100 | ENG-A | 0 | N/A | 2026-03-26 | 93 | Valid | Valid | Valid | 46091 | 18 | 12 |  | No | Late | Clean | 1 | Unique
ACT-0094 | QA/QC | Test Package Review | Check package completeness | Medium | 2026-03-25 | 2026-04-06 | 2026-03-31 | 2026-04-15 | Completed | 100 | QA-B | 0 | Approved | 2026-04-17 | 94 | Valid | Valid | Valid | 46127 | 15 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0095 | Construction | Rework | Complete required rework | Unknown | 2026-04-21 | 2026-05-01 | 2026-04-25 | 2026-05-08 | Completed | 100 | CONST-B | 2 | N/A | 2026-05-26 | 95 | Valid | Valid | Valid | 46150 | 13 | 7 |  | No | Late | Missing Priority | 1 | Unique
ACT-0096 | Construction | Site Preparation | Prepare work area | Medium | 2026-06-07 | 2026-06-10 |  |  | Not Started | 0 | CONST-A | 0 | N/A | 2026-06-13 | 96 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0097 | Procurement | Delivery Tracking | Confirm delivery status | Low | 2026-05-12 | 2026-05-27 | 2026-05-17 | 2026-06-05 | Completed | 100 | PROC-A | 3 | N/A | 2026-06-16 | 97 | Valid | Valid | Valid | 46178 | 19 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0098 | QA/QC | Inspection | Verify completed installation | Low | 2026-01-24 | 2026-02-05 | 2026-01-22 | 2026-02-09 | Completed | 100 | QA-B | 0 | N/A | 2026-02-09 | 98 | Valid | Valid | Valid | 46062 | 18 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0099 | Engineering | Material Review | Check technical datasheet | Critical | 2026-01-27 | 2026-02-11 | 2026-01-25 | 2026-02-08 | Completed | 100 | ENG-A | 1 | Approved | 2026-02-18 | 99 | Valid | Valid | Valid | 46061 | 14 | -3 |  | No | On Time | Clean | 1 | Unique
ACT-0100 | QA/QC | Testing | Conduct functional test | Medium | 2026-02-03 | 2026-02-21 | 2026-02-03 |  | In Progress | 95 | QA-A | 4 | N/A | 2026-02-07 | 100 | Valid | Incomplete | Valid |  |  |  | 200 | Yes | Overdue | Clean | 1 | Unique
ACT-0101 | Engineering | Technical Query | Resolve site technical query | Medium | 2026-02-13 | 2026-02-17 | 2026-02-15 |  | In Progress | 70 | ENG-C | 2 | N/A | 2026-03-05 | 101 | Valid | Incomplete | Valid |  |  |  | 188 | Yes | Overdue | Clean | 1 | Unique
ACT-0102 | Construction | Site Preparation | Coordinate access preparation | Medium | 2026-04-27 | 2026-05-01 | 2026-04-26 |  | In Progress | 80 | CONST-A | 0 | N/A | 2026-05-12 | 102 | Valid | Incomplete | Valid |  |  |  | 118 | Yes | Overdue | Clean | 1 | Unique
ACT-0103 | QA/QC | Test Package Review | Review test package | Low | 2026-03-19 | 2026-03-23 | 2026-03-23 | 2026-03-29 | Completed | 100 | QA-B | 1 | Approved | 2026-03-30 | 103 | Valid | Valid | Valid | 46110 | 6 | 6 |  | No | Late | Clean | 1 | Unique
ACT-0104 | Document Control | Revision Control | Check revision history | High | 2026-05-13 | 2026-05-19 | 2026-05-11 |  | In Progress | 20 | DOC-A | 1 | N/A | 2026-05-16 | 104 | Valid | Incomplete | Valid |  |  |  | 103 | Yes | Overdue | Clean | 1 | Unique
ACT-0105 | QA/QC | Test Package Review | Check package completeness | Medium | 2026-06-10 | 2026-06-17 | 2026-06-14 |  | In Progress | 50 | QA-A | 2 | Pending | 2026-06-24 | 105 | Valid | Incomplete | Valid |  |  |  | 69 | Yes | Overdue | Clean | 1 | Unique
ACT-0106 | QA/QC | Test Package Review | Check package completeness | Medium | 2026-06-22 | 2026-06-28 | 2026-06-22 | 2026-07-02 | Completed | 100 | QA-A | 4 | Approved | 2026-07-14 | 106 | Valid | Valid | Valid | 46205 | 10 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0107 | Construction | Installation | Install project component | Medium | 2026-06-18 | 2026-06-30 | 2026-06-18 |  | In Progress | 75 | CONST-C | 0 | N/A | 2026-07-01 | 107 | Valid | Incomplete | Valid |  |  |  | 65 | Yes | Overdue | Clean | 1 | Unique
ACT-0108 | QA/QC | NCR Follow-up | Verify NCR closure | Medium | 2026-02-28 | 2026-03-12 | 2026-02-26 | 2026-03-19 | Completed | 100 | QC-C | 0 | N/A | 2026-03-22 | 108 | Valid | Valid | Valid | 46100 | 21 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0109 | Procurement | Material Request | Coordinate material requirement | Medium | 2026-07-20 | 2026-07-26 | 2026-07-26 | 2026-08-12 | Completed | 100 | PROC-B | 1 | Pending | 2026-08-22 | 109 | Valid | Valid | Valid | 46246 | 17 | 17 |  | No | Late | Clean | 1 | Unique
ACT-0110 | QA/QC | Testing | Perform pressure test | High | 2026-07-16 | 2026-08-01 | 2026-07-23 | 2026-08-21 | Completed | 100 | QC-C | 3 | N/A | 2026-08-20 | 110 | Valid | Valid | Valid | 46255 | 29 | 20 |  | No | Late | Clean | 1 | Unique
ACT-0111 | Document Control | Approval Tracking | Follow up document approval | High | 2026-07-23 | 2026-08-06 | 2026-07-23 |  | In Progress | 30 | DOC-A | 2 | Pending | 2026-07-31 | 111 | Valid | Incomplete | Valid |  |  |  | 30 | Yes | Overdue | Clean | 1 | Unique
ACT-0112 | Planning | Lookahead Planning | Update short-term plan | Critical | 2026-07-06 | 2026-07-24 | 2026-07-06 | 2026-08-09 | Completed | 100 | PLAN-B | 3 | N/A | 2026-08-13 | 112 | Valid | Valid | Valid | 46243 | 34 | 16 |  | No | Late | Clean | 1 | Unique
ACT-0113 | Engineering | Drawing Revision | Update drawing comments | High | 2026-01-11 | 2026-01-26 |  |  | Not Started | 0 | ENG-B | 1 | Pending | 2026-01-13 | 113 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0114 | QA/QC | NCR Follow-up | Follow up corrective action | High | 2026-06-20 | 2026-07-02 | 2026-06-24 |  | In Progress | 25 | QA-B | 2 | N/A | 2026-07-09 | 114 | Valid | Incomplete | Valid |  |  |  | 59 | Yes | Overdue | Clean | 1 | Unique
ACT-0115 | Construction | Installation | Complete field installation | Medium | 2026-02-12 | 2026-03-03 | 2026-02-17 |  | In Progress | 40 | CONST-A | 0 | N/A | 2026-02-20 | 115 | Valid | Incomplete | Valid |  |  |  | 186 | Yes | Overdue | Clean | 1 | Unique
ACT-0116 | QA/QC | Test Package Review | Review test package | Low | 2026-05-12 | 2026-05-31 |  |  | Not Started | 0 | QA-B | 1 | Pending | 2026-05-16 | 116 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0117 | Construction | Site Preparation | Prepare work area | Medium | 2026-02-21 | 2026-02-25 | 2026-02-19 | 2026-03-22 | Completed | 100 | CONST-C | 2 | N/A | 2026-04-07 | 117 | Valid | Valid | Valid | 46103 | 31 | 25 |  | No | Late | Clean | 1 | Unique
ACT-0118 | Engineering | Material Review | Review material submittal | High | 2026-04-10 | 2026-04-20 | 2026-04-10 | 2026-04-27 | Completed | 100 | ENG-C | 2 | Approved | 2026-05-15 | 118 | Valid | Valid | Valid | 46139 | 17 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0119 | Procurement | Vendor Follow-up | Follow up vendor response | Medium | 2026-04-01 | 2026-04-08 | 2026-04-01 | 2026-03-31 | Completed | 100 | PROC-A | 0 | N/A | 2026-04-04 | 119 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0120 | Planning | Variance Review | Analyze schedule variance | Medium | 2026-01-16 | 2026-01-24 | 2026-01-16 | 2026-02-02 | Completed | 100 | PLAN-B | 3 | N/A | 2026-02-17 | 120 | Valid | Valid | Valid | 46055 | 17 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0121 | Engineering | Drawing Revision | Update drawing comments | Medium | 2026-07-23 | 2026-07-26 | 2026-07-23 | 2026-08-03 | Completed | 100 | ENG-B | 3 | Approved | 2026-08-15 | 121 | Valid | Valid | Valid | 46237 | 11 | 8 |  | No | Late | Clean | 2 | Duplicate
ACT-0121 | Document Control | Approval Tracking | Update approval register | Medium | 2026-07-28 | 2026-08-15 | 2026-08-01 |  | In Progress | 25 | DOC-B | 1 | Pending | 2026-08-03 | 122 | Valid | Incomplete | Valid |  |  |  | 21 | Yes | Overdue | Clean | 2 | Duplicate
ACT-0123 | Planning | Lookahead Planning | Review upcoming activities | High | 2026-04-24 | 2026-05-01 | 2026-04-27 | 2026-05-19 | Completed | 100 | PLAN-B | 1 | N/A | 2026-06-01 | 123 | Valid | Valid | Valid | 46161 | 22 | 18 |  | No | Late | Clean | 1 | Unique
ACT-0124 | Construction | Installation | Complete field installation | High | 2026-04-18 | 2026-05-01 | 2026-04-23 |  | In Progress | 10 | CONST-A | 0 | N/A | 2026-05-07 | 124 | Valid | Incomplete | Valid |  |  |  | 121 | Yes | Overdue | Clean | 1 | Unique
ACT-0125 | Engineering | Drawing Revision | Prepare revised drawing | Medium | 2026-04-13 | 2026-05-03 |  |  | Not Started | 0 | ENG-B | 0 | Pending | 2026-04-24 | 125 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0126 | Construction | Installation | Execute planned installation | Medium | 2026-04-08 | 2026-04-22 | 2026-04-09 | 2026-05-22 | Completed | 100 | CONST-B | 0 | N/A | 2026-06-07 | 126 | Valid | Valid | Valid | 46164 | 43 | 30 |  | No | Late | Clean | 1 | Unique
ACT-0127 | Document Control | Document Submission | Prepare document for submission | High | 2026-07-04 | 2026-07-20 | 2026-07-02 |  | In Progress | 25 | DOC-A | 3 | Pending | 2026-07-16 | 127 | Valid | Incomplete | Valid |  |  |  | 51 | Yes | Overdue | Clean | 1 | Unique
ACT-0128 | Procurement | Delivery Tracking | Update delivery schedule | Medium | 2026-01-21 | 2026-02-09 | 2026-01-21 |  | In Progress | 95 | PROC-B | 2 | N/A | 2026-01-26 | 128 | Valid | Incomplete | Valid |  |  |  | 213 | Yes | Overdue | Clean | 1 | Unique
ACT-0129 | Construction | Installation | Complete field installation | High | 2026-03-06 | 2026-03-23 |  |  | Not Started | 0 | CONST-B | 1 | N/A | 2026-03-17 | 129 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0130 | Procurement | Vendor Follow-up | Coordinate supplier action | High | 2026-01-21 | 2026-02-01 | 2026-01-24 | 2026-02-04 | Completed | 100 | PROC-A | 1 | N/A | 2026-02-22 | 130 | Valid | Valid | Valid | 46057 | 11 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0131 | Engineering | Technical Query | Respond to engineering query | Low | 2026-05-04 | 2026-05-22 | 2026-05-10 |  | In Progress | 25 | ENG-A | 1 | N/A | 2026-05-11 | 131 | Valid | Incomplete | Valid |  |  |  | 104 | Yes | Overdue | Clean | 1 | Unique
ACT-0132 | Construction | Site Preparation | Prepare work area | Medium | 2026-07-05 | 2026-07-14 | 2026-07-04 |  | In Progress | 20 | CONST-B | 0 | N/A | 2026-07-21 | 132 | Valid | Incomplete | Valid |  |  |  | 49 | Yes | Overdue | Clean | 1 | Unique
ACT-0133 | Engineering | Technical Query | Respond to engineering query | Medium | 2026-05-13 | 2026-05-20 | 2026-05-13 |  | In Progress | 50 | ENG-A | 3 | N/A | 2026-05-31 | 133 | Valid | Incomplete | Valid |  |  |  | 101 | Yes | Overdue | Clean | 1 | Unique
ACT-0134 | Procurement | Material Request | Prepare material request | Low | 2026-06-18 | 2026-07-08 | 2026-06-20 | 2026-07-10 | Completed | 100 | PROC-B | 0 | Pending | 2026-07-27 | 134 | Valid | Valid | Valid | 46213 | 20 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0135 | Planning | Lookahead Planning | Review upcoming activities | Medium | 2026-06-29 | 2026-07-13 | 2026-06-28 | 2026-07-24 | Completed | 100 | PLAN-B | 1 | N/A | 2026-07-30 | 135 | Valid | Valid | Valid | 46227 | 26 | 11 |  | No | Late | Clean | 1 | Unique
ACT-0136 | Construction | Site Preparation | Coordinate access preparation | Medium | 2026-04-03 | 2026-04-17 | 2026-04-07 | 2026-04-20 | Completed | 100 | CONST-B | 1 | N/A | 2026-04-28 | 136 | Valid | Valid | Valid | 46132 | 13 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0137 | QA/QC | Inspection | Perform site inspection | Medium | 2026-04-13 | 2026-04-28 | 2026-04-14 |  | In Progress | 50 | QA-A | 4 | N/A | 2026-04-24 | 137 | Valid | Incomplete | Valid |  |  |  | 130 | Yes | Overdue | Clean | 1 | Unique
ACT-0138 | Procurement | Purchase Review | Check purchase documentation | Medium | 2026-03-24 | 2026-04-10 |  |  | Not Started | 0 | PROC-A | 4 | Pending | 2026-03-31 | 138 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0139 | Construction | Installation | Complete field installation | Medium | 2026-06-06 | 2026-06-23 | 2026-06-11 | 2026-07-03 | Completed | 100 | CONST-B | 0 | N/A | 2026-07-14 | 139 | Valid | Valid | Valid | 46206 | 22 | 10 |  | No | Late | Clean | 1 | Unique
ACT-0140 | QA/QC | Test Package Review | Review test package | Medium | 2026-02-23 | 2026-03-08 | 2026-03-01 |  | In Progress | 80 | QA-B | 2 | Pending | 2026-03-04 | 140 | Valid | Incomplete | Valid |  |  |  | 174 | Yes | Overdue | Clean | 1 | Unique
ACT-0141 | QA/QC | NCR Follow-up | Review corrective evidence | Critical | 2026-07-17 | 2026-07-23 | 2026-07-21 | 2026-07-27 | Completed | 100 | QA-B | 0 | N/A | 2026-08-06 | 141 | Valid | Valid | Valid | 46230 | 6 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0142 | Construction | Punch List | Resolve outstanding punch item | High | 2026-02-09 | 2026-02-21 | 2026-02-12 | 2026-02-22 | Completed | 100 | CONST-B | 3 | N/A | 2026-03-12 | 142 | Valid | Valid | Valid | 46075 | 10 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0143 | Construction | Rework | Rectify field discrepancy | Medium | 2026-05-06 | 2026-05-08 | 2026-05-12 |  | In Progress | 80 | CONST-C | 0 | N/A | 2026-05-12 | 143 | Valid | Incomplete | Valid |  |  |  | 102 | Yes | Overdue | Clean | 1 | Unique
ACT-0144 | Construction | Punch List | Resolve outstanding punch item | Low | 2026-05-07 | 2026-05-14 | 2026-05-09 | 2026-05-11 | Completed | 100 | CONST-A | 3 | N/A | 2026-05-18 | 144 | Valid | Valid | Valid | 46153 | 2 | -3 |  | No | On Time | Clean | 1 | Unique
ACT-0145 | Construction | Installation | Complete field installation | Low | 2026-03-26 | 2026-04-10 | 2026-03-27 |  | In Progress | 95 | CONST-C | 2 | N/A | 2026-03-31 | 145 | Valid | Incomplete | Valid |  |  |  | 148 | Yes | Overdue | Clean | 1 | Unique
ACT-0146 | QA/QC | NCR Follow-up | Review corrective evidence | Medium | 2026-04-11 | 2026-04-23 | 2026-04-10 | 2026-04-21 | Completed | 100 | QC-C | 2 | N/A | 2026-04-29 | 146 | Valid | Valid | Valid | 46133 | 11 | -2 |  | No | On Time | Clean | 1 | Unique
ACT-0147 | Construction | Punch List | Verify punch completion | Medium | 2026-03-03 | 2026-03-14 | 2026-03-05 |  | In Progress | 70 | CONST-C | 0 | N/A | 2026-03-16 | 147 | Valid | Incomplete | Valid |  |  |  | 170 | Yes | Overdue | Clean | 1 | Unique
ACT-0148 | Document Control | Transmittal | Issue transmittal record | Medium | 2026-06-27 | 2026-07-16 | 2026-07-05 |  | In Progress | 40 | DOC-B | 0 | Rejected | 2026-07-07 | 148 | Valid | Incomplete | Valid |  |  |  | 48 | Yes | Overdue | Clean | 1 | Unique
ACT-0149 | Document Control | Transmittal | Track transmittal response | Medium | 2026-02-25 | 2026-03-16 | 2026-02-25 | 2026-03-19 | Completed | 100 | DOC-A | 2 | Approved | 2026-03-20 | 149 | Valid | Valid | Valid | 46100 | 22 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0150 | Construction | Installation | Complete field installation | Medium | 2026-07-07 | 2026-07-24 | 2026-07-12 |  | On Hold | 50 | CONST-B | 5 | N/A | 2026-07-17 | 150 | Valid | Incomplete | Valid |  |  |  | 41 | Yes | Overdue | Clean | 1 | Unique
ACT-0151 | Planning | Variance Review | Investigate progress variance | High | 2026-07-17 | 2026-07-28 | 2026-07-15 | 2026-07-18 | Completed | 100 | PLAN-A | 1 | N/A | 2026-08-04 | 151 | Valid | Valid | Valid | 46221 | 3 | -10 |  | No | On Time | Clean | 1 | Unique
ACT-0152 | Document Control | Revision Control | Check revision history | High | 2026-02-19 | 2026-02-22 | 2026-02-17 |  | In Progress | 40 | DOC-B | 3 | N/A | 2026-02-17 | 152 | Valid | Incomplete | Valid |  |  |  | 186 | Yes | Overdue | Clean | 1 | Unique
ACT-0153 | Construction | Installation | Install project component | Medium | 2026-06-18 | 2026-07-07 | 2026-06-24 |  | In Progress | 75 | CONST-A | 1 | N/A | 2026-06-30 | 153 | Valid | Incomplete | Valid |  |  |  | 59 | Yes | Overdue | Clean | 1 | Unique
ACT-0154 | QA/QC | Test Package Review | Validate test records | Medium | 2026-02-21 | 2026-02-23 | 2026-02-24 |  | In Progress | 90 | QA-B | 3 | Approved | 2026-03-12 | 154 | Valid | Incomplete | Valid |  |  |  | 179 | Yes | Overdue | Clean | 1 | Unique
ACT-0155 | Engineering | Design Review | Review engineering drawing | Critical | 2026-05-07 | 2026-05-19 | 2026-05-05 | 2026-05-18 | Completed | 100 | ENG-C | 0 | Approved | 2026-06-05 | 155 | Valid | Valid | Valid | 46160 | 13 | -1 |  | No | On Time | Clean | 1 | Unique
ACT-0156 | Construction | Site Preparation | Coordinate access preparation | Medium | 2026-03-06 | 2026-03-09 | 2026-03-12 | 2026-03-25 | Completed | 100 | CONST-C | 4 | N/A | 2026-04-03 | 156 | Valid | Valid | Valid | 46106 | 13 | 16 |  | No | Late | Clean | 1 | Unique
ACT-0157 | Engineering | Technical Query | Clarify design requirement | High | 2026-03-02 | 2026-03-08 | 2026-03-08 | 2026-03-20 | Completed | 100 | ENG-C | 2 | N/A | 2026-04-04 | 157 | Valid | Valid | Valid | 46101 | 12 | 12 |  | No | Late | Clean | 1 | Unique
ACT-0158 | Procurement | Vendor Follow-up | Follow up vendor response | High | 2026-06-06 | 2026-06-10 | 2026-06-09 | 2026-06-10 | Completed | 100 | PROC-A | 0 | N/A | 2026-06-27 | 158 | Valid | Valid | Valid | 46183 | 1 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0159 | Construction | Punch List | Close punch item | Medium | 2026-05-18 | 2026-06-03 | 2026-05-28 | 2026-06-09 | Completed | 100 | CONST-B | 1 | N/A | 2026-06-10 | 159 | Valid | Valid | Valid | 46182 | 12 | 6 |  | No | Late | Clean | 1 | Unique
ACT-0160 | Engineering | Material Review | Validate material specification | Medium | 2026-05-28 | 2026-06-13 | 2026-05-28 | 2026-06-24 | Completed | 100 | ENG-A | 0 | Approved | 2026-06-26 | 160 | Valid | Valid | Valid | 46197 | 27 | 11 |  | No | Late | Clean | 1 | Unique
ACT-0161 | Construction | Installation | Execute planned installation | Critical | 2026-01-22 | 2026-02-08 |  |  | Not Started | 0 | CONST-C | 1 | N/A | 2026-01-26 | 161 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0162 | Document Control | Approval Tracking | Follow up document approval | Critical | 2026-04-12 | 2026-04-28 | 2026-04-13 |  | In Progress | 90 | DOC-B | 4 | Approved | 2026-04-17 | 162 | Valid | Incomplete | Valid |  |  |  | 131 | Yes | Overdue | Clean | 1 | Unique
ACT-0163 | Engineering | Material Review | Check technical datasheet | Medium | 2026-03-03 | 2026-03-05 | 2026-03-09 |  | In Progress | 60 | ENG-A | 3 | Pending | 2026-03-20 | 163 | Valid | Incomplete | Valid |  |  |  | 166 | Yes | Overdue | Clean | 1 | Unique
ACT-0164 | QA/QC | Inspection | Perform site inspection | High | 2026-04-22 | 2026-04-24 | 2026-04-23 | 2026-04-24 | Completed | 100 | QA-A | 2 | N/A | 2026-04-25 | 164 | Valid | Valid | Valid | 46136 | 1 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0165 | Procurement | Purchase Review | Validate procurement status | Medium | 2026-03-01 | 2026-03-04 | 2026-03-02 |  | In Progress | 95 | PROC-A | 1 | Pending | 2026-03-12 | 165 | Valid | Incomplete | Valid |  |  |  | 173 | Yes | Overdue | Clean | 1 | Unique
ACT-0166 | QA/QC | Testing | Complete system testing | Medium | 2026-04-20 | 2026-05-01 | 2026-04-18 |  | In Progress | 90 | QA-A | 1 | N/A | 2026-05-03 | 166 | Valid | Incomplete | Valid |  |  |  | 126 | Yes | Overdue | Clean | 1 | Unique
ACT-0167 | Document Control | Approval Tracking | Update approval register | Medium | 2026-04-21 | 2026-05-06 | 2026-04-21 | 2026-05-10 | Completed | 100 | DOC-B | 3 | Approved | 2026-05-14 | 167 | Valid | Valid | Valid | 46152 | 19 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0168 | Document Control | Approval Tracking | Follow up document approval | Medium | 2026-02-08 | 2026-02-22 | 2026-02-06 | 2026-02-16 | Completed | 100 | DOC-A | 3 | Approved | 2026-02-22 | 168 | Valid | Valid | Valid | 46069 | 10 | -6 |  | No | On Time | Clean | 1 | Unique
ACT-0169 | QA/QC | Inspection | Perform site inspection | Unknown | 2026-07-18 | 2026-08-07 | 2026-07-16 |  | In Progress | 50 | QA-A | 0 | N/A | 2026-07-16 | 169 | Valid | Incomplete | Valid |  |  |  | 37 | Yes | Overdue | Missing Priority | 1 | Unique
ACT-0170 | Document Control | Document Submission | Issue controlled document | Critical | 2026-05-07 | 2026-05-16 | 2026-05-07 | 2026-05-13 | Completed | 100 | DOC-B | 0 | Approved | 2026-05-27 | 170 | Valid | Valid | Valid | 46155 | 6 | -3 |  | No | On Time | Clean | 1 | Unique
ACT-0171 | QA/QC | NCR Follow-up | Review corrective evidence | High | 2026-05-04 | 2026-05-09 | 2026-05-05 | 2026-05-03 | Completed | 100 | QA-B | 0 | N/A | 2026-05-13 | 171 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0172 | Engineering | Drawing Revision | Prepare revised drawing | Medium | 2026-03-12 | 2026-03-31 | 2026-03-11 | 2026-04-01 | Completed | 100 | ENG-B | 0 | Approved | 2026-04-08 | 172 | Valid | Valid | Valid | 46113 | 21 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0173 | Construction | Site Preparation | Complete site readiness activity | High | 2026-05-10 | 2026-05-27 | 2026-05-12 | 2026-05-29 | Completed | 100 | CONST-C | 1 | N/A | 2026-06-03 | 173 | Valid | Valid | Valid | 46171 | 17 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0174 | Document Control | Document Submission | Issue controlled document | Low | 2026-01-24 | 2026-01-27 | 2026-01-22 | 2026-02-08 | Completed | 100 | DOC-B | 2 | Approved | 2026-02-24 | 174 | Valid | Valid | Valid | 46061 | 17 | 12 |  | No | Late | Clean | 1 | Unique
ACT-0175 | QA/QC | Test Package Review | Validate test records | Medium | 2026-01-06 | 2026-01-25 | 2026-01-13 | 2026-02-01 | Completed | 100 | QA-A | 5 | Approved | 2026-02-14 | 175 | Valid | Valid | Valid | 46054 | 19 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0176 | Engineering | Design Review | Review technical specification | Medium | 2026-02-23 | 2026-03-13 | 2026-02-21 | 2026-03-29 | Completed | 100 | ENG-C | 4 | Approved | 2026-04-05 | 176 | Valid | Valid | Valid | 46110 | 36 | 16 |  | No | Late | Clean | 1 | Unique
ACT-0177 | QA/QC | Inspection | Conduct quality inspection | Critical | 2026-06-20 | 2026-06-23 | 2026-06-19 | 2026-07-06 | Completed | 100 | QA-A | 0 | N/A | 2026-07-11 | 177 | Valid | Valid | Valid | 46209 | 17 | 13 |  | No | Late | Clean | 1 | Unique
ACT-0178 | Construction | Rework | Rectify field discrepancy | High | 2026-05-29 | 2026-06-03 | 2026-06-03 |  | In Progress | 80 | CONST-A | 1 | N/A | 2026-06-04 | 178 | Valid | Incomplete | Valid |  |  |  | 80 | Yes | Overdue | Clean | 1 | Unique
ACT-0179 | Planning | Lookahead Planning | Update short-term plan | Medium | 2026-01-13 | 2026-01-20 | 2026-01-13 | 2026-02-02 | Completed | 100 | PLAN-A | 2 | N/A | 2026-02-14 | 179 | Valid | Valid | Valid | 46055 | 20 | 13 |  | No | Late | Clean | 1 | Unique
ACT-0180 | QA/QC | Testing | Complete system testing | High | 2026-04-14 | 2026-05-03 | 2026-04-15 |  | In Progress | 95 | QC-C | 2 | N/A | 2026-05-01 | 180 | Valid | Incomplete | Valid |  |  |  | 129 | Yes | Overdue | Clean | 1 | Unique
ACT-0181 | Document Control | Document Submission | Submit project document | Medium | 2026-01-24 | 2026-02-05 | 2026-01-22 |  | In Progress | 90 | DOC-A | 0 | Rejected | 2026-02-06 | 181 | Valid | Incomplete | Valid |  |  |  | 212 | Yes | Overdue | Clean | 1 | Unique
ACT-0182 | QA/QC | Test Package Review | Check package completeness | Medium | 2026-06-03 | 2026-06-17 | 2026-06-02 |  | In Progress | 95 | QC-C | 0 | Pending | 2026-06-14 | 182 | Valid | Incomplete | Valid |  |  |  | 81 | Yes | Overdue | Clean | 1 | Unique
ACT-0183 | Procurement | Vendor Follow-up | Coordinate supplier action | Medium | 2026-04-07 | 2026-04-12 | 2026-04-15 |  | In Progress | 20 | PROC-B | 0 | N/A | 2026-04-29 | 183 | Valid | Incomplete | Valid |  |  |  | 129 | Yes | Overdue | Clean | 1 | Unique
ACT-0184 | Engineering | Design Review | Check design compliance | Medium | 2026-06-06 | 2026-06-18 | 2026-06-06 | 2026-06-12 | Completed | 100 | ENG-C | 2 | Approved | 2026-06-19 | 184 | Valid | Valid | Valid | 46185 | 6 | -6 |  | No | On Time | Clean | 1 | Unique
ACT-0185 | Construction | Rework | Correct installation issue | Medium | 2026-03-23 | 2026-04-02 | 2026-03-29 | 2026-04-04 | Completed | 100 | CONST-B | 1 | N/A | 2026-04-06 | 185 | Valid | Valid | Valid | 46116 | 6 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0186 | QA/QC | Testing | Complete system testing | High | 2026-06-06 | 2026-06-14 | 2026-06-10 | 2026-06-29 | Completed | 100 | QA-B | 3 | N/A | 2026-07-11 | 186 | Valid | Valid | Valid | 46202 | 19 | 15 |  | No | Late | Clean | 1 | Unique
ACT-0187 | Construction | Rework | Rectify field discrepancy | Critical | 2026-02-08 | 2026-02-19 | 2026-02-11 |  | In Progress | 50 | CONST-B | 0 | N/A | 2026-02-23 | 187 | Valid | Incomplete | Valid |  |  |  | 192 | Yes | Overdue | Clean | 1 | Unique
ACT-0188 | QA/QC | Test Package Review | Validate test records | High | 2026-03-29 | 2026-04-12 | 2026-04-01 |  | In Progress | 75 | QC-C | 0 | Approved | 2026-04-01 | 188 | Valid | Incomplete | Valid |  |  |  | 143 | Yes | Overdue | Clean | 1 | Unique
ACT-0189 | Construction | Punch List | Verify punch completion | Unknown | 2026-07-01 | 2026-07-05 | 2026-07-01 |  | In Progress | 70 | CONST-A | 0 | N/A | 2026-07-10 | 189 | Valid | Incomplete | Valid |  |  |  | 52 | Yes | Overdue | Missing Priority | 1 | Unique
ACT-0190 | QA/QC | Testing | Complete system testing | Medium | 2026-04-11 | 2026-04-15 | 2026-04-10 | 2026-04-15 | Completed | 100 | QC-C | 4 | N/A | 2026-04-28 | 190 | Valid | Valid | Valid | 46127 | 5 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0191 | Engineering | Technical Query | Respond to engineering query | High | 2026-05-22 | 2026-05-26 | 2026-05-23 | 2026-06-11 | Completed | 100 | ENG-C | 1 | N/A | 2026-06-29 | 191 | Valid | Valid | Valid | 46184 | 19 | 16 |  | No | Late | Clean | 1 | Unique
ACT-0192 | Planning | Variance Review | Investigate progress variance | Critical | 2026-04-25 | 2026-04-30 |  |  | Not Started | 0 | PLAN-A | 0 | N/A | 2026-05-11 | 192 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0193 | Construction | Rework | Complete required rework | High | 2026-06-04 | 2026-06-22 | 2026-06-11 | 2026-07-01 | Completed | 100 | CONST-A | 4 | N/A | 2026-07-03 | 193 | Valid | Valid | Valid | 46204 | 20 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0194 | Procurement | Vendor Follow-up | Check vendor document status | Medium | 2026-05-01 | 2026-05-09 | 2026-05-03 |  | In Progress | 20 | PROC-A | 0 | N/A | 2026-05-06 | 194 | Valid | Incomplete | Valid |  |  |  | 111 | Yes | Overdue | Clean | 1 | Unique
ACT-0195 | Procurement | Material Request | Coordinate material requirement | High | 2026-07-13 | 2026-07-22 | 2026-07-18 | 2026-07-29 | Completed | 100 | PROC-A | 1 | Approved | 2026-08-03 | 195 | Valid | Valid | Valid | 46232 | 11 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0196 | Planning | Variance Review | Investigate progress variance | Low | 2026-06-11 | 2026-06-19 | 2026-06-15 | 2026-06-27 | Completed | 100 | PLAN-A | 0 | N/A | 2026-06-29 | 196 | Valid | Valid | Valid | 46200 | 12 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0197 | Procurement | Vendor Follow-up | Check vendor document status | Medium | 2026-05-02 | 2026-05-07 | 2026-05-06 |  | In Progress | 90 | PROC-B | 0 | N/A | 2026-05-18 | 197 | Valid | Incomplete | Valid |  |  |  | 108 | Yes | Overdue | Clean | 1 | Unique
ACT-0198 | Construction | Site Preparation | Complete site readiness activity | High | 2026-06-12 | 2026-06-19 | 2026-06-14 |  | In Progress | 25 | CONST-B | 0 | N/A | 2026-06-21 | 198 | Valid | Incomplete | Valid |  |  |  | 69 | Yes | Overdue | Clean | 1 | Unique
ACT-0199 | Engineering | Technical Query | Respond to engineering query | Medium | 2026-04-14 | 2026-04-29 | 2026-04-13 | 2026-04-26 | Completed | 100 | ENG-C | 1 | N/A | 2026-05-01 | 199 | Valid | Valid | Valid | 46138 | 13 | -3 |  | No | On Time | Clean | 1 | Unique
ACT-0200 | Engineering | Technical Query | Resolve site technical query | Medium | 2026-04-30 | 2026-05-03 | 2026-05-03 |  | In Progress | 30 | ENG-C | 3 | N/A | 2026-05-20 | 200 | Valid | Incomplete | Valid |  |  |  | 111 | Yes | Overdue | Clean | 1 | Unique
ACT-0201 | Planning | Variance Review | Review delayed activity | Medium | 2026-07-05 | 2026-07-21 | 2026-07-06 |  | In Progress | 40 | PLAN-A | 0 | N/A | 2026-07-15 | 201 | Valid | Incomplete | Valid |  |  |  | 47 | Yes | Overdue | Clean | 1 | Unique
ACT-0202 | Procurement | Purchase Review | Check purchase documentation | Medium | 2026-05-31 | 2026-06-05 | 2026-06-04 | 2026-06-26 | Completed | 100 | PROC-A | 2 | Approved | 2026-07-10 | 202 | Valid | Valid | Valid | 46199 | 22 | 21 |  | No | Late | Clean | 1 | Unique
ACT-0203 | Document Control | Document Submission | Issue controlled document | High | 2026-07-16 | 2026-07-25 | 2026-07-17 |  | In Progress | 50 | DOC-A | 3 | Pending | 2026-07-20 | 203 | Valid | Incomplete | Valid |  |  |  | 36 | Yes | Overdue | Clean | 1 | Unique
ACT-0204 | QA/QC | NCR Follow-up | No Description | High | 2026-04-24 | 2026-05-01 | 2026-04-27 |  | In Progress | 75 | QA-A | 0 | N/A | 2026-05-14 | 204 | Valid | Incomplete | Valid |  |  |  | 117 | Yes | Overdue | Missing Description | 1 | Unique
ACT-0205 | QA/QC | NCR Follow-up | Verify NCR closure | Medium | 2026-05-16 | 2026-05-21 | 2026-05-14 |  | In Progress | 10 | QC-C | 5 | N/A | 2026-05-18 | 205 | Valid | Incomplete | Valid |  |  |  | 100 | Yes | Overdue | Clean | 1 | Unique
ACT-0206 | Document Control | Revision Control | Update document revision | High | 2026-03-09 | 2026-03-23 | 2026-03-08 | 2026-03-24 | Completed | 100 | DOC-B | 1 | N/A | 2026-03-26 | 206 | Valid | Valid | Valid | 46105 | 16 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0207 | Construction | Site Preparation | Coordinate access preparation | Critical | 2026-04-09 | 2026-04-25 | 2026-04-12 |  | In Progress | 95 | CONST-A | 5 | N/A | 2026-04-23 | 207 | Valid | Incomplete | Valid |  |  |  | 132 | Yes | Overdue | Clean | 1 | Unique
ACT-0208 | Procurement | Purchase Review | Review purchase requirement | Critical | 2026-02-28 | 2026-03-17 | 2026-03-04 |  | In Progress | 80 | PROC-A | 0 | Approved | 2026-03-14 | 208 | Valid | Incomplete | Valid |  |  |  | 171 | Yes | Overdue | Clean | 1 | Unique
ACT-0209 | Engineering | Material Review | Review material submittal | Medium | 2026-02-14 | 2026-03-02 | 2026-02-19 |  | In Progress | 90 | ENG-A | 0 | Approved | 2026-02-27 | 209 | Valid | Incomplete | Valid |  |  |  | 184 | Yes | Overdue | Clean | 1 | Unique
ACT-0210 | Planning | Lookahead Planning | Prepare lookahead plan | Medium | 2026-06-20 | 2026-06-27 |  |  | Not Started | 0 | PLAN-B | 1 | N/A | 2026-06-27 | 210 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0211 | Planning | Schedule Update | Update activity schedule | Medium | 2026-01-24 | 2026-01-30 | 2026-01-24 | 2026-02-01 | Completed | 100 | PLAN-B | 0 | N/A | 2026-02-04 | 211 | Valid | Valid | Valid | 46054 | 8 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0212 | Planning | Variance Review | Analyze schedule variance | Medium | 2026-01-27 | 2026-02-01 | 2026-01-28 | 2026-02-01 | Completed | 100 | PLAN-A | 3 | N/A | 2026-02-05 | 212 | Valid | Valid | Valid | 46054 | 4 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0213 | Engineering | Design Review | Review technical specification | High | 2026-04-27 | 2026-05-10 | 2026-05-02 |  | In Progress | 60 | ENG-A | 1 | Pending | 2026-05-08 | 213 | Valid | Incomplete | Valid |  |  |  | 112 | Yes | Overdue | Clean | 1 | Unique
ACT-0214 | Document Control | Revision Control | Update document revision | High | 2026-04-13 | 2026-04-26 | 2026-04-13 | 2026-05-04 | Completed | 100 | DOC-B | 0 | N/A | 2026-05-21 | 214 | Valid | Valid | Valid | 46146 | 21 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0215 | Procurement | Material Request | Coordinate material requirement | High | 2026-02-26 | 2026-03-16 | 2026-03-03 |  | In Progress | 30 | PROC-A | 1 | Pending | 2026-03-18 | 215 | Valid | Incomplete | Valid |  |  |  | 172 | Yes | Overdue | Clean | 1 | Unique
ACT-0216 | Construction | Installation | Install project component | Critical | 2026-02-07 | 2026-02-21 | 2026-02-14 | 2026-02-22 | Completed | 100 | CONST-A | 2 | N/A | 2026-02-24 | 216 | Valid | Valid | Valid | 46075 | 8 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0217 | Construction | Installation | Install project component | Medium | 2026-01-20 | 2026-02-03 | 2026-01-27 |  | In Progress | 60 | CONST-A | 1 | N/A | 2026-02-08 | 217 | Valid | Incomplete | Valid |  |  |  | 207 | Yes | Overdue | Clean | 1 | Unique
ACT-0218 | Planning | Progress Review | Validate reported progress | Low | 2026-01-25 | 2026-02-12 | 2026-01-28 | 2026-02-14 | Completed | 100 | PLAN-B | 1 | N/A | 2026-02-16 | 218 | Valid | Valid | Valid | 46067 | 17 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0219 | Planning | Progress Review | Review weekly progress | Medium | 2026-04-26 | 2026-05-01 | 2026-04-25 |  | In Progress | 20 | PLAN-A | 0 | N/A | 2026-04-29 | 219 | Valid | Incomplete | Valid |  |  |  | 119 | Yes | Overdue | Clean | 1 | Unique
ACT-0220 | Engineering | Technical Query | Respond to engineering query | Medium | 2026-07-08 | 2026-07-18 | 2026-07-08 | 2026-07-24 | Completed | 100 | ENG-B | 3 | N/A | 2026-07-24 | 220 | Valid | Valid | Valid | 46227 | 16 | 6 |  | No | Late | Clean | 1 | Unique
ACT-0221 | Procurement | Delivery Tracking | Update delivery schedule | Low | 2026-07-06 | 2026-07-26 | 2026-07-06 | 2026-08-04 | Completed | 100 | PROC-B | 3 | N/A | 2026-08-09 | 221 | Valid | Valid | Valid | 46238 | 29 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0222 | Engineering | Design Review | Review technical specification | High | 2026-02-03 | 2026-02-12 | 2026-02-04 | 2026-02-17 | Completed | 100 | ENG-A | 0 | Approved | 2026-02-21 | 222 | Valid | Valid | Valid | 46070 | 13 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0223 | Document Control | Document Submission | Issue controlled document | High | 2026-07-06 | 2026-07-21 | 2026-07-06 | 2026-07-31 | Completed | 100 | DOC-A | 3 | Approved | 2026-08-03 | 223 | Valid | Valid | Valid | 46234 | 25 | 10 |  | No | Late | Clean | 1 | Unique
ACT-0224 | Engineering | Design Review | Check design compliance | Low | 2026-05-04 | 2026-05-15 | 2026-05-04 | 2026-05-27 | Completed | 100 | ENG-C | 1 | Approved | 2026-06-05 | 224 | Valid | Valid | Valid | 46169 | 23 | 12 |  | No | Late | Clean | 1 | Unique
ACT-0225 | Construction | Rework | Complete required rework | High | 2026-05-11 | 2026-05-19 | 2026-05-16 | 2026-05-30 | Completed | 100 | CONST-A | 4 | N/A | 2026-05-30 | 225 | Valid | Valid | Valid | 46172 | 14 | 11 |  | No | Late | Clean | 1 | Unique
ACT-0226 | Construction | Installation | Install project component | Low | 2026-06-22 | 2026-07-06 | 2026-06-23 |  | In Progress | 75 | CONST-B | 5 | N/A | 2026-07-06 | 226 | Valid | Incomplete | Valid |  |  |  | 60 | Yes | Overdue | Clean | 1 | Unique
ACT-0227 | Document Control | Revision Control | Maintain revision register | Medium | 2026-01-16 | 2026-01-25 | 2026-01-14 | 2026-01-27 | Completed | 100 | DOC-A | 5 | N/A | 2026-01-29 | 227 | Valid | Valid | Valid | 46049 | 13 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0228 | Construction | Rework | Correct installation issue | High | 2026-01-20 | 2026-02-04 | 2026-01-25 |  | In Progress | 60 | CONST-B | 2 | N/A | 2026-02-04 | 228 | Valid | Incomplete | Valid |  |  |  | 209 | Yes | Overdue | Clean | 1 | Unique
ACT-0229 | Construction | Punch List | Close punch item | Critical | 2026-02-08 | 2026-02-28 | 2026-02-13 | 2026-03-03 | Completed | 100 | CONST-A | 0 | N/A | 2026-03-14 | 229 | Valid | Valid | Valid | 46084 | 18 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0230 | Construction | Rework | Complete required rework | High | 2026-01-28 | 2026-02-04 | 2026-02-01 | 2026-02-10 | Completed | 100 | CONST-A | 0 | N/A | 2026-02-20 | 230 | Valid | Valid | Valid | 46063 | 9 | 6 |  | No | Late | Clean | 1 | Unique
ACT-0231 | Engineering | Drawing Revision | Update drawing comments | Medium | 2026-01-17 | 2026-01-28 | 2026-01-15 |  | On Hold | 40 | ENG-A | 3 | Pending | 2026-02-01 | 231 | Valid | Incomplete | Valid |  |  |  | 219 | Yes | Overdue | Clean | 1 | Unique
ACT-0232 | Engineering | Design Review | Review engineering drawing | Medium | 2026-01-20 | 2026-01-29 | 2026-01-23 |  | In Progress | 80 | ENG-A | 1 | Approved | 2026-01-25 | 232 | Valid | Incomplete | Valid |  |  |  | 211 | Yes | Overdue | Clean | 1 | Unique
ACT-0233 | Document Control | Revision Control | Maintain revision register | Medium | 2026-02-06 | 2026-02-10 | 2026-02-04 |  | In Progress | 10 | DOC-A | 4 | N/A | 2026-02-05 | 233 | Valid | Incomplete | Valid |  |  |  | 199 | Yes | Overdue | Clean | 1 | Unique
ACT-0234 | Document Control | Approval Tracking | Update approval register | Medium | 2026-01-12 | 2026-01-26 | 2026-01-14 | 2026-02-03 | Completed | 100 | DOC-A | 0 | Pending | 2026-02-04 | 234 | Valid | Valid | Valid | 46056 | 20 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0235 | Planning | Variance Review | Investigate progress variance | High | 2026-05-07 | 2026-05-10 | 2026-05-05 |  | In Progress | 30 | PLAN-A | 2 | N/A | 2026-05-22 | 235 | Valid | Incomplete | Valid |  |  |  | 109 | Yes | Overdue | Clean | 1 | Unique
ACT-0236 | Document Control | Transmittal | Issue transmittal record | Medium | 2026-05-09 | 2026-05-22 | 2026-05-13 | 2026-05-22 | Completed | 100 | DOC-A | 0 | Approved | 2026-05-30 | 236 | Valid | Valid | Valid | 46164 | 9 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0237 | Procurement | Purchase Review | Check purchase documentation | Medium | 2026-06-03 | 2026-06-12 | 2026-06-08 | 2026-06-20 | Completed | 100 | PROC-A | 3 | Pending | 2026-06-21 | 237 | Valid | Valid | Valid | 46193 | 12 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0238 | Construction | Rework | Complete required rework | Critical | 2026-02-18 | 2026-02-25 | 2026-02-18 | 2026-03-06 | Completed | 100 | CONST-C | 1 | N/A | 2026-03-17 | 238 | Valid | Valid | Valid | 46087 | 16 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0239 | Construction | Punch List | Verify punch completion | Medium | 2026-02-18 | 2026-03-07 |  |  | Not Started | 0 | CONST-A | 0 | N/A | 2026-02-25 | 239 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0240 | Construction | Installation | Install project component | Critical | 2026-02-25 | 2026-03-03 | 2026-02-25 | 2026-03-18 | Completed | 100 | CONST-C | 0 | N/A | 2026-03-22 | 240 | Valid | Valid | Valid | 46099 | 21 | 15 |  | No | Late | Clean | 1 | Unique
ACT-0241 | Planning | Progress Review | Review weekly progress | High | 2026-04-08 | 2026-04-12 | 2026-04-06 |  | In Progress | 20 | PLAN-A | 0 | N/A | 2026-04-16 | 241 | Valid | Incomplete | Valid |  |  |  | 138 | Yes | Overdue | Clean | 1 | Unique
ACT-0242 | Document Control | Approval Tracking | Update approval register | Critical | 2026-06-20 | 2026-07-02 | 2026-06-27 |  | In Progress | 30 | DOC-B | 2 | Approved | 2026-07-09 | 242 | Valid | Incomplete | Valid |  |  |  | 56 | Yes | Overdue | Clean | 1 | Unique
ACT-0243 | Planning | Lookahead Planning | Prepare lookahead plan | Medium | 2026-01-05 | 2026-01-25 | 2026-01-05 |  | In Progress | 10 | PLAN-A | 0 | N/A | 2026-01-15 | 243 | Valid | Incomplete | Valid |  |  |  | 229 | Yes | Overdue | Clean | 1 | Unique
ACT-0244 | Construction | Installation | Install project component | Medium | 2026-07-14 | 2026-07-18 | 2026-07-19 |  | In Progress | 95 | CONST-B | 2 | N/A | 2026-07-29 | 244 | Valid | Incomplete | Valid |  |  |  | 34 | Yes | Overdue | Clean | 1 | Unique
ACT-0245 | Engineering | Drawing Revision | Revise issued drawing | High | 2026-04-04 | 2026-04-14 | 2026-04-05 |  | On Hold | 40 | ENG-B | 2 | Rejected | 2026-04-18 | 245 | Valid | Incomplete | Valid |  |  |  | 139 | Yes | Overdue | Clean | 1 | Unique
ACT-0246 | Document Control | Transmittal | Track transmittal response | Medium | 2026-05-07 | 2026-05-27 | 2026-05-07 | 2026-05-27 | Completed | 100 | DOC-B | 3 | Approved | 2026-06-06 | 246 | Valid | Valid | Valid | 46169 | 20 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0247 | Document Control | Document Submission | Prepare document for submission | Medium | 2026-04-11 | 2026-04-18 | 2026-04-09 | 2026-04-18 | Completed | 100 | DOC-A | 1 | Approved | 2026-05-03 | 247 | Valid | Valid | Valid | 46130 | 9 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0248 | Construction | Punch List | Resolve outstanding punch item | High | 2026-02-14 | 2026-02-17 | 2026-02-18 |  | In Progress | 95 | CONST-B | 1 | N/A | 2026-02-27 | 248 | Valid | Incomplete | Valid |  |  |  | 185 | Yes | Overdue | Clean | 1 | Unique
ACT-0249 | QA/QC | Inspection | Verify completed installation | Medium | 2026-05-10 | 2026-05-16 |  |  | Not Started | 0 | QA-B | 0 | N/A | 2026-05-12 | 249 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0250 | Procurement | Purchase Review | Review purchase requirement | Low | 2026-02-26 | 2026-03-05 | 2026-03-04 |  | In Progress | 20 | PROC-B | 0 | Pending | 2026-03-19 | 250 | Valid | Incomplete | Valid |  |  |  | 171 | Yes | Overdue | Clean | 1 | Unique
ACT-0251 | Engineering | Material Review | Review material submittal | Medium | 2026-04-12 | 2026-04-25 | 2026-04-17 | 2026-05-02 | Completed | 100 | ENG-C | 3 | Approved | 2026-05-06 | 251 | Valid | Valid | Valid | 46144 | 15 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0252 | Planning | Schedule Update | Update milestone tracker | Medium | 2026-05-23 | 2026-06-07 | 2026-05-21 |  | In Progress | 60 | PLAN-A | 4 | N/A | 2026-06-05 | 252 | Valid | Incomplete | Valid |  |  |  | 93 | Yes | Overdue | Clean | 1 | Unique
ACT-0253 | Construction | Installation | Install project component | Critical | 2026-07-06 | 2026-07-09 | 2026-07-06 |  | In Progress | 90 | CONST-A | 5 | N/A | 2026-07-10 | 253 | Valid | Incomplete | Valid |  |  |  | 47 | Yes | Overdue | Clean | 1 | Unique
ACT-0254 | Document Control | Approval Tracking | Track pending approval | Critical | 2026-02-16 | 2026-02-24 | 2026-02-20 |  | In Progress | 90 | DOC-A | 0 | Pending | 2026-03-02 | 254 | Valid | Incomplete | Valid |  |  |  | 183 | Yes | Overdue | Clean | 1 | Unique
ACT-0255 | Engineering | Material Review | Check technical datasheet | Medium | 2026-03-16 | 2026-04-03 | 2026-03-20 |  | In Progress | 80 | ENG-B | 1 | Approved | 2026-03-23 | 255 | Valid | Incomplete | Valid |  |  |  | 155 | Yes | Overdue | Clean | 1 | Unique
ACT-0256 | Engineering | Design Review | Review engineering drawing | Medium | 2026-01-30 | 2026-02-10 | 2026-02-06 | 2026-02-04 | Completed | 100 | ENG-A | 2 | Approved | 2026-02-19 | 256 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0257 | Engineering | Material Review | Review material submittal | High | 2026-06-28 | 2026-07-12 |  |  | Not Started | 0 | ENG-A | 3 | Pending | 2026-07-05 | 257 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0258 | Procurement | Delivery Tracking | Confirm delivery status | Low | 2026-07-27 | 2026-08-07 | 2026-08-04 |  | In Progress | 30 | PROC-B | 0 | N/A | 2026-08-18 | 258 | Valid | Incomplete | Valid |  |  |  | 18 | Yes | Overdue | Clean | 1 | Unique
ACT-0259 | QA/QC | Test Package Review | Validate test records | High | 2026-02-22 | 2026-03-10 | 2026-02-20 |  | In Progress | 75 | QA-A | 3 | Approved | 2026-03-08 | 259 | Valid | Incomplete | Valid |  |  |  | 183 | Yes | Overdue | Clean | 1 | Unique
ACT-0260 | Engineering | Material Review | Review material submittal | High | 2026-05-19 | 2026-06-08 |  |  | Not Started | 0 | ENG-A | 0 | Approved | 2026-05-20 | 260 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0261 | Engineering | Design Review | Check design compliance | High | 2026-03-16 | 2026-03-29 | 2026-03-14 | 2026-04-02 | Completed | 100 | ENG-A | 0 | Approved | 2026-04-16 | 261 | Valid | Valid | Valid | 46114 | 19 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0262 | Document Control | Approval Tracking | Update approval register | Medium | 2026-04-03 | 2026-04-10 | 2026-04-03 | 2026-04-29 | Completed | 100 | DOC-A | 0 | Approved | 2026-05-17 | 262 | Valid | Valid | Valid | 46141 | 26 | 19 |  | No | Late | Clean | 1 | Unique
ACT-0263 | Procurement | Vendor Follow-up | Coordinate supplier action | Medium | 2026-06-20 | 2026-07-05 | 2026-06-30 |  | In Progress | 25 | PROC-A | 2 | N/A | 2026-06-30 | 263 | Valid | Incomplete | Valid |  |  |  | 53 | Yes | Overdue | Clean | 1 | Unique
ACT-0264 | QA/QC | NCR Follow-up | Review corrective evidence | Critical | 2026-06-18 | 2026-06-28 | 2026-06-16 | 2026-07-01 | Completed | 100 | QC-C | 1 | N/A | 2026-07-17 | 264 | Valid | Valid | Valid | 46204 | 15 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0265 | QA/QC | Inspection | Perform site inspection | Medium | 2026-06-23 | 2026-07-06 | 2026-06-27 | 2026-07-10 | Completed | 100 | QA-B | 1 | N/A | 2026-07-20 | 265 | Valid | Valid | Valid | 46213 | 13 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0266 | Planning | Lookahead Planning | Review upcoming activities | Unknown | 2026-06-20 | 2026-07-01 | 2026-06-26 | 2026-07-04 | Completed | 100 | PLAN-B | 3 | N/A | 2026-07-16 | 266 | Valid | Valid | Valid | 46207 | 8 | 3 |  | No | Late | Missing Priority | 1 | Unique
ACT-0267 | Planning | Schedule Update | Update milestone tracker | Medium | 2026-03-21 | 2026-03-31 | 2026-03-23 | 2026-04-02 | Completed | 100 | PLAN-B | 5 | N/A | 2026-04-08 | 267 | Valid | Valid | Valid | 46114 | 10 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0268 | Planning | Progress Review | Analyze progress status | Medium | 2026-07-24 | 2026-08-10 | 2026-07-22 |  | In Progress | 25 | PLAN-A | 3 | N/A | 2026-08-08 | 268 | Valid | Incomplete | Valid |  |  |  | 31 | Yes | Overdue | Clean | 1 | Unique
ACT-0269 | QA/QC | Test Package Review | Review test package | High | 2026-07-09 | 2026-07-28 | 2026-07-13 | 2026-08-15 | Completed | 100 | QA-B | 0 | Approved | 2026-08-19 | 269 | Valid | Valid | Valid | 46249 | 33 | 18 |  | No | Late | Clean | 1 | Unique
ACT-0270 | QA/QC | NCR Follow-up | Verify NCR closure | High | 2026-05-05 | 2026-05-08 | 2026-05-03 | 2026-05-06 | Completed | 100 | QA-A | 3 | N/A | 2026-05-22 | 270 | Valid | Valid | Valid | 46148 | 3 | -2 |  | No | On Time | Clean | 1 | Unique
ACT-0271 | Document Control | Approval Tracking | Update approval register | Medium | 2026-01-18 | 2026-01-24 | 2026-01-20 | 2026-02-04 | Completed | 100 | DOC-A | 3 | Approved | 2026-02-14 | 271 | Valid | Valid | Valid | 46057 | 15 | 11 |  | No | Late | Clean | 1 | Unique
ACT-0272 | Procurement | Purchase Review | Validate procurement status | High | 2026-02-19 | 2026-03-03 | 2026-02-26 |  | In Progress | 25 | PROC-A | 1 | Approved | 2026-02-28 | 272 | Valid | Incomplete | Valid |  |  |  | 177 | Yes | Overdue | Clean | 1 | Unique
ACT-0273 | Construction | Rework | Complete required rework | Medium | 2026-05-07 | 2026-05-21 |  |  | Not Started | 0 | CONST-A | 1 | N/A | 2026-05-18 | 273 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0274 | Document Control | Revision Control | Update document revision | High | 2026-06-14 | 2026-06-23 | 2026-06-15 |  | In Progress | 20 | DOC-B | 1 | N/A | 2026-07-03 | 274 | Valid | Incomplete | Valid |  |  |  | 68 | Yes | Overdue | Clean | 1 | Unique
ACT-0275 | Engineering | Design Review | Check design compliance | Critical | 2026-05-01 | 2026-05-19 | 2026-04-29 |  | In Progress | 70 | ENG-A | 1 | Pending | 2026-05-11 | 275 | Valid | Incomplete | Valid |  |  |  | 115 | Yes | Overdue | Clean | 1 | Unique
ACT-0276 | QA/QC | Testing | Conduct functional test | High | 2026-06-04 | 2026-06-22 | 2026-06-13 | 2026-06-27 | Completed | 100 | QC-C | 3 | N/A | 2026-07-05 | 276 | Valid | Valid | Valid | 46200 | 14 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0277 | Construction | Installation | Execute planned installation | Low | 2026-01-10 | 2026-01-13 | 2026-01-12 | 2026-01-15 | Completed | 100 | CONST-A | 1 | N/A | 2026-01-19 | 277 | Valid | Valid | Valid | 46037 | 3 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0278 | Planning | Schedule Update | Refresh progress schedule | Medium | 2026-01-30 | 2026-02-17 | 2026-02-03 |  | In Progress | 20 | PLAN-B | 1 | N/A | 2026-02-06 | 278 | Valid | Incomplete | Valid |  |  |  | 200 | Yes | Overdue | Clean | 1 | Unique
ACT-0279 | Engineering | Design Review | Check design compliance | Medium | 2026-02-25 | 2026-03-07 | 2026-03-02 | 2026-03-10 | Completed | 100 | ENG-C | 0 | Approved | 2026-03-16 | 279 | Valid | Valid | Valid | 46091 | 8 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0280 | Document Control | Transmittal | Prepare document transmittal | Low | 2026-06-25 | 2026-06-29 | 2026-06-29 | 2026-06-23 | Completed | 100 | DOC-B | 0 | Approved | 2026-06-26 | 280 | Valid | Check | Check |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0281 | Planning | Variance Review | Investigate progress variance | Medium | 2026-01-17 | 2026-01-22 | 2026-01-23 | 2026-01-14 | Completed | 100 | PLAN-A | 2 | N/A | 2026-01-27 | 281 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0282 | Engineering | Design Review | Review engineering drawing | High | 2026-06-23 | 2026-06-30 | 2026-07-02 | 2026-06-23 | Completed | 100 | ENG-A | 2 | Approved | 2026-07-03 | 282 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0283 | Engineering | Material Review | Validate material specification | Medium | 2026-04-13 | 2026-04-30 | 2026-04-11 | 2026-04-24 | Completed | 100 | ENG-A | 2 | Approved | 2026-04-29 | 283 | Valid | Valid | Valid | 46136 | 13 | -6 |  | No | On Time | Clean | 1 | Unique
ACT-0284 | Construction | Rework | Rectify field discrepancy | High | 2026-02-20 | 2026-03-06 | 2026-02-18 |  | In Progress | 25 | CONST-A | 1 | N/A | 2026-03-05 | 284 | Valid | Incomplete | Valid |  |  |  | 185 | Yes | Overdue | Clean | 1 | Unique
ACT-0285 | Document Control | Approval Tracking | Track pending approval | Low | 2026-06-21 | 2026-07-03 |  |  | Not Started | 0 | DOC-A | 3 | Pending | 2026-07-09 | 285 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0286 | Document Control | Transmittal | Track transmittal response | Medium | 2026-07-03 | 2026-07-08 | 2026-07-01 |  | In Progress | 90 | DOC-A | 2 | Pending | 2026-07-18 | 286 | Valid | Incomplete | Valid |  |  |  | 52 | Yes | Overdue | Clean | 1 | Unique
ACT-0287 | Engineering | Drawing Revision | Prepare revised drawing | High | 2026-05-11 | 2026-05-18 |  |  | Not Started | 0 | ENG-A | 1 | Pending | 2026-05-19 | 287 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0288 | Construction | Rework | Complete required rework | High | 2026-01-25 | 2026-02-10 | 2026-01-26 | 2026-02-18 | Completed | 100 | CONST-C | 0 | N/A | 2026-03-05 | 288 | Valid | Valid | Valid | 46071 | 23 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0289 | Planning | Schedule Update | Refresh progress schedule | Medium | 2026-05-27 | 2026-06-15 |  |  | Not Started | 0 | PLAN-A | 0 | N/A | 2026-06-05 | 289 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0290 | Planning | Variance Review | Investigate progress variance | Medium | 2026-01-18 | 2026-01-27 | 2026-01-16 | 2026-02-10 | Completed | 100 | PLAN-B | 2 | N/A | 2026-02-21 | 290 | Valid | Valid | Valid | 46063 | 25 | 14 |  | No | Late | Clean | 1 | Unique
ACT-0291 | Engineering | Drawing Revision | Revise issued drawing | Medium | 2026-06-16 | 2026-06-27 | 2026-06-16 |  | In Progress | 95 | ENG-C | 2 | Pending | 2026-06-24 | 291 | Valid | Incomplete | Valid |  |  |  | 67 | Yes | Overdue | Clean | 1 | Unique
ACT-0292 | Engineering | Design Review | Check design compliance | Medium | 2026-07-24 | 2026-08-01 | 2026-07-27 | 2026-07-22 | Completed | 100 | ENG-B | 3 | Approved | 2026-08-05 | 292 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0293 | Planning | Progress Review | Validate reported progress | Low | 2026-07-12 | 2026-07-15 | 2026-07-17 | 2026-07-03 | Completed | 100 | PLAN-A | 2 | N/A | 2026-07-08 | 293 | Valid | Check | Check |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0294 | Planning | Progress Review | Review weekly progress | Medium | 2026-06-07 | 2026-06-19 | 2026-06-05 | 2026-07-09 | Completed | 100 | PLAN-B | 2 | N/A | 2026-07-17 | 294 | Valid | Valid | Valid | 46212 | 34 | 20 |  | No | Late | Clean | 1 | Unique
ACT-0295 | Document Control | Transmittal | Issue transmittal record | High | 2026-02-09 | 2026-02-24 | 2026-02-09 |  | In Progress | 95 | DOC-A | 1 | Pending | 2026-02-26 | 295 | Valid | Incomplete | Valid |  |  |  | 194 | Yes | Overdue | Clean | 1 | Unique
ACT-0296 | QA/QC | NCR Follow-up | Review corrective evidence | Medium | 2026-06-26 | 2026-07-02 | 2026-06-24 | 2026-06-23 | Completed | 100 | QC-C | 2 | N/A | 2026-07-03 | 296 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0297 | Engineering | Technical Query | Respond to engineering query | Medium | 2026-05-31 | 2026-06-15 | 2026-06-05 |  | In Progress | 10 | ENG-B | 1 | N/A | 2026-06-05 | 297 | Valid | Incomplete | Valid |  |  |  | 78 | Yes | Overdue | Clean | 1 | Unique
ACT-0298 | Engineering | Design Review | Review engineering drawing | Medium | 2026-07-25 | 2026-08-01 | 2026-07-24 |  | In Progress | 10 | ENG-A | 2 | Pending | 2026-08-10 | 298 | Valid | Incomplete | Valid |  |  |  | 29 | Yes | Overdue | Clean | 1 | Unique
ACT-0299 | QA/QC | Test Package Review | Review test package | High | 2026-06-26 | 2026-07-15 | 2026-06-28 | 2026-07-12 | Completed | 100 | QC-C | 2 | Approved | 2026-07-21 | 299 | Valid | Valid | Valid | 46215 | 14 | -3 |  | No | On Time | Clean | 1 | Unique
ACT-0300 | Planning | Variance Review | Investigate progress variance | Medium | 2026-07-25 | 2026-08-06 | 2026-08-01 | 2026-08-13 | Completed | 100 | PLAN-B | 3 | N/A | 2026-08-21 | 300 | Valid | Valid | Valid | 46247 | 12 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0301 | Procurement | Vendor Follow-up | Coordinate supplier action | Critical | 2026-03-21 | 2026-04-06 | 2026-03-23 | 2026-04-13 | Completed | 100 | PROC-A | 1 | N/A | 2026-04-25 | 301 | Valid | Valid | Valid | 46125 | 21 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0302 | Construction | Site Preparation | Prepare work area | Medium | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-18 | Completed | 100 | CONST-C | 0 | N/A | 2026-03-19 | 302 | Valid | Valid | Valid | 46099 | 5 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0303 | Construction | Site Preparation | Complete site readiness activity | High | 2026-05-25 | 2026-06-07 |  |  | Not Started | 0 | CONST-A | 2 | N/A | 2026-06-10 | 303 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0304 | Document Control | Document Submission | Issue controlled document | Medium | 2026-05-24 | 2026-06-12 | 2026-05-22 |  | In Progress | 40 | DOC-B | 0 | Approved | 2026-06-07 | 304 | Valid | Incomplete | Valid |  |  |  | 92 | Yes | Overdue | Clean | 1 | Unique
ACT-0305 | Document Control | Document Submission | Submit project document | Unknown | 2026-04-29 | 2026-05-08 | 2026-05-07 |  | In Progress | 10 | DOC-B | 2 | Pending | 2026-05-10 | 305 | Valid | Incomplete | Valid |  |  |  | 107 | Yes | Overdue | Missing Priority | 1 | Unique
ACT-0306 | QA/QC | NCR Follow-up | Follow up corrective action | Critical | 2026-07-21 | 2026-08-03 | 2026-07-19 | 2026-08-09 | Completed | 100 | QC-C | 2 | N/A | 2026-08-19 | 306 | Valid | Valid | Valid | 46243 | 21 | 6 |  | No | Late | Clean | 1 | Unique
ACT-0307 | Engineering | Design Review | Review engineering drawing | Critical | 2026-07-21 | 2026-08-09 | 2026-07-21 |  | In Progress | 90 | ENG-C | 1 | Pending | 2026-08-07 | 307 | Valid | Incomplete | Valid |  |  |  | 32 | Yes | Overdue | Clean | 1 | Unique
ACT-0308 | Document Control | Approval Tracking | Update approval register | High | 2026-01-23 | 2026-01-29 |  |  | Not Started | 0 | DOC-A | 2 | Pending | 2026-01-25 | 308 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0309 | Engineering | Technical Query | Respond to engineering query | Low | 2026-03-04 | 2026-03-14 | 2026-03-04 | 2026-03-14 | Completed | 100 | ENG-C | 1 | N/A | 2026-03-17 | 309 | Valid | Valid | Valid | 46095 | 10 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0310 | Engineering | Design Review | Review technical specification | High | 2026-07-03 | 2026-07-07 | 2026-07-06 | 2026-07-08 | Completed | 100 | ENG-B | 1 | Approved | 2026-07-22 | 310 | Valid | Valid | Valid | 46211 | 2 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0311 | QA/QC | Inspection | Verify completed installation | Medium | 2026-03-02 | 2026-03-08 | 2026-03-10 |  | In Progress | 40 | QA-B | 4 | N/A | 2026-03-14 | 311 | Valid | Incomplete | Valid |  |  |  | 165 | Yes | Overdue | Clean | 1 | Unique
ACT-0312 | Planning | Lookahead Planning | Prepare lookahead plan | Medium | 2026-05-27 | 2026-06-02 | 2026-06-02 | 2026-06-05 | Completed | 100 | PLAN-A | 4 | N/A | 2026-06-14 | 312 | Valid | Valid | Valid | 46178 | 3 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0313 | Procurement | Delivery Tracking | Track material delivery | Medium | 2026-06-19 | 2026-07-07 | 2026-06-25 | 2026-07-29 | Completed | 100 | PROC-A | 0 | N/A | 2026-08-16 | 313 | Valid | Valid | Valid | 46232 | 34 | 22 |  | No | Late | Clean | 1 | Unique
ACT-0314 | Procurement | Purchase Review | Check purchase documentation | Medium | 2026-03-20 | 2026-03-24 | 2026-03-25 |  | In Progress | 90 | PROC-A | 2 | Pending | 2026-03-27 | 314 | Valid | Incomplete | Valid |  |  |  | 150 | Yes | Overdue | Clean | 1 | Unique
ACT-0315 | QA/QC | Test Package Review | Check package completeness | High | 2026-03-24 | 2026-04-13 | 2026-03-31 | 2026-04-27 | Completed | 100 | QC-C | 0 | Approved | 2026-05-04 | 315 | Valid | Valid | Valid | 46139 | 27 | 14 |  | No | Late | Clean | 1 | Unique
ACT-0316 | Planning | Variance Review | Investigate progress variance | High | 2026-02-08 | 2026-02-20 | 2026-02-06 | 2026-02-19 | Completed | 100 | PLAN-A | 1 | N/A | 2026-02-24 | 316 | Valid | Valid | Valid | 46072 | 13 | -1 |  | No | On Time | Clean | 1 | Unique
ACT-0317 | Procurement | Vendor Follow-up | Coordinate supplier action | Medium | 2026-07-11 | 2026-07-15 | 2026-07-17 |  | In Progress | 90 | PROC-B | 0 | N/A | 2026-08-04 | 317 | Valid | Incomplete | Valid |  |  |  | 36 | Yes | Overdue | Clean | 1 | Unique
ACT-0318 | Procurement | Vendor Follow-up | Follow up vendor response | Medium | 2026-05-24 | 2026-06-12 | 2026-05-28 | 2026-06-16 | Completed | 100 | PROC-A | 2 | N/A | 2026-06-25 | 318 | Valid | Valid | Valid | 46189 | 19 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0319 | Construction | Installation | Install project component | Medium | 2026-01-07 | 2026-01-16 | 2026-01-12 | 2026-01-16 | Completed | 100 | CONST-A | 1 | N/A | 2026-01-30 | 319 | Valid | Valid | Valid | 46038 | 4 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0320 | Engineering | Drawing Revision | Prepare revised drawing | High | 2026-04-06 | 2026-04-09 | 2026-04-06 | 2026-04-14 | Completed | 100 | ENG-B | 0 | Approved | 2026-04-25 | 320 | Valid | Valid | Valid | 46126 | 8 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0321 | Construction | Rework | Correct installation issue | Low | 2026-06-20 | 2026-07-02 | 2026-06-28 | 2026-07-09 | Completed | 100 | CONST-C | 2 | N/A | 2026-07-27 | 321 | Valid | Valid | Valid | 46212 | 11 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0322 | Construction | Rework | Rectify field discrepancy | Medium | 2026-06-04 | 2026-06-08 | 2026-06-02 | 2026-06-30 | Completed | 100 | CONST-B | 1 | N/A | 2026-07-11 | 322 | Valid | Valid | Valid | 46203 | 28 | 22 |  | No | Late | Clean | 1 | Unique
ACT-0323 | Procurement | Material Request | Coordinate material requirement | High | 2026-04-27 | 2026-05-04 | 2026-04-27 | 2026-05-15 | Completed | 100 | PROC-A | 0 | Approved | 2026-05-18 | 323 | Valid | Valid | Valid | 46157 | 18 | 11 |  | No | Late | Clean | 1 | Unique
ACT-0324 | Construction | Site Preparation | Coordinate access preparation | Low | 2026-06-26 | 2026-07-13 | 2026-06-25 | 2026-07-16 | Completed | 100 | CONST-C | 0 | N/A | 2026-07-20 | 324 | Valid | Valid | Valid | 46219 | 21 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0325 | Construction | Punch List | Resolve outstanding punch item | Medium | 2026-05-31 | 2026-06-06 |  |  | Not Started | 0 | CONST-C | 0 | N/A | 2026-06-05 | 325 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0326 | Document Control | Document Submission | Issue controlled document | High | 2026-03-18 | 2026-03-22 | 2026-03-16 | 2026-03-21 | Completed | 100 | DOC-A | 0 | Approved | 2026-03-25 | 326 | Valid | Valid | Valid | 46102 | 5 | -1 |  | No | On Time | Clean | 1 | Unique
ACT-0327 | Construction | Site Preparation | Prepare work area | High | 2026-04-02 | 2026-04-18 | 2026-04-08 | 2026-05-01 | Completed | 100 | CONST-C | 0 | N/A | 2026-05-17 | 327 | Valid | Valid | Valid | 46143 | 23 | 13 |  | No | Late | Clean | 1 | Unique
ACT-0328 | Planning | Progress Review | Analyze progress status | Low | 2026-05-06 | 2026-05-09 | 2026-05-04 | 2026-05-09 | Completed | 100 | PLAN-A | 2 | N/A | 2026-05-26 | 328 | Valid | Valid | Valid | 46151 | 5 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0329 | Document Control | Approval Tracking | Update approval register | Medium | 2026-01-16 | 2026-02-03 | 2026-01-21 |  | In Progress | 95 | DOC-A | 3 | Approved | 2026-02-08 | 329 | Valid | Incomplete | Valid |  |  |  | 213 | Yes | Overdue | Clean | 1 | Unique
ACT-0330 | Construction | Site Preparation | Complete site readiness activity | High | 2026-01-26 | 2026-02-06 | 2026-01-27 | 2026-02-15 | Completed | 100 | CONST-C | 2 | N/A | 2026-02-15 | 330 | Valid | Valid | Valid | 46068 | 19 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0331 | Construction | Installation | Install project component | High | 2026-06-30 | 2026-07-12 | 2026-07-03 | 2026-07-12 | Completed | 100 | CONST-B | 0 | N/A | 2026-07-29 | 331 | Valid | Valid | Valid | 46215 | 9 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0332 | Construction | Site Preparation | Coordinate access preparation | Medium | 2026-02-26 | 2026-03-13 | 2026-03-03 | 2026-03-27 | Completed | 100 | CONST-C | 1 | N/A | 2026-04-05 | 332 | Valid | Valid | Valid | 46108 | 24 | 14 |  | No | Late | Clean | 1 | Unique
ACT-0333 | QA/QC | Test Package Review | Validate test records | Medium | 2026-06-22 | 2026-06-27 | 2026-06-28 | 2026-07-02 | Completed | 100 | QC-C | 0 | Approved | 2026-07-12 | 333 | Valid | Valid | Valid | 46205 | 4 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0334 | Construction | Installation | Complete field installation | Medium | 2026-06-16 | 2026-06-18 | 2026-06-17 |  | In Progress | 80 | CONST-B | 1 | N/A | 2026-06-19 | 334 | Valid | Incomplete | Valid |  |  |  | 66 | Yes | Overdue | Clean | 1 | Unique
ACT-0335 | QA/QC | Inspection | Conduct quality inspection | Low | 2026-04-13 | 2026-04-27 | 2026-04-11 | 2026-05-02 | Completed | 100 | QC-C | 4 | N/A | 2026-05-07 | 335 | Valid | Valid | Valid | 46144 | 21 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0336 | Construction | Installation | Complete field installation | High | 2026-07-29 | 2026-08-16 | 2026-08-06 |  | In Progress | 25 | CONST-A | 2 | N/A | 2026-08-17 | 336 | Valid | Incomplete | Valid |  |  |  | 16 | Yes | Overdue | Clean | 1 | Unique
ACT-0337 | Planning | Progress Review | Review weekly progress | Critical | 2026-07-23 | 2026-08-06 | 2026-07-25 |  | In Progress | 75 | PLAN-A | 0 | N/A | 2026-07-27 | 337 | Valid | Incomplete | Valid |  |  |  | 28 | Yes | Overdue | Clean | 1 | Unique
ACT-0338 | Construction | Site Preparation | Complete site readiness activity | Critical | 2026-03-16 | 2026-03-25 | 2026-03-22 | 2026-04-21 | Completed | 100 | CONST-C | 0 | N/A | 2026-05-04 | 338 | Valid | Valid | Valid | 46133 | 30 | 27 |  | No | Late | Clean | 1 | Unique
ACT-0339 | Engineering | Design Review | Review technical specification | Medium | 2026-02-03 | 2026-02-21 | 2026-02-09 | 2026-02-16 | Completed | 100 | ENG-B | 2 | Pending | 2026-03-06 | 339 | Valid | Valid | Valid | 46069 | 7 | -5 |  | No | On Time | Clean | 1 | Unique
ACT-0340 | Procurement | Delivery Tracking | Confirm delivery status | High | 2026-06-04 | 2026-06-06 | 2026-06-07 |  | In Progress | 95 | PROC-B | 0 | N/A | 2026-06-17 | 340 | Valid | Incomplete | Valid |  |  |  | 76 | Yes | Overdue | Clean | 1 | Unique
ACT-0341 | Document Control | Document Submission | Issue controlled document | High | 2026-03-09 | 2026-03-20 | 2026-03-14 |  | In Progress | 20 | DOC-B | 1 | Pending | 2026-03-24 | 341 | Valid | Incomplete | Valid |  |  |  | 161 | Yes | Overdue | Clean | 1 | Unique
ACT-0342 | QA/QC | NCR Follow-up | Follow up corrective action | Critical | 2026-06-28 | 2026-07-06 | 2026-07-02 |  | In Progress | 30 | QA-A | 3 | N/A | 2026-07-13 | 342 | Valid | Incomplete | Valid |  |  |  | 51 | Yes | Overdue | Clean | 1 | Unique
ACT-0343 | Procurement | Material Request | Prepare material request | High | 2026-06-23 | 2026-07-10 | 2026-07-03 |  | In Progress | 10 | PROC-B | 3 | Pending | 2026-07-13 | 343 | Valid | Incomplete | Valid |  |  |  | 50 | Yes | Overdue | Clean | 1 | Unique
ACT-0344 | Document Control | Transmittal | Issue transmittal record | Medium | 2026-07-19 | 2026-08-06 | 2026-07-21 | 2026-08-20 | Completed | 100 | DOC-B | 2 | Approved | 2026-08-22 | 344 | Valid | Valid | Valid | 46254 | 30 | 14 |  | No | Late | Clean | 1 | Unique
ACT-0345 | QA/QC | Testing | Perform pressure test | Critical | 2026-07-02 | 2026-07-20 | 2026-07-04 | 2026-07-25 | Completed | 100 | QA-B | 1 | N/A | 2026-08-04 | 345 | Valid | Valid | Valid | 46228 | 21 | 5 |  | No | Late | Clean | 2 | Duplicate
ACT-0345 | Construction | Site Preparation | Prepare work area | Medium | 2026-03-06 | 2026-03-16 | 2026-03-06 | 2026-03-21 | Completed | 100 | CONST-B | 0 | N/A | 2026-04-01 | 346 | Valid | Valid | Valid | 46102 | 15 | 5 |  | No | Late | Clean | 2 | Duplicate
ACT-0347 | Procurement | Delivery Tracking | Confirm delivery status | Medium | 2026-02-07 | 2026-02-27 | 2026-02-13 |  | In Progress | 60 | PROC-B | 0 | N/A | 2026-02-17 | 347 | Valid | Incomplete | Valid |  |  |  | 190 | Yes | Overdue | Clean | 1 | Unique
ACT-0348 | Procurement | Vendor Follow-up | Check vendor document status | Medium | 2026-06-15 | 2026-07-03 | 2026-06-14 | 2026-07-08 | Completed | 100 | PROC-B | 3 | N/A | 2026-07-09 | 348 | Valid | Valid | Valid | 46211 | 24 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0349 | Engineering | Drawing Revision | Revise issued drawing | Medium | 2026-03-11 | 2026-03-28 | 2026-03-12 | 2026-04-01 | Completed | 100 | ENG-B | 1 | Approved | 2026-04-09 | 349 | Valid | Valid | Valid | 46113 | 20 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0350 | Engineering | Design Review | Check design compliance | High | 2026-06-09 | 2026-06-17 | 2026-06-08 |  | In Progress | 40 | ENG-C | 1 | Pending | 2026-06-23 | 350 | Valid | Incomplete | Valid |  |  |  | 75 | Yes | Overdue | Clean | 1 | Unique
ACT-0351 | Construction | Installation | Install project component | Unknown | 2026-05-03 | 2026-05-09 | 2026-05-01 | 2026-05-05 | Completed | 100 | CONST-A | 1 | N/A | 2026-05-17 | 351 | Valid | Valid | Valid | 46147 | 4 | -4 |  | No | On Time | Missing Priority | 1 | Unique
ACT-0352 | Engineering | Technical Query | Resolve site technical query | Medium | 2026-06-21 | 2026-07-02 | 2026-06-20 |  | In Progress | 50 | ENG-B | 2 | N/A | 2026-07-06 | 352 | Valid | Incomplete | Valid |  |  |  | 63 | Yes | Overdue | Clean | 1 | Unique
ACT-0353 | Construction | Punch List | Close punch item | Medium | 2026-03-06 | 2026-03-16 | 2026-03-06 |  | In Progress | 25 | CONST-A | 1 | N/A | 2026-03-09 | 353 | Valid | Incomplete | Valid |  |  |  | 169 | Yes | Overdue | Clean | 1 | Unique
ACT-0354 | Document Control | Approval Tracking | Update approval register | Low | 2026-07-21 | 2026-08-04 | 2026-07-24 |  | In Progress | 60 | DOC-B | 0 | Pending | 2026-08-02 | 354 | Valid | Incomplete | Valid |  |  |  | 29 | Yes | Overdue | Clean | 1 | Unique
ACT-0355 | Construction | Punch List | Resolve outstanding punch item | High | 2026-01-12 | 2026-01-15 | 2026-01-15 |  | In Progress | 70 | CONST-B | 1 | N/A | 2026-02-01 | 355 | Valid | Incomplete | Valid |  |  |  | 219 | Yes | Overdue | Clean | 1 | Unique
ACT-0356 | Construction | Punch List | Resolve outstanding punch item | Medium | 2026-06-05 | 2026-06-21 | 2026-06-05 | 2026-06-23 | Completed | 100 | CONST-B | 2 | N/A | 2026-07-02 | 356 | Valid | Valid | Valid | 46196 | 18 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0357 | Construction | Punch List | Close punch item | Medium | 2026-04-08 | 2026-04-23 | 2026-04-11 |  | In Progress | 50 | CONST-A | 0 | N/A | 2026-04-28 | 357 | Valid | Incomplete | Valid |  |  |  | 133 | Yes | Overdue | Clean | 1 | Unique
ACT-0358 | Planning | Variance Review | No Description | Medium | 2026-07-20 | 2026-08-04 | 2026-07-21 |  | In Progress | 75 | PLAN-B | 1 | N/A | 2026-08-03 | 358 | Valid | Incomplete | Valid |  |  |  | 32 | Yes | Overdue | Missing Description | 1 | Unique
ACT-0359 | QA/QC | Testing | Complete system testing | High | 2026-04-14 | 2026-04-28 | 2026-04-21 | 2026-05-10 | Completed | 100 | QA-B | 2 | N/A | 2026-05-18 | 359 | Valid | Valid | Valid | 46152 | 19 | 12 |  | No | Late | Clean | 1 | Unique
ACT-0360 | Planning | Lookahead Planning | Review upcoming activities | Medium | 2026-01-22 | 2026-01-29 | 2026-01-26 | 2026-02-06 | Completed | 100 | PLAN-A | 2 | N/A | 2026-02-21 | 360 | Valid | Valid | Valid | 46059 | 11 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0361 | QA/QC | Testing | Conduct functional test | Critical | 2026-01-10 | 2026-01-17 | 2026-01-11 | 2026-01-28 | Completed | 100 | QA-A | 0 | N/A | 2026-01-30 | 361 | Valid | Valid | Valid | 46050 | 17 | 11 |  | No | Late | Clean | 1 | Unique
ACT-0362 | Engineering | Drawing Revision | Update drawing comments | Medium | 2026-07-25 | 2026-08-11 | 2026-07-23 | 2026-08-19 | Completed | 100 | ENG-B | 3 | Pending | 2026-08-20 | 362 | Valid | Valid | Valid | 46253 | 27 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0363 | Procurement | Material Request | Coordinate material requirement | Medium | 2026-02-23 | 2026-03-05 | 2026-02-27 |  | In Progress | 70 | PROC-B | 0 | Rejected | 2026-03-05 | 363 | Valid | Incomplete | Valid |  |  |  | 176 | Yes | Overdue | Clean | 1 | Unique
ACT-0364 | Planning | Schedule Update | Update milestone tracker | High | 2026-02-27 | 2026-03-16 | 2026-02-27 |  | In Progress | 25 | PLAN-A | 1 | N/A | 2026-02-28 | 364 | Valid | Incomplete | Valid |  |  |  | 176 | Yes | Overdue | Clean | 1 | Unique
ACT-0365 | QA/QC | NCR Follow-up | Follow up corrective action | Medium | 2026-01-18 | 2026-01-26 | 2026-01-20 | 2026-02-10 | Completed | 100 | QA-A | 2 | N/A | 2026-02-28 | 365 | Valid | Valid | Valid | 46063 | 21 | 15 |  | No | Late | Clean | 1 | Unique
ACT-0366 | QA/QC | Testing | Conduct functional test | Critical | 2026-06-02 | 2026-06-19 | 2026-06-08 | 2026-07-07 | Completed | 100 | QC-C | 1 | N/A | 2026-07-17 | 366 | Valid | Valid | Valid | 46210 | 29 | 18 |  | No | Late | Clean | 1 | Unique
ACT-0367 | Engineering | Technical Query | Respond to engineering query | Medium | 2026-05-22 | 2026-05-27 | 2026-05-24 |  | In Progress | 70 | ENG-C | 2 | N/A | 2026-05-24 | 367 | Valid | Incomplete | Valid |  |  |  | 90 | Yes | Overdue | Clean | 1 | Unique
ACT-0368 | QA/QC | Testing | Perform pressure test | High | 2026-05-09 | 2026-05-25 | 2026-05-22 | 2026-05-22 | Completed | 100 | QC-C | 1 | N/A | 2026-06-01 | 368 | Valid | Valid | Valid | 46164 | 0 | -3 |  | No | On Time | Clean | 1 | Unique
ACT-0369 | Construction | Punch List | Close punch item | Medium | 2026-04-30 | 2026-05-11 | 2026-05-03 | 2026-05-08 | Completed | 100 | CONST-A | 1 | N/A | 2026-05-13 | 369 | Valid | Valid | Valid | 46150 | 5 | -3 |  | No | On Time | Clean | 1 | Unique
ACT-0370 | Construction | Site Preparation | Coordinate access preparation | Medium | 2026-07-08 | 2026-07-12 | 2026-07-13 | 2026-07-14 | Completed | 100 | CONST-A | 1 | N/A | 2026-07-31 | 370 | Valid | Valid | Valid | 46217 | 1 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0371 | Construction | Site Preparation | Complete site readiness activity | High | 2026-02-02 | 2026-02-07 | 2026-02-08 | 2026-02-19 | Completed | 100 | CONST-A | 3 | N/A | 2026-02-25 | 371 | Valid | Valid | Valid | 46072 | 11 | 12 |  | No | Late | Clean | 1 | Unique
ACT-0372 | Construction | Installation | Complete field installation | Medium | 2026-04-14 | 2026-05-01 | 2026-04-15 |  | In Progress | 50 | CONST-A | 0 | N/A | 2026-04-17 | 372 | Valid | Incomplete | Valid |  |  |  | 129 | Yes | Overdue | Clean | 1 | Unique
ACT-0373 | Document Control | Revision Control | Maintain revision register | Medium | 2026-01-25 | 2026-02-10 | 2026-01-31 |  | In Progress | 50 | DOC-B | 2 | N/A | 2026-02-01 | 373 | Valid | Incomplete | Valid |  |  |  | 203 | Yes | Overdue | Clean | 1 | Unique
ACT-0374 | Construction | Installation | Install project component | Low | 2026-03-01 | 2026-03-19 | 2026-03-06 |  | In Progress | 30 | CONST-C | 0 | N/A | 2026-03-13 | 374 | Valid | Incomplete | Valid |  |  |  | 169 | Yes | Overdue | Clean | 1 | Unique
ACT-0375 | Construction | Punch List | Resolve outstanding punch item | High | 2026-04-21 | 2026-04-26 | 2026-04-20 |  | In Progress | 20 | CONST-C | 0 | N/A | 2026-04-25 | 375 | Valid | Incomplete | Valid |  |  |  | 124 | Yes | Overdue | Clean | 1 | Unique
ACT-0376 | Construction | Site Preparation | Coordinate access preparation | Medium | 2026-06-07 | 2026-06-23 | 2026-06-07 |  | In Progress | 50 | CONST-C | 3 | N/A | 2026-06-20 | 376 | Valid | Incomplete | Valid |  |  |  | 76 | Yes | Overdue | Clean | 1 | Unique
ACT-0377 | Construction | Site Preparation | Coordinate access preparation | Medium | 2026-05-24 | 2026-06-01 | 2026-05-22 | 2026-06-06 | Completed | 100 | CONST-A | 1 | N/A | 2026-06-18 | 377 | Valid | Valid | Valid | 46179 | 15 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0378 | Planning | Lookahead Planning | Update short-term plan | Low | 2026-02-08 | 2026-02-19 |  |  | Not Started | 0 | PLAN-B | 5 | N/A | 2026-02-14 | 378 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0379 | Engineering | Technical Query | Respond to engineering query | Medium | 2026-05-31 | 2026-06-20 | 2026-06-05 | 2026-06-26 | Completed | 100 | ENG-A | 1 | N/A | 2026-07-14 | 379 | Valid | Valid | Valid | 46199 | 21 | 6 |  | No | Late | Clean | 1 | Unique
ACT-0380 | QA/QC | NCR Follow-up | Follow up corrective action | Medium | 2026-05-30 | 2026-06-07 | 2026-05-31 | 2026-05-31 | Completed | 100 | QA-A | 3 | N/A | 2026-06-18 | 380 | Valid | Valid | Valid | 46173 | 0 | -7 |  | No | On Time | Clean | 1 | Unique
ACT-0381 | Construction | Site Preparation | Prepare work area | High | 2026-06-01 | 2026-06-15 |  |  | Not Started | 0 | CONST-B | 0 | N/A | 2026-06-11 | 381 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0382 | Document Control | Approval Tracking | Follow up document approval | Critical | 2026-02-04 | 2026-02-13 | 2026-02-10 |  | In Progress | 10 | DOC-A | 0 | Pending | 2026-02-27 | 382 | Valid | Incomplete | Valid |  |  |  | 193 | Yes | Overdue | Clean | 1 | Unique
ACT-0383 | QA/QC | Testing | Conduct functional test | Low | 2026-07-11 | 2026-07-25 | 2026-07-09 |  | In Progress | 20 | QA-B | 0 | N/A | 2026-07-18 | 383 | Valid | Incomplete | Valid |  |  |  | 44 | Yes | Overdue | Clean | 1 | Unique
ACT-0384 | Engineering | Technical Query | Resolve site technical query | Medium | 2026-07-14 | 2026-07-17 | 2026-07-15 | 2026-07-30 | Completed | 100 | ENG-B | 2 | N/A | 2026-08-03 | 384 | Valid | Valid | Valid | 46233 | 15 | 13 |  | No | Late | Clean | 1 | Unique
ACT-0385 | Construction | Rework | Complete required rework | High | 2026-02-24 | 2026-03-15 | 2026-02-27 | 2026-03-19 | Completed | 100 | CONST-C | 2 | N/A | 2026-03-29 | 385 | Valid | Valid | Valid | 46100 | 20 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0386 | Document Control | Document Submission | Submit project document | High | 2026-04-23 | 2026-05-06 | 2026-04-23 | 2026-05-19 | Completed | 100 | DOC-A | 0 | Rejected | 2026-06-02 | 386 | Valid | Valid | Valid | 46161 | 26 | 13 |  | No | Late | Clean | 1 | Unique
ACT-0387 | Construction | Punch List | Close punch item | High | 2026-02-13 | 2026-02-17 | 2026-02-25 |  | In Progress | 40 | CONST-B | 0 | N/A | 2026-02-28 | 387 | Valid | Incomplete | Valid |  |  |  | 178 | Yes | Overdue | Clean | 1 | Unique
ACT-0388 | Construction | Installation | Install project component | Medium | 2026-05-22 | 2026-05-30 | 2026-05-28 | 2026-06-08 | Completed | 100 | CONST-C | 2 | N/A | 2026-06-12 | 388 | Valid | Valid | Valid | 46181 | 11 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0389 | Planning | Schedule Update | Refresh progress schedule | High | 2026-06-23 | 2026-07-11 |  |  | Not Started | 0 | PLAN-A | 0 | N/A | 2026-07-02 | 389 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0390 | Procurement | Delivery Tracking | Track material delivery | Medium | 2026-01-07 | 2026-01-11 | 2026-01-15 | 2026-01-30 | Completed | 100 | PROC-B | 3 | N/A | 2026-01-30 | 390 | Valid | Valid | Valid | 46052 | 15 | 19 |  | No | Late | Clean | 1 | Unique
ACT-0391 | Document Control | Approval Tracking | Track pending approval | Critical | 2026-05-15 | 2026-05-20 | 2026-05-13 | 2026-05-21 | Completed | 100 | DOC-A | 0 | Pending | 2026-06-07 | 391 | Valid | Valid | Valid | 46163 | 8 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0392 | Engineering | Technical Query | Clarify design requirement | Medium | 2026-07-14 | 2026-07-21 |  |  | Not Started | 0 | ENG-C | 2 | N/A | 2026-07-25 | 392 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0393 | QA/QC | NCR Follow-up | Follow up corrective action | High | 2026-04-14 | 2026-04-16 | 2026-04-15 |  | In Progress | 50 | QA-A | 3 | N/A | 2026-04-19 | 393 | Valid | Incomplete | Valid |  |  |  | 129 | Yes | Overdue | Clean | 1 | Unique
ACT-0394 | Planning | Progress Review | Validate reported progress | Medium | 2026-02-13 | 2026-02-28 | 2026-02-17 | 2026-02-28 | Completed | 100 | PLAN-A | 0 | N/A | 2026-03-04 | 394 | Valid | Valid | Valid | 46081 | 11 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0395 | Document Control | Transmittal | Track transmittal response | High | 2026-05-19 | 2026-05-25 | 2026-05-26 |  | In Progress | 25 | DOC-A | 0 | Pending | 2026-05-29 | 395 | Valid | Incomplete | Valid |  |  |  | 88 | Yes | Overdue | Clean | 1 | Unique
ACT-0396 | QA/QC | Testing | Complete system testing | Low | 2026-03-27 | 2026-04-11 | 2026-03-26 | 2026-04-17 | Completed | 100 | QA-A | 2 | N/A | 2026-04-25 | 396 | Valid | Valid | Valid | 46129 | 22 | 6 |  | No | Late | Clean | 1 | Unique
ACT-0397 | Procurement | Material Request | Prepare material request | Medium | 2026-07-19 | 2026-07-29 | 2026-07-17 |  | In Progress | 30 | PROC-A | 2 | Pending | 2026-08-01 | 397 | Valid | Incomplete | Valid |  |  |  | 36 | Yes | Overdue | Clean | 1 | Unique
ACT-0398 | Construction | Rework | Rectify field discrepancy | High | 2026-02-21 | 2026-03-07 | 2026-02-26 | 2026-03-20 | Completed | 100 | CONST-B | 2 | N/A | 2026-03-20 | 398 | Valid | Valid | Valid | 46101 | 22 | 13 |  | No | Late | Clean | 1 | Unique
ACT-0399 | Document Control | Revision Control | Maintain revision register | High | 2026-02-25 | 2026-03-05 |  |  | Not Started | 10 | DOC-B | 4 | N/A | 2026-03-11 | 399 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0400 | Planning | Variance Review | Analyze schedule variance | Medium | 2026-07-22 | 2026-07-25 | 2026-07-25 | 2026-07-17 | Completed | 100 | PLAN-A | 4 | N/A | 2026-08-04 | 400 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0401 | Construction | Rework | Complete required rework | High | 2026-01-15 | 2026-01-24 | 2026-01-14 | 2026-02-10 | Completed | 100 | CONST-A | 1 | N/A | 2026-02-11 | 401 | Valid | Valid | Valid | 46063 | 27 | 17 |  | No | Late | Clean | 1 | Unique
ACT-0402 | QA/QC | Test Package Review | Check package completeness | High | 2026-03-19 | 2026-04-04 | 2026-03-19 |  | In Progress | 70 | QA-A | 3 | Pending | 2026-04-04 | 402 | Valid | Incomplete | Valid |  |  |  | 156 | Yes | Overdue | Clean | 1 | Unique
ACT-0403 | Engineering | Drawing Revision | Update drawing comments | Medium | 2026-04-30 | 2026-05-02 | 2026-05-10 | 2026-05-05 | Completed | 100 | ENG-C | 1 | Approved | 2026-05-10 | 403 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0404 | Planning | Schedule Update | Update activity schedule | High | 2026-06-16 | 2026-06-29 | 2026-06-15 |  | In Progress | 75 | PLAN-B | 1 | N/A | 2026-06-20 | 404 | Valid | Incomplete | Valid |  |  |  | 68 | Yes | Overdue | Clean | 1 | Unique
ACT-0405 | Construction | Installation | Complete field installation | Critical | 2026-05-29 | 2026-06-04 | 2026-06-05 | 2026-06-24 | Completed | 100 | CONST-B | 0 | N/A | 2026-07-08 | 405 | Valid | Valid | Valid | 46197 | 19 | 20 |  | No | Late | Clean | 1 | Unique
ACT-0406 | Construction | Installation | Complete field installation | Critical | 2026-01-05 | 2026-01-15 |  |  | Not Started | 0 | CONST-C | 1 | N/A | 2026-01-20 | 406 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0407 | Procurement | Purchase Review | Review purchase requirement | Medium | 2026-06-22 | 2026-07-09 | 2026-06-21 | 2026-07-24 | Completed | 100 | PROC-A | 3 | Approved | 2026-08-10 | 407 | Valid | Valid | Valid | 46227 | 33 | 15 |  | No | Late | Clean | 1 | Unique
ACT-0408 | Engineering | Drawing Revision | Revise issued drawing | High | 2026-01-14 | 2026-01-20 | 2026-01-12 | 2026-01-12 | Completed | 100 | ENG-A | 4 | Approved | 2026-01-25 | 408 | Valid | Valid | Valid | 46034 | 0 | -8 |  | No | On Time | Clean | 1 | Unique
ACT-0409 | Engineering | Technical Query | Respond to engineering query | High | 2026-07-03 | 2026-07-23 | 2026-07-06 | 2026-08-04 | Completed | 100 | ENG-B | 4 | N/A | 2026-08-06 | 409 | Valid | Valid | Valid | 46238 | 29 | 12 |  | No | Late | Clean | 1 | Unique
ACT-0410 | QA/QC | Test Package Review | Review test package | High | 2026-05-25 | 2026-05-29 | 2026-05-31 | 2026-06-14 | Completed | 100 | QC-C | 1 | Approved | 2026-06-20 | 410 | Valid | Valid | Valid | 46187 | 14 | 16 |  | No | Late | Clean | 1 | Unique
ACT-0411 | Engineering | Design Review | Check design compliance | High | 2026-06-08 | 2026-06-19 | 2026-06-11 | 2026-06-19 | Completed | 100 | ENG-B | 1 | Pending | 2026-07-07 | 411 | Valid | Valid | Valid | 46192 | 8 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0412 | Construction | Rework | Complete required rework | High | 2026-06-10 | 2026-06-19 | 2026-06-13 | 2026-06-28 | Completed | 100 | CONST-C | 1 | N/A | 2026-07-01 | 412 | Valid | Valid | Valid | 46201 | 15 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0413 | Procurement | Purchase Review | Validate procurement status | Low | 2026-04-04 | 2026-04-23 | 2026-04-09 |  | In Progress | 20 | PROC-A | 0 | Pending | 2026-04-19 | 413 | Valid | Incomplete | Valid |  |  |  | 135 | Yes | Overdue | Clean | 1 | Unique
ACT-0414 | Engineering | Technical Query | Clarify design requirement | Medium | 2026-05-30 | 2026-06-01 | 2026-06-06 | 2026-06-15 | Completed | 100 | ENG-A | 1 | N/A | 2026-06-30 | 414 | Valid | Valid | Valid | 46188 | 9 | 14 |  | No | Late | Clean | 1 | Unique
ACT-0415 | Planning | Variance Review | Analyze schedule variance | High | 2026-05-22 | 2026-06-03 | 2026-05-20 |  | In Progress | 10 | PLAN-B | 3 | N/A | 2026-05-29 | 415 | Valid | Incomplete | Valid |  |  |  | 94 | Yes | Overdue | Clean | 1 | Unique
ACT-0416 | Construction | Installation | Complete field installation | Medium | 2026-03-30 | 2026-04-12 |  |  | Not Started | 0 | CONST-B | 0 | N/A | 2026-03-30 | 416 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0417 | Document Control | Revision Control | Maintain revision register | High | 2026-02-21 | 2026-02-26 | 2026-02-22 | 2026-02-18 | Completed | 100 | DOC-A | 0 | N/A | 2026-03-03 | 417 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0418 | Construction | Punch List | Verify punch completion | Medium | 2026-03-23 | 2026-03-31 | 2026-03-28 | 2026-04-16 | Completed | 100 | CONST-B | 0 | N/A | 2026-04-18 | 418 | Valid | Valid | Valid | 46128 | 19 | 16 |  | No | Late | Clean | 1 | Unique
ACT-0419 | Construction | Rework | Rectify field discrepancy | Medium | 2026-04-02 | 2026-04-19 | 2026-03-31 | 2026-04-26 | Completed | 100 | CONST-C | 3 | N/A | 2026-05-12 | 419 | Valid | Valid | Valid | 46138 | 26 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0420 | Document Control | Revision Control | Maintain revision register | Low | 2026-04-14 | 2026-05-02 | 2026-04-14 |  | In Progress | 50 | DOC-A | 1 | N/A | 2026-04-15 | 420 | Valid | Incomplete | Valid |  |  |  | 130 | Yes | Overdue | Clean | 1 | Unique
ACT-0421 | Construction | Site Preparation | Prepare work area | Medium | 2026-03-25 | 2026-04-02 | 2026-03-29 | 2026-04-10 | Completed | 100 | CONST-B | 1 | N/A | 2026-04-13 | 421 | Valid | Valid | Valid | 46122 | 12 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0422 | Engineering | Technical Query | Resolve site technical query | Low | 2026-06-13 | 2026-07-02 | 2026-06-18 | 2026-07-02 | Completed | 100 | ENG-C | 0 | N/A | 2026-07-11 | 422 | Valid | Valid | Valid | 46205 | 14 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0423 | QA/QC | Inspection | Verify completed installation | High | 2026-04-01 | 2026-04-20 | 2026-04-06 | 2026-04-16 | Completed | 100 | QA-A | 0 | N/A | 2026-04-17 | 423 | Valid | Valid | Valid | 46128 | 10 | -4 |  | No | On Time | Clean | 1 | Unique
ACT-0424 | Construction | Punch List | Resolve outstanding punch item | High | 2026-06-05 | 2026-06-21 | 2026-06-09 | 2026-07-06 | Completed | 100 | CONST-A | 2 | N/A | 2026-07-23 | 424 | Valid | Valid | Valid | 46209 | 27 | 15 |  | No | Late | Clean | 1 | Unique
ACT-0425 | Document Control | Approval Tracking | Update approval register | Medium | 2026-07-29 | 2026-08-14 | 2026-07-27 | 2026-08-10 | Completed | 100 | DOC-B | 1 | Pending | 2026-08-14 | 425 | Valid | Valid | Valid | 46244 | 14 | -4 |  | No | On Time | Clean | 1 | Unique
ACT-0426 | Document Control | Approval Tracking | Track pending approval | High | 2026-06-24 | 2026-07-06 | 2026-06-22 |  | In Progress | 10 | DOC-B | 0 | Pending | 2026-07-07 | 426 | Valid | Incomplete | Valid |  |  |  | 61 | Yes | Overdue | Clean | 1 | Unique
ACT-0427 | Procurement | Delivery Tracking | Confirm delivery status | High | 2026-02-06 | 2026-02-24 | 2026-02-12 | 2026-02-23 | Completed | 100 | PROC-B | 2 | N/A | 2026-03-04 | 427 | Valid | Valid | Valid | 46076 | 11 | -1 |  | No | On Time | Clean | 1 | Unique
ACT-0428 | Construction | Rework | Correct installation issue | High | 2026-05-25 | 2026-06-01 | 2026-05-25 |  | In Progress | 60 | CONST-C | 1 | N/A | 2026-06-04 | 428 | Valid | Incomplete | Valid |  |  |  | 89 | Yes | Overdue | Clean | 1 | Unique
ACT-0429 | Planning | Progress Review | Analyze progress status | High | 2026-07-13 | 2026-08-02 | 2026-07-16 | 2026-07-31 | Completed | 100 | PLAN-A | 0 | N/A | 2026-08-14 | 429 | Valid | Valid | Valid | 46234 | 15 | -2 |  | No | On Time | Clean | 1 | Unique
ACT-0430 | QA/QC | Test Package Review | No Description | High | 2026-06-29 | 2026-07-13 | 2026-06-29 |  | On Hold | 20 | QA-A | 3 | Approved | 2026-06-29 | 430 | Valid | Incomplete | Valid |  |  |  | 54 | Yes | Overdue | Missing Description | 1 | Unique
ACT-0431 | Planning | Variance Review | Review delayed activity | Medium | 2026-06-11 | 2026-07-01 | 2026-06-14 | 2026-07-19 | Completed | 100 | PLAN-B | 2 | N/A | 2026-07-28 | 431 | Valid | Valid | Valid | 46222 | 35 | 18 |  | No | Late | Clean | 1 | Unique
ACT-0432 | Planning | Lookahead Planning | Prepare lookahead plan | High | 2026-06-10 | 2026-06-28 | 2026-06-13 | 2026-07-05 | Completed | 100 | PLAN-A | 1 | N/A | 2026-07-06 | 432 | Valid | Valid | Valid | 46208 | 22 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0433 | Planning | Lookahead Planning | Prepare lookahead plan | High | 2026-01-12 | 2026-01-21 | 2026-01-10 |  | In Progress | 60 | PLAN-B | 1 | N/A | 2026-01-15 | 433 | Valid | Incomplete | Valid |  |  |  | 224 | Yes | Overdue | Clean | 1 | Unique
ACT-0434 | Engineering | Material Review | Validate material specification | High | 2026-02-13 | 2026-02-24 | 2026-02-12 |  | In Progress | 20 | ENG-C | 2 | Pending | 2026-02-27 | 434 | Valid | Incomplete | Valid |  |  |  | 191 | Yes | Overdue | Clean | 1 | Unique
ACT-0435 | Construction | Punch List | Close punch item | Medium | 2026-04-21 | 2026-05-07 | 2026-04-21 |  | In Progress | 60 | CONST-B | 1 | N/A | 2026-05-05 | 435 | Valid | Incomplete | Valid |  |  |  | 123 | Yes | Overdue | Clean | 1 | Unique
ACT-0436 | QA/QC | Testing | Perform pressure test | High | 2026-06-01 | 2026-06-18 | 2026-05-30 | 2026-06-17 | Completed | 100 | QA-A | 1 | N/A | 2026-06-28 | 436 | Valid | Valid | Valid | 46190 | 18 | -1 |  | No | On Time | Clean | 1 | Unique
ACT-0437 | Document Control | Approval Tracking | Update approval register | Medium | 2026-06-02 | 2026-06-19 | 2026-06-03 | 2026-06-21 | Completed | 100 | DOC-B | 3 | Approved | 2026-06-29 | 437 | Valid | Valid | Valid | 46194 | 18 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0438 | Construction | Installation | Complete field installation | Medium | 2026-07-13 | 2026-07-17 | 2026-07-12 | 2026-07-17 | Completed | 100 | CONST-A | 3 | N/A | 2026-08-03 | 438 | Valid | Valid | Valid | 46220 | 5 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0439 | Construction | Rework | Rectify field discrepancy | Unknown | 2026-04-22 | 2026-05-05 | 2026-04-22 |  | In Progress | 10 | CONST-C | 2 | N/A | 2026-05-01 | 439 | Valid | Incomplete | Valid |  |  |  | 122 | Yes | Overdue | Missing Priority | 1 | Unique
ACT-0440 | Procurement | Delivery Tracking | Track material delivery | High | 2026-06-02 | 2026-06-09 | 2026-06-04 |  | On Hold | 40 | PROC-A | 0 | N/A | 2026-06-20 | 440 | Valid | Incomplete | Valid |  |  |  | 79 | Yes | Overdue | Clean | 1 | Unique
ACT-0441 | Procurement | Delivery Tracking | Confirm delivery status | Medium | 2026-03-17 | 2026-03-27 | 2026-03-18 | 2026-04-11 | Completed | 100 | PROC-B | 1 | N/A | 2026-04-15 | 441 | Valid | Valid | Valid | 46123 | 24 | 15 |  | No | Late | Clean | 1 | Unique
ACT-0442 | QA/QC | Testing | Perform pressure test | High | 2026-03-06 | 2026-03-23 | 2026-03-09 | 2026-04-21 | Completed | 100 | QA-B | 4 | N/A | 2026-04-25 | 442 | Valid | Valid | Valid | 46133 | 43 | 29 |  | No | Late | Clean | 1 | Unique
ACT-0443 | Procurement | Purchase Review | Validate procurement status | Medium | 2026-04-27 | 2026-05-04 | 2026-05-03 |  | In Progress | 90 | PROC-A | 0 | Approved | 2026-05-04 | 443 | Valid | Incomplete | Valid |  |  |  | 111 | Yes | Overdue | Clean | 1 | Unique
ACT-0444 | Construction | Rework | Complete required rework | Medium | 2026-07-16 | 2026-08-04 | 2026-07-17 | 2026-08-06 | Completed | 100 | CONST-A | 1 | N/A | 2026-08-19 | 444 | Valid | Valid | Valid | 46240 | 20 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0445 | QA/QC | Test Package Review | Check package completeness | High | 2026-05-20 | 2026-05-23 | 2026-05-19 |  | In Progress | 90 | QA-A | 3 | Pending | 2026-05-27 | 445 | Valid | Incomplete | Valid |  |  |  | 95 | Yes | Overdue | Clean | 1 | Unique
ACT-0446 | QA/QC | Test Package Review | Check package completeness | High | 2026-07-15 | 2026-07-24 | 2026-07-16 | 2026-08-02 | Completed | 100 | QA-A | 2 | Approved | 2026-08-19 | 446 | Valid | Valid | Valid | 46236 | 17 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0447 | Planning | Schedule Update | Update activity schedule | Medium | 2026-05-19 | 2026-05-24 | 2026-05-23 | 2026-05-26 | Completed | 100 | PLAN-A | 0 | N/A | 2026-05-28 | 447 | Valid | Valid | Valid | 46168 | 3 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0448 | Document Control | Revision Control | Maintain revision register | High | 2026-07-05 | 2026-07-10 | 2026-07-04 |  | In Progress | 90 | DOC-A | 1 | N/A | 2026-07-09 | 448 | Valid | Incomplete | Valid |  |  |  | 49 | Yes | Overdue | Clean | 1 | Unique
ACT-0449 | Planning | Lookahead Planning | Review upcoming activities | Medium | 2026-01-24 | 2026-02-09 | 2026-01-24 |  | In Progress | 50 | PLAN-B | 0 | N/A | 2026-01-26 | 449 | Valid | Incomplete | Valid |  |  |  | 210 | Yes | Overdue | Clean | 1 | Unique
ACT-0450 | Procurement | Purchase Review | Validate procurement status | Medium | 2026-01-20 | 2026-01-30 | 2026-01-28 | 2026-02-02 | Completed | 100 | PROC-B | 4 | Approved | 2026-02-07 | 450 | Valid | Valid | Valid | 46055 | 5 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0451 | Engineering | Material Review | Review material submittal | High | 2026-02-01 | 2026-02-17 | 2026-02-04 | 2026-03-03 | Completed | 100 | ENG-A | 0 | Approved | 2026-03-18 | 451 | Valid | Valid | Valid | 46084 | 27 | 14 |  | No | Late | Clean | 1 | Unique
ACT-0452 | Planning | Schedule Update | Update activity schedule | High | 2026-03-14 | 2026-03-20 | 2026-03-17 |  | In Progress | 75 | PLAN-B | 2 | N/A | 2026-04-01 | 452 | Valid | Incomplete | Valid |  |  |  | 158 | Yes | Overdue | Clean | 1 | Unique
ACT-0453 | Construction | Installation | Execute planned installation | Medium | 2026-04-13 | 2026-04-30 | 2026-04-11 | 2026-05-04 | Completed | 100 | CONST-C | 0 | N/A | 2026-05-05 | 453 | Valid | Valid | Valid | 46146 | 23 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0454 | Document Control | Document Submission | Prepare document for submission | Medium | 2026-04-02 | 2026-04-06 | 2026-04-03 | 2026-04-04 | Completed | 100 | DOC-B | 1 | Pending | 2026-04-10 | 454 | Valid | Valid | Valid | 46116 | 1 | -2 |  | No | On Time | Clean | 1 | Unique
ACT-0455 | Planning | Schedule Update | Update milestone tracker | High | 2026-05-09 | 2026-05-13 | 2026-05-08 | 2026-05-17 | Completed | 100 | PLAN-A | 0 | N/A | 2026-06-04 | 455 | Valid | Valid | Valid | 46159 | 9 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0456 | Construction | Installation | Execute planned installation | High | 2026-05-12 | 2026-05-31 | 2026-05-19 | 2026-05-22 | Completed | 100 | CONST-C | 0 | N/A | 2026-06-01 | 456 | Valid | Valid | Valid | 46164 | 3 | -9 |  | No | On Time | Clean | 1 | Unique
ACT-0457 | Engineering | Design Review | Review engineering drawing | High | 2026-06-24 | 2026-07-12 | 2026-06-23 | 2026-07-03 | Completed | 100 | ENG-C | 1 | Pending | 2026-07-04 | 457 | Valid | Valid | Valid | 46206 | 10 | -9 |  | No | On Time | Clean | 1 | Unique
ACT-0458 | Engineering | Design Review | Check design compliance | Critical | 2026-06-12 | 2026-06-15 | 2026-06-13 |  | In Progress | 20 | ENG-A | 1 | Pending | 2026-07-01 | 458 | Valid | Incomplete | Valid |  |  |  | 70 | Yes | Overdue | Clean | 1 | Unique
ACT-0459 | Procurement | Material Request | Prepare material request | Medium | 2026-07-28 | 2026-08-06 |  |  | Not Started | 0 | PROC-B | 0 | Pending | 2026-08-09 | 459 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0460 | Engineering | Drawing Revision | Update drawing comments | High | 2026-07-27 | 2026-08-04 | 2026-07-28 |  | In Progress | 20 | ENG-C | 0 | Approved | 2026-08-02 | 460 | Valid | Incomplete | Valid |  |  |  | 25 | Yes | Overdue | Clean | 1 | Unique
ACT-0461 | QA/QC | Testing | Perform pressure test | Medium | 2026-06-02 | 2026-06-05 | 2026-06-05 | 2026-06-02 | Completed | 100 | QA-A | 0 | N/A | 2026-06-17 | 461 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0462 | Engineering | Drawing Revision | Revise issued drawing | High | 2026-06-05 | 2026-06-16 | 2026-06-09 |  | In Progress | 90 | ENG-A | 0 | Pending | 2026-06-16 | 462 | Valid | Incomplete | Valid |  |  |  | 74 | Yes | Overdue | Clean | 1 | Unique
ACT-0463 | Construction | Installation | Execute planned installation | Medium | 2026-05-12 | 2026-05-16 | 2026-05-10 |  | In Progress | 10 | CONST-A | 1 | N/A | 2026-05-16 | 463 | Valid | Incomplete | Valid |  |  |  | 104 | Yes | Overdue | Clean | 1 | Unique
ACT-0464 | Document Control | Document Submission | Issue controlled document | Medium | 2026-07-18 | 2026-08-06 | 2026-07-16 | 2026-08-12 | Completed | 100 | DOC-B | 0 | Approved | 2026-08-16 | 464 | Valid | Valid | Valid | 46246 | 27 | 6 |  | No | Late | Clean | 1 | Unique
ACT-0465 | Construction | Punch List | Resolve outstanding punch item | Critical | 2026-01-18 | 2026-01-31 | 2026-01-18 |  | In Progress | 10 | CONST-C | 0 | N/A | 2026-01-19 | 465 | Valid | Incomplete | Valid |  |  |  | 216 | Yes | Overdue | Clean | 1 | Unique
ACT-0466 | Engineering | Design Review | Check design compliance | Medium | 2026-01-23 | 2026-02-01 | 2026-01-26 | 2026-02-03 | Completed | 100 | ENG-B | 2 | Approved | 2026-02-06 | 466 | Valid | Valid | Valid | 46056 | 8 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0467 | QA/QC | Testing | Complete system testing | Medium | 2026-02-25 | 2026-03-11 | 2026-03-01 | 2026-03-15 | Completed | 100 | QC-C | 1 | N/A | 2026-03-21 | 467 | Valid | Valid | Valid | 46096 | 14 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0468 | Construction | Rework | Complete required rework | Medium | 2026-07-08 | 2026-07-16 | 2026-07-10 |  | In Progress | 25 | CONST-A | 0 | N/A | 2026-07-28 | 468 | Valid | Incomplete | Valid |  |  |  | 43 | Yes | Overdue | Clean | 1 | Unique
ACT-0469 | QA/QC | Inspection | Verify completed installation | Medium | 2026-02-17 | 2026-03-01 | 2026-02-18 |  | In Progress | 25 | QA-A | 1 | N/A | 2026-03-07 | 469 | Valid | Incomplete | Valid |  |  |  | 185 | Yes | Overdue | Clean | 1 | Unique
ACT-0470 | Engineering | Material Review | Review material submittal | High | 2026-05-03 | 2026-05-13 |  |  | Not Started | 0 | ENG-B | 1 | Approved | 2026-05-10 | 470 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0471 | Construction | Punch List | Resolve outstanding punch item | Critical | 2026-05-31 | 2026-06-02 | 2026-06-05 | 2026-06-24 | Completed | 100 | CONST-C | 1 | N/A | 2026-07-07 | 471 | Valid | Valid | Valid | 46197 | 19 | 22 |  | No | Late | Clean | 1 | Unique
ACT-0472 | QA/QC | Inspection | Verify completed installation | Medium | 2026-01-26 | 2026-02-14 | 2026-01-27 |  | In Progress | 30 | QA-A | 0 | N/A | 2026-02-05 | 472 | Valid | Incomplete | Valid |  |  |  | 207 | Yes | Overdue | Clean | 1 | Unique
ACT-0473 | Planning | Schedule Update | Update activity schedule | Medium | 2026-03-24 | 2026-03-31 | 2026-03-29 | 2026-03-24 | Completed | 100 | PLAN-B | 1 | N/A | 2026-03-28 | 473 | Valid | Check | Check |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0474 | Engineering | Technical Query | Respond to engineering query | Medium | 2026-06-16 | 2026-06-18 | 2026-06-25 | 2026-06-30 | Completed | 100 | ENG-B | 0 | N/A | 2026-07-13 | 474 | Valid | Valid | Valid | 46203 | 5 | 12 |  | No | Late | Clean | 1 | Unique
ACT-0475 | Planning | Progress Review | Analyze progress status | Low | 2026-03-31 | 2026-04-03 | 2026-04-04 | 2026-04-02 | Completed | 100 | PLAN-A | 1 | N/A | 2026-04-16 | 475 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0476 | QA/QC | Testing | Complete system testing | Medium | 2026-01-22 | 2026-02-10 | 2026-01-27 | 2026-03-10 | Completed | 100 | QC-C | 0 | N/A | 2026-03-25 | 476 | Valid | Valid | Valid | 46091 | 42 | 28 |  | No | Late | Clean | 1 | Unique
ACT-0477 | Document Control | Revision Control | Maintain revision register | High | 2026-03-28 | 2026-04-10 | 2026-03-26 | 2026-04-13 | Completed | 100 | DOC-B | 1 | N/A | 2026-04-27 | 477 | Valid | Valid | Valid | 46125 | 18 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0478 | Construction | Installation | Install project component | High | 2026-06-27 | 2026-07-16 | 2026-06-27 |  | In Progress | 20 | CONST-A | 0 | N/A | 2026-07-11 | 478 | Valid | Incomplete | Valid |  |  |  | 56 | Yes | Overdue | Clean | 1 | Unique
ACT-0479 | Engineering | Drawing Revision | Update drawing comments | Critical | 2026-01-24 | 2026-01-29 | 2026-01-26 | 2026-02-05 | Completed | 100 | ENG-B | 0 | Pending | 2026-02-05 | 479 | Valid | Valid | Valid | 46058 | 10 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0480 | Construction | Punch List | Verify punch completion | Medium | 2026-04-28 | 2026-04-30 | 2026-05-03 | 2026-05-14 | Completed | 100 | CONST-B | 4 | N/A | 2026-05-24 | 480 | Valid | Valid | Valid | 46156 | 11 | 14 |  | No | Late | Clean | 1 | Unique
ACT-0481 | Construction | Site Preparation | Complete site readiness activity | High | 2026-07-02 | 2026-07-20 | 2026-07-03 | 2026-07-28 | Completed | 100 | CONST-B | 2 | N/A | 2026-08-02 | 481 | Valid | Valid | Valid | 46231 | 25 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0482 | QA/QC | NCR Follow-up | Verify NCR closure | High | 2026-01-17 | 2026-01-23 | 2026-01-21 | 2026-02-08 | Completed | 100 | QA-A | 2 | N/A | 2026-02-17 | 482 | Valid | Valid | Valid | 46061 | 18 | 16 |  | No | Late | Clean | 1 | Unique
ACT-0483 | Document Control | Revision Control | Update document revision | Medium | 2026-01-15 | 2026-01-27 | 2026-01-24 | 2026-01-27 | Completed | 100 | DOC-B | 2 | N/A | 2026-02-06 | 483 | Valid | Valid | Valid | 46049 | 3 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0484 | Engineering | Material Review | Check technical datasheet | Critical | 2026-05-21 | 2026-06-01 | 2026-05-24 | 2026-06-18 | Completed | 100 | ENG-A | 4 | Pending | 2026-06-22 | 484 | Valid | Valid | Valid | 46191 | 25 | 17 |  | No | Late | Clean | 1 | Unique
ACT-0485 | Document Control | Transmittal | Track transmittal response | High | 2026-05-06 | 2026-05-17 | 2026-05-05 |  | In Progress | 90 | DOC-B | 0 | Pending | 2026-05-19 | 485 | Valid | Incomplete | Valid |  |  |  | 109 | Yes | Overdue | Clean | 1 | Unique
ACT-0486 | Planning | Variance Review | Analyze schedule variance | Medium | 2026-05-26 | 2026-05-31 | 2026-05-24 | 2026-06-11 | Completed | 100 | PLAN-A | 0 | N/A | 2026-06-12 | 486 | Valid | Valid | Valid | 46184 | 18 | 11 |  | No | Late | Clean | 1 | Unique
ACT-0487 | Construction | Punch List | No Description | Medium | 2026-01-26 | 2026-02-14 | 2026-01-25 |  | In Progress | 70 | CONST-A | 0 | N/A | 2026-02-10 | 487 | Valid | Incomplete | Valid |  |  |  | 209 | Yes | Overdue | Missing Description | 1 | Unique
ACT-0488 | Document Control | Transmittal | Issue transmittal record | Medium | 2026-04-24 | 2026-05-07 | 2026-04-22 | 2026-05-07 | Completed | 100 | DOC-B | 1 | Approved | 2026-05-13 | 488 | Valid | Valid | Valid | 46149 | 15 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0489 | Procurement | Purchase Review | Validate procurement status | Medium | 2026-07-10 | 2026-07-25 | 2026-07-16 | 2026-08-11 | Completed | 100 | PROC-A | 0 | Approved | 2026-08-20 | 489 | Valid | Valid | Valid | 46245 | 26 | 17 |  | No | Late | Clean | 1 | Unique
ACT-0490 | Document Control | Approval Tracking | Track pending approval | Low | 2026-06-17 | 2026-06-27 | 2026-06-15 | 2026-06-27 | Completed | 100 | DOC-B | 0 | Approved | 2026-07-09 | 490 | Valid | Valid | Valid | 46200 | 12 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0491 | Construction | Installation | Install project component | High | 2026-03-23 | 2026-04-09 | 2026-03-21 | 2026-04-19 | Completed | 100 | CONST-A | 0 | N/A | 2026-05-04 | 491 | Valid | Valid | Valid | 46131 | 29 | 10 |  | No | Late | Clean | 1 | Unique
ACT-0492 | Planning | Lookahead Planning | Review upcoming activities | Medium | 2026-06-30 | 2026-07-09 |  |  | Not Started | 0 | PLAN-A | 2 | N/A | 2026-07-15 | 492 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0493 | Construction | Site Preparation | Coordinate access preparation | Medium | 2026-04-26 | 2026-05-06 | 2026-04-29 | 2026-05-14 | Completed | 100 | CONST-A | 1 | N/A | 2026-06-01 | 493 | Valid | Valid | Valid | 46156 | 15 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0494 | Procurement | Vendor Follow-up | No Description | Low | 2026-03-27 | 2026-04-12 | 2026-03-29 | 2026-04-27 | Completed | 100 | PROC-A | 1 | N/A | 2026-05-08 | 494 | Valid | Valid | Valid | 46139 | 29 | 15 |  | No | Late | Missing Description | 1 | Unique
ACT-0495 | QA/QC | Inspection | Conduct quality inspection | Medium | 2026-06-14 | 2026-06-21 | 2026-06-19 | 2026-07-01 | Completed | 100 | QA-B | 0 | N/A | 2026-07-10 | 495 | Valid | Valid | Valid | 46204 | 12 | 10 |  | No | Late | Clean | 1 | Unique
ACT-0496 | Planning | Lookahead Planning | Prepare lookahead plan | Medium | 2026-04-05 | 2026-04-11 |  |  | Not Started | 0 | PLAN-B | 1 | N/A | 2026-04-16 | 496 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0497 | Construction | Punch List | Close punch item | Medium | 2026-05-13 | 2026-05-22 | 2026-05-19 |  | In Progress | 95 | CONST-C | 3 | N/A | 2026-06-04 | 497 | Valid | Incomplete | Valid |  |  |  | 95 | Yes | Overdue | Clean | 1 | Unique
ACT-0498 | Planning | Schedule Update | Refresh progress schedule | Medium | 2026-01-24 | 2026-01-29 | 2026-01-29 | 2026-01-28 | Completed | 100 | PLAN-B | 1 | N/A | 2026-02-11 | 498 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0499 | Engineering | Technical Query | Resolve site technical query | High | 2026-02-04 | 2026-02-13 | 2026-02-04 | 2026-02-07 | Completed | 100 | ENG-B | 0 | N/A | 2026-02-09 | 499 | Valid | Valid | Valid | 46060 | 3 | -6 |  | No | On Time | Clean | 1 | Unique
ACT-0500 | Planning | Schedule Update | Update activity schedule | Low | 2026-05-08 | 2026-05-23 |  |  | Not Started | 0 | PLAN-A | 0 | N/A | 2026-05-24 | 500 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0501 | Construction | Site Preparation | Prepare work area | Low | 2026-06-24 | 2026-06-26 | 2026-06-29 | 2026-06-19 | Completed | 100 | CONST-C | 3 | N/A | 2026-06-24 | 501 | Valid | Check | Check |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0502 | QA/QC | Inspection | Perform site inspection | High | 2026-03-17 | 2026-04-06 | 2026-03-21 |  | In Progress | 80 | QA-A | 0 | N/A | 2026-04-08 | 502 | Valid | Incomplete | Valid |  |  |  | 154 | Yes | Overdue | Clean | 1 | Unique
ACT-0503 | Construction | Punch List | Verify punch completion | Medium | 2026-07-17 | 2026-08-05 |  |  | Not Started | 0 | CONST-C | 2 | N/A | 2026-07-23 | 503 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0504 | Procurement | Purchase Review | Validate procurement status | High | 2026-02-21 | 2026-03-09 | 2026-02-28 | 2026-04-01 | Completed | 100 | PROC-A | 1 | Approved | 2026-04-14 | 504 | Valid | Valid | Valid | 46113 | 32 | 23 |  | No | Late | Clean | 1 | Unique
ACT-0505 | Procurement | Delivery Tracking | Track material delivery | Medium | 2026-05-18 | 2026-05-24 | 2026-05-16 | 2026-06-01 | Completed | 100 | PROC-A | 0 | N/A | 2026-06-16 | 505 | Valid | Valid | Valid | 46174 | 16 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0506 | QA/QC | Test Package Review | Validate test records | High | 2026-06-29 | 2026-07-15 | 2026-07-07 | 2026-07-30 | Completed | 100 | QC-C | 3 | Pending | 2026-08-14 | 506 | Valid | Valid | Valid | 46233 | 23 | 15 |  | No | Late | Clean | 1 | Unique
ACT-0507 | QA/QC | Inspection | Conduct quality inspection | Medium | 2026-01-31 | 2026-02-14 | 2026-02-01 |  | In Progress | 25 | QA-A | 1 | N/A | 2026-02-19 | 507 | Valid | Incomplete | Valid |  |  |  | 202 | Yes | Overdue | Clean | 1 | Unique
ACT-0508 | Procurement | Vendor Follow-up | Follow up vendor response | Medium | 2026-02-24 | 2026-03-08 | 2026-03-02 | 2026-03-13 | Completed | 100 | PROC-B | 1 | N/A | 2026-03-28 | 508 | Valid | Valid | Valid | 46094 | 11 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0509 | Procurement | Delivery Tracking | Update delivery schedule | Critical | 2026-04-06 | 2026-04-23 | 2026-04-21 | 2026-04-27 | Completed | 100 | PROC-A | 0 | N/A | 2026-05-11 | 509 | Valid | Valid | Valid | 46139 | 6 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0510 | Engineering | Material Review | Validate material specification | Medium | 2026-02-08 | 2026-02-10 | 2026-02-11 |  | In Progress | 60 | ENG-C | 1 | Pending | 2026-02-20 | 510 | Valid | Incomplete | Valid |  |  |  | 192 | Yes | Overdue | Clean | 1 | Unique
ACT-0511 | Construction | Installation | Execute planned installation | High | 2026-07-20 | 2026-08-06 | 2026-07-23 | 2026-08-11 | Completed | 100 | CONST-C | 0 | N/A | 2026-08-21 | 511 | Valid | Valid | Valid | 46245 | 19 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0512 | Construction | Installation | Install project component | High | 2026-02-04 | 2026-02-18 | 2026-02-04 |  | In Progress | 10 | CONST-C | 0 | N/A | 2026-02-21 | 512 | Valid | Incomplete | Valid |  |  |  | 199 | Yes | Overdue | Clean | 1 | Unique
ACT-0513 | Document Control | Transmittal | Track transmittal response | Medium | 2026-04-25 | 2026-05-01 | 2026-04-23 | 2026-05-13 | Completed | 100 | DOC-B | 1 | Approved | 2026-05-30 | 513 | Valid | Valid | Valid | 46155 | 20 | 12 |  | No | Late | Clean | 1 | Unique
ACT-0514 | Construction | Punch List | Resolve outstanding punch item | Low | 2026-03-13 | 2026-03-30 | 2026-03-13 |  | In Progress | 10 | CONST-A | 0 | N/A | 2026-03-14 | 514 | Valid | Incomplete | Valid |  |  |  | 162 | Yes | Overdue | Clean | 1 | Unique
ACT-0515 | Procurement | Delivery Tracking | Update delivery schedule | High | 2026-07-19 | 2026-07-31 | 2026-07-27 | 2026-08-20 | Completed | 100 | PROC-A | 0 | N/A | 2026-08-21 | 515 | Valid | Valid | Valid | 46254 | 24 | 20 |  | No | Late | Clean | 1 | Unique
ACT-0516 | Planning | Schedule Update | Update milestone tracker | Low | 2026-03-24 | 2026-03-29 | 2026-03-24 | 2026-03-28 | Completed | 100 | PLAN-B | 3 | N/A | 2026-04-15 | 516 | Valid | Valid | Valid | 46109 | 4 | -1 |  | No | On Time | Clean | 1 | Unique
ACT-0517 | QA/QC | Test Package Review | Validate test records | Low | 2026-03-27 | 2026-04-10 | 2026-04-02 | 2026-04-24 | Completed | 100 | QC-C | 2 | Approved | 2026-05-09 | 517 | Valid | Valid | Valid | 46136 | 22 | 14 |  | No | Late | Clean | 1 | Unique
ACT-0518 | Procurement | Delivery Tracking | Track material delivery | High | 2026-04-08 | 2026-04-23 | 2026-04-14 |  | In Progress | 20 | PROC-A | 3 | N/A | 2026-05-01 | 518 | Valid | Incomplete | Valid |  |  |  | 130 | Yes | Overdue | Clean | 1 | Unique
ACT-0519 | QA/QC | Inspection | Verify completed installation | Critical | 2026-04-17 | 2026-04-26 | 2026-04-25 | 2026-04-29 | Completed | 100 | QA-A | 1 | N/A | 2026-05-07 | 519 | Valid | Valid | Valid | 46141 | 4 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0520 | Construction | Rework | Complete required rework | Medium | 2026-07-27 | 2026-07-31 | 2026-07-28 | 2026-08-18 | Completed | 100 | CONST-B | 0 | N/A | 2026-08-19 | 520 | Valid | Valid | Valid | 46252 | 21 | 18 |  | No | Late | Clean | 1 | Unique
ACT-0521 | Construction | Rework | Rectify field discrepancy | High | 2026-02-20 | 2026-02-22 | 2026-02-20 | 2026-03-03 | Completed | 100 | CONST-B | 2 | N/A | 2026-03-17 | 521 | Valid | Valid | Valid | 46084 | 11 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0522 | Document Control | Approval Tracking | Update approval register | High | 2026-01-20 | 2026-02-07 | 2026-01-19 |  | In Progress | 60 | DOC-A | 1 | Approved | 2026-01-21 | 522 | Valid | Incomplete | Valid |  |  |  | 215 | Yes | Overdue | Clean | 1 | Unique
ACT-0523 | Procurement | Delivery Tracking | Confirm delivery status | High | 2026-03-11 | 2026-03-20 | 2026-03-15 | 2026-04-03 | Completed | 100 | PROC-B | 3 | N/A | 2026-04-17 | 523 | Valid | Valid | Valid | 46115 | 19 | 14 |  | No | Late | Clean | 1 | Unique
ACT-0524 | Construction | Rework | Complete required rework | High | 2026-01-14 | 2026-01-22 | 2026-01-20 | 2026-01-31 | Completed | 100 | CONST-C | 2 | N/A | 2026-02-05 | 524 | Valid | Valid | Valid | 46053 | 11 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0525 | Procurement | Purchase Review | Review purchase requirement | Low | 2026-01-26 | 2026-02-07 | 2026-02-06 |  | In Progress | 60 | PROC-B | 3 | Pending | 2026-02-08 | 525 | Valid | Incomplete | Valid |  |  |  | 197 | Yes | Overdue | Clean | 1 | Unique
ACT-0526 | Document Control | Revision Control | Update document revision | Low | 2026-07-12 | 2026-07-30 | 2026-07-10 |  | In Progress | 40 | DOC-A | 1 | N/A | 2026-07-12 | 526 | Valid | Incomplete | Valid |  |  |  | 43 | Yes | Overdue | Clean | 1 | Unique
ACT-0527 | Construction | Site Preparation | Complete site readiness activity | High | 2026-07-12 | 2026-07-26 | 2026-07-14 |  | In Progress | 30 | CONST-A | 0 | N/A | 2026-07-19 | 527 | Valid | Incomplete | Valid |  |  |  | 39 | Yes | Overdue | Clean | 1 | Unique
ACT-0528 | Document Control | Approval Tracking | Follow up document approval | Medium | 2026-06-04 | 2026-06-07 | 2026-06-02 | 2026-06-24 | Completed | 100 | DOC-A | 1 | Approved | 2026-07-02 | 528 | Valid | Valid | Valid | 46197 | 22 | 17 |  | No | Late | Clean | 1 | Unique
ACT-0529 | QA/QC | NCR Follow-up | Verify NCR closure | Low | 2026-06-09 | 2026-06-12 | 2026-06-07 |  | In Progress | 30 | QA-B | 0 | N/A | 2026-06-19 | 529 | Valid | Incomplete | Valid |  |  |  | 76 | Yes | Overdue | Clean | 1 | Unique
ACT-0530 | Construction | Site Preparation | Coordinate access preparation | Medium | 2026-03-06 | 2026-03-22 | 2026-03-04 |  | In Progress | 40 | CONST-B | 0 | N/A | 2026-03-11 | 530 | Valid | Incomplete | Valid |  |  |  | 171 | Yes | Overdue | Clean | 1 | Unique
ACT-0531 | QA/QC | Testing | Perform pressure test | High | 2026-07-20 | 2026-08-04 | 2026-07-22 |  | In Progress | 95 | QC-C | 1 | N/A | 2026-08-01 | 531 | Valid | Incomplete | Valid |  |  |  | 31 | Yes | Overdue | Clean | 1 | Unique
ACT-0532 | Construction | Installation | Complete field installation | High | 2026-05-14 | 2026-05-18 | 2026-05-18 |  | In Progress | 95 | CONST-A | 0 | N/A | 2026-05-18 | 532 | Valid | Incomplete | Valid |  |  |  | 96 | Yes | Overdue | Clean | 1 | Unique
ACT-0533 | Planning | Progress Review | Analyze progress status | Medium | 2026-06-18 | 2026-06-24 |  |  | Not Started | 0 | PLAN-B | 0 | N/A | 2026-06-27 | 533 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0534 | Construction | Installation | Complete field installation | Medium | 2026-07-06 | 2026-07-12 | 2026-07-06 | 2026-07-09 | Completed | 100 | CONST-B | 1 | N/A | 2026-07-13 | 534 | Valid | Valid | Valid | 46212 | 3 | -3 |  | No | On Time | Clean | 1 | Unique
ACT-0535 | Engineering | Technical Query | Clarify design requirement | Medium | 2026-04-21 | 2026-05-04 | 2026-04-29 |  | In Progress | 10 | ENG-A | 4 | N/A | 2026-05-06 | 535 | Valid | Incomplete | Valid |  |  |  | 115 | Yes | Overdue | Clean | 1 | Unique
ACT-0536 | Document Control | Revision Control | Check revision history | High | 2026-02-17 | 2026-02-20 | 2026-02-15 | 2026-02-23 | Completed | 100 | DOC-A | 1 | N/A | 2026-03-13 | 536 | Valid | Valid | Valid | 46076 | 8 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0537 | Engineering | Material Review | Validate material specification | High | 2026-05-11 | 2026-05-16 | 2026-05-14 | 2026-06-03 | Completed | 100 | ENG-A | 0 | Approved | 2026-06-15 | 537 | Valid | Valid | Valid | 46176 | 20 | 18 |  | No | Late | Clean | 1 | Unique
ACT-0538 | Construction | Punch List | Resolve outstanding punch item | Medium | 2026-03-18 | 2026-03-26 | 2026-03-18 | 2026-04-09 | Completed | 100 | CONST-A | 0 | N/A | 2026-04-23 | 538 | Valid | Valid | Valid | 46121 | 22 | 14 |  | No | Late | Clean | 1 | Unique
ACT-0539 | QA/QC | Test Package Review | Review test package | Low | 2026-02-08 | 2026-02-20 | 2026-02-12 | 2026-02-28 | Completed | 100 | QA-A | 1 | Approved | 2026-03-02 | 539 | Valid | Valid | Valid | 46081 | 16 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0540 | Construction | Installation | Install project component | Critical | 2026-05-05 | 2026-05-18 | 2026-05-12 |  | In Progress | 80 | CONST-A | 2 | N/A | 2026-05-13 | 540 | Valid | Incomplete | Valid |  |  |  | 102 | Yes | Overdue | Clean | 1 | Unique
ACT-0541 | QA/QC | Test Package Review | Check package completeness | Critical | 2026-06-25 | 2026-07-08 | 2026-06-28 | 2026-07-13 | Completed | 100 | QA-B | 0 | Approved | 2026-07-23 | 541 | Valid | Valid | Valid | 46216 | 15 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0542 | Engineering | Technical Query | Respond to engineering query | Medium | 2026-02-10 | 2026-02-20 | 2026-02-13 |  | In Progress | 95 | ENG-B | 1 | N/A | 2026-02-26 | 542 | Valid | Incomplete | Valid |  |  |  | 190 | Yes | Overdue | Clean | 1 | Unique
ACT-0543 | Document Control | Transmittal | Track transmittal response | High | 2026-03-13 | 2026-03-31 | 2026-03-14 |  | In Progress | 70 | DOC-A | 2 | Pending | 2026-03-28 | 543 | Valid | Incomplete | Valid |  |  |  | 161 | Yes | Overdue | Clean | 1 | Unique
ACT-0544 | Engineering | Design Review | Review engineering drawing | Medium | 2026-05-05 | 2026-05-15 | 2026-05-05 |  | In Progress | 70 | ENG-B | 1 | Pending | 2026-05-20 | 544 | Valid | Incomplete | Valid |  |  |  | 109 | Yes | Overdue | Clean | 1 | Unique
ACT-0545 | Construction | Punch List | Close punch item | Medium | 2026-02-26 | 2026-03-09 | 2026-03-01 | 2026-03-12 | Completed | 100 | CONST-A | 3 | N/A | 2026-03-30 | 545 | Valid | Valid | Valid | 46093 | 11 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0546 | Construction | Installation | Execute planned installation | High | 2026-02-20 | 2026-03-07 | 2026-02-23 | 2026-03-13 | Completed | 100 | CONST-C | 0 | N/A | 2026-03-22 | 546 | Valid | Valid | Valid | 46094 | 18 | 6 |  | No | Late | Clean | 1 | Unique
ACT-0547 | Document Control | Document Submission | Prepare document for submission | Medium | 2026-02-01 | 2026-02-13 | 2026-02-02 | 2026-02-22 | Completed | 100 | DOC-B | 1 | Pending | 2026-02-22 | 547 | Valid | Valid | Valid | 46075 | 20 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0548 | Document Control | Approval Tracking | Follow up document approval | Critical | 2026-07-11 | 2026-07-31 | 2026-07-09 |  | In Progress | 40 | DOC-B | 0 | Pending | 2026-07-11 | 548 | Valid | Incomplete | Valid |  |  |  | 44 | Yes | Overdue | Clean | 1 | Unique
ACT-0549 | Engineering | Technical Query | No Description | Medium | 2026-07-21 | 2026-08-04 | 2026-07-24 |  | In Progress | 90 | ENG-B | 0 | N/A | 2026-08-02 | 549 | Valid | Incomplete | Valid |  |  |  | 29 | Yes | Overdue | Missing Description | 1 | Unique
ACT-0550 | Procurement | Delivery Tracking | Update delivery schedule | High | 2026-04-06 | 2026-04-11 | 2026-04-08 | 2026-04-07 | Completed | 100 | PROC-B | 1 | N/A | 2026-04-25 | 550 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0551 | Engineering | Material Review | Validate material specification | High | 2026-04-26 | 2026-05-11 | 2026-04-28 | 2026-05-27 | Completed | 100 | ENG-C | 2 | Approved | 2026-06-11 | 551 | Valid | Valid | Valid | 46169 | 29 | 16 |  | No | Late | Clean | 1 | Unique
ACT-0552 | Construction | Installation | Install project component | Medium | 2026-01-25 | 2026-02-11 | 2026-01-27 |  | In Progress | 40 | CONST-B | 3 | N/A | 2026-02-12 | 552 | Valid | Incomplete | Valid |  |  |  | 207 | Yes | Overdue | Clean | 1 | Unique
ACT-0553 | QA/QC | Inspection | Conduct quality inspection | Low | 2026-01-16 | 2026-02-03 | 2026-01-16 |  | In Progress | 40 | QA-A | 1 | N/A | 2026-02-03 | 553 | Valid | Incomplete | Valid |  |  |  | 218 | Yes | Overdue | Clean | 1 | Unique
ACT-0554 | Procurement | Material Request | Prepare material request | High | 2026-05-03 | 2026-05-10 | 2026-05-07 |  | On Hold | 40 | PROC-B | 3 | Pending | 2026-05-25 | 554 | Valid | Incomplete | Valid |  |  |  | 107 | Yes | Overdue | Clean | 1 | Unique
ACT-0555 | Procurement | Purchase Review | Check purchase documentation | High | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-05-01 | Completed | 100 | PROC-A | 2 | Approved | 2026-05-01 | 555 | Valid | Valid | Valid | 46143 | 15 | 22 |  | No | Late | Clean | 1 | Unique
ACT-0556 | QA/QC | Inspection | Perform site inspection | High | 2026-05-02 | 2026-05-16 | 2026-05-09 | 2026-05-20 | Completed | 100 | QC-C | 1 | N/A | 2026-05-31 | 556 | Valid | Valid | Valid | 46162 | 11 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0557 | Planning | Variance Review | Investigate progress variance | Low | 2026-02-08 | 2026-02-10 | 2026-02-11 | 2026-02-02 | Completed | 100 | PLAN-A | 0 | N/A | 2026-02-17 | 557 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0558 | Planning | Variance Review | Review delayed activity | High | 2026-05-22 | 2026-05-30 | 2026-05-23 | 2026-05-29 | Completed | 100 | PLAN-B | 0 | N/A | 2026-06-02 | 558 | Valid | Valid | Valid | 46171 | 6 | -1 |  | No | On Time | Clean | 1 | Unique
ACT-0559 | Document Control | Approval Tracking | Track pending approval | High | 2026-06-03 | 2026-06-12 | 2026-06-01 | 2026-06-10 | Completed | 100 | DOC-B | 0 | Approved | 2026-06-23 | 559 | Valid | Valid | Valid | 46183 | 9 | -2 |  | No | On Time | Clean | 1 | Unique
ACT-0560 | Procurement | Delivery Tracking | Track material delivery | Medium | 2026-05-09 | 2026-05-27 | 2026-05-09 |  | In Progress | 95 | PROC-B | 0 | N/A | 2026-05-09 | 560 | Valid | Incomplete | Valid |  |  |  | 105 | Yes | Overdue | Clean | 1 | Unique
ACT-0561 | Construction | Installation | Install project component | High | 2026-04-21 | 2026-05-08 | 2026-04-21 |  | In Progress | 70 | CONST-A | 2 | N/A | 2026-04-21 | 561 | Valid | Incomplete | Valid |  |  |  | 123 | Yes | Overdue | Clean | 1 | Unique
ACT-0562 | QA/QC | Testing | Perform pressure test | Medium | 2026-03-05 | 2026-03-23 | 2026-03-10 |  | In Progress | 90 | QC-C | 1 | N/A | 2026-03-19 | 562 | Valid | Incomplete | Valid |  |  |  | 165 | Yes | Overdue | Clean | 1 | Unique
ACT-0563 | Planning | Variance Review | Review delayed activity | High | 2026-04-07 | 2026-04-24 | 2026-04-07 |  | In Progress | 40 | PLAN-B | 2 | N/A | 2026-04-09 | 563 | Valid | Incomplete | Valid |  |  |  | 137 | Yes | Overdue | Clean | 1 | Unique
ACT-0564 | Engineering | Drawing Revision | Revise issued drawing | High | 2026-01-30 | 2026-02-14 | 2026-01-29 | 2026-02-19 | Completed | 100 | ENG-B | 5 | Approved | 2026-02-27 | 564 | Valid | Valid | Valid | 46072 | 21 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0565 | Planning | Progress Review | Analyze progress status | Low | 2026-01-21 | 2026-02-02 | 2026-01-21 | 2026-02-02 | Completed | 100 | PLAN-B | 0 | N/A | 2026-02-12 | 565 | Valid | Valid | Valid | 46055 | 12 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0566 | Procurement | Delivery Tracking | Track material delivery | High | 2026-05-16 | 2026-05-21 | 2026-05-23 | 2026-05-29 | Completed | 100 | PROC-A | 3 | N/A | 2026-06-01 | 566 | Valid | Valid | Valid | 46171 | 6 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0567 | Procurement | Material Request | Coordinate material requirement | Low | 2026-01-31 | 2026-02-07 | 2026-02-10 | 2026-02-07 | Completed | 100 | PROC-B | 0 | Approved | 2026-02-23 | 567 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0568 | Planning | Schedule Update | Update activity schedule | High | 2026-03-31 | 2026-04-06 | 2026-04-04 |  | On Hold | 70 | PLAN-B | 2 | N/A | 2026-04-14 | 568 | Valid | Incomplete | Valid |  |  |  | 140 | Yes | Overdue | Clean | 1 | Unique
ACT-0569 | Construction | Installation | Install project component | Medium | 2026-07-17 | 2026-08-01 | 2026-07-30 |  | In Progress | 75 | CONST-A | 1 | N/A | 2026-08-06 | 569 | Valid | Incomplete | Valid |  |  |  | 23 | Yes | Overdue | Clean | 1 | Unique
ACT-0570 | Procurement | Purchase Review | Validate procurement status | High | 2026-05-17 | 2026-05-30 | 2026-05-15 |  | In Progress | 20 | PROC-B | 0 | Pending | 2026-05-20 | 570 | Valid | Incomplete | Valid |  |  |  | 99 | Yes | Overdue | Clean | 1 | Unique
ACT-0571 | Engineering | Design Review | Review technical specification | Critical | 2026-02-12 | 2026-03-04 |  |  | Not Started | 0 | ENG-B | 2 | Pending | 2026-02-28 | 571 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0572 | Construction | Site Preparation | Coordinate access preparation | High | 2026-04-03 | 2026-04-05 | 2026-04-08 |  | In Progress | 25 | CONST-C | 2 | N/A | 2026-04-22 | 572 | Valid | Incomplete | Valid |  |  |  | 136 | Yes | Overdue | Clean | 1 | Unique
ACT-0573 | QA/QC | Test Package Review | Validate test records | Medium | 2026-07-24 | 2026-08-07 | 2026-07-27 |  | In Progress | 95 | QA-B | 2 | Pending | 2026-08-13 | 573 | Valid | Incomplete | Valid |  |  |  | 26 | Yes | Overdue | Clean | 1 | Unique
ACT-0574 | QA/QC | NCR Follow-up | Review corrective evidence | Medium | 2026-06-16 | 2026-06-23 |  |  | Not Started | 0 | QC-C | 3 | N/A | 2026-07-03 | 574 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0575 | QA/QC | NCR Follow-up | Review corrective evidence | Medium | 2026-05-14 | 2026-05-19 | 2026-05-15 |  | In Progress | 75 | QC-C | 1 | N/A | 2026-05-16 | 575 | Valid | Incomplete | Valid |  |  |  | 99 | Yes | Overdue | Clean | 1 | Unique
ACT-0576 | Document Control | Approval Tracking | Follow up document approval | Medium | 2026-01-06 | 2026-01-22 | 2026-01-07 | 2026-02-08 | Completed | 100 | DOC-A | 2 | Pending | 2026-02-25 | 576 | Valid | Valid | Valid | 46061 | 32 | 17 |  | No | Late | Clean | 1 | Unique
ACT-0577 | QA/QC | NCR Follow-up | Review corrective evidence | High | 2026-07-07 | 2026-07-27 | 2026-07-08 | 2026-07-25 | Completed | 100 | QA-A | 0 | N/A | 2026-08-12 | 577 | Valid | Valid | Valid | 46228 | 17 | -2 |  | No | On Time | Clean | 1 | Unique
ACT-0578 | Procurement | Delivery Tracking | Confirm delivery status | Low | 2026-07-06 | 2026-07-21 | 2026-07-11 |  | In Progress | 70 | PROC-B | 0 | N/A | 2026-07-27 | 578 | Valid | Incomplete | Valid |  |  |  | 42 | Yes | Overdue | Clean | 1 | Unique
ACT-0579 | Construction | Rework | Complete required rework | High | 2026-06-16 | 2026-07-01 | 2026-06-20 |  | In Progress | 95 | CONST-A | 5 | N/A | 2026-06-25 | 579 | Valid | Incomplete | Valid |  |  |  | 63 | Yes | Overdue | Clean | 1 | Unique
ACT-0580 | Construction | Rework | Rectify field discrepancy | Medium | 2026-07-04 | 2026-07-22 | 2026-07-09 | 2026-08-04 | Completed | 100 | CONST-B | 2 | N/A | 2026-08-21 | 580 | Valid | Valid | Valid | 46238 | 26 | 13 |  | No | Late | Clean | 1 | Unique
ACT-0581 | Document Control | Document Submission | Issue controlled document | High | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-20 | Completed | 100 | DOC-B | 0 | Approved | 2026-03-01 | 581 | Valid | Valid | Valid | 46073 | 18 | 13 |  | No | Late | Clean | 1 | Unique
ACT-0582 | Engineering | Drawing Revision | Revise issued drawing | High | 2026-04-22 | 2026-04-25 | 2026-04-22 | 2026-05-06 | Completed | 100 | ENG-B | 2 | Approved | 2026-05-23 | 582 | Valid | Valid | Valid | 46148 | 14 | 11 |  | No | Late | Clean | 1 | Unique
ACT-0583 | Engineering | Design Review | Check design compliance | Medium | 2026-03-25 | 2026-04-14 | 2026-03-25 |  | In Progress | 25 | ENG-B | 2 | Pending | 2026-04-08 | 583 | Valid | Incomplete | Valid |  |  |  | 150 | Yes | Overdue | Clean | 1 | Unique
ACT-0584 | Planning | Progress Review | Analyze progress status | Medium | 2026-07-28 | 2026-08-12 | 2026-08-01 |  | In Progress | 10 | PLAN-B | 4 | N/A | 2026-08-15 | 584 | Valid | Incomplete | Valid |  |  |  | 21 | Yes | Overdue | Clean | 1 | Unique
ACT-0585 | Planning | Progress Review | Analyze progress status | Low | 2026-06-15 | 2026-06-26 | 2026-06-19 | 2026-07-06 | Completed | 90 | PLAN-A | 1 | N/A | 2026-07-24 | 585 | Valid | Valid | Valid | 46209 | 17 | 10 |  | No | Late | Clean | 1 | Unique
ACT-0586 | Document Control | Revision Control | Check revision history | Medium | 2026-01-09 | 2026-01-14 | 2026-01-07 | 2026-01-14 | Completed | 100 | DOC-B | 0 | N/A | 2026-02-01 | 586 | Valid | Valid | Valid | 46036 | 7 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0587 | Engineering | Technical Query | Clarify design requirement | High | 2026-05-10 | 2026-05-12 | 2026-05-12 | 2026-05-18 | Completed | 100 | ENG-A | 1 | N/A | 2026-05-20 | 587 | Valid | Valid | Valid | 46160 | 6 | 6 |  | No | Late | Clean | 1 | Unique
ACT-0588 | Document Control | Revision Control | Check revision history | Medium | 2026-03-11 | 2026-03-15 | 2026-03-18 | 2026-03-15 | Completed | 100 | DOC-A | 4 | N/A | 2026-03-20 | 588 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0589 | Planning | Lookahead Planning | Review upcoming activities | Low | 2026-02-10 | 2026-02-25 | 2026-02-10 |  | On Hold | 20 | PLAN-A | 2 | N/A | 2026-02-28 | 589 | Valid | Incomplete | Valid |  |  |  | 193 | Yes | Overdue | Clean | 1 | Unique
ACT-0590 | Construction | Rework | Correct installation issue | Medium | 2026-03-27 | 2026-04-12 | 2026-04-08 | 2026-05-03 | Completed | 100 | CONST-B | 4 | N/A | 2026-05-03 | 590 | Valid | Valid | Valid | 46145 | 25 | 21 |  | No | Late | Clean | 1 | Unique
ACT-0591 | Construction | Installation | Complete field installation | High | 2026-06-20 | 2026-06-26 | 2026-06-24 | 2026-07-15 | Completed | 100 | CONST-B | 0 | N/A | 2026-07-19 | 591 | Valid | Valid | Valid | 46218 | 21 | 19 |  | No | Late | Clean | 1 | Unique
ACT-0592 | Construction | Punch List | Close punch item | Medium | 2026-04-23 | 2026-05-12 | 2026-04-29 | 2026-05-08 | Completed | 100 | CONST-A | 0 | N/A | 2026-05-13 | 592 | Valid | Valid | Valid | 46150 | 9 | -4 |  | No | On Time | Clean | 1 | Unique
ACT-0593 | Engineering | Material Review | Validate material specification | High | 2026-06-28 | 2026-07-12 | 2026-07-01 |  | In Progress | 75 | ENG-C | 0 | Pending | 2026-07-18 | 593 | Valid | Incomplete | Valid |  |  |  | 52 | Yes | Overdue | Clean | 1 | Unique
ACT-0594 | Engineering | Design Review | Check design compliance | High | 2026-02-09 | 2026-02-28 | 2026-02-12 | 2026-03-01 | Completed | 100 | ENG-C | 2 | Pending | 2026-03-11 | 594 | Valid | Valid | Valid | 46082 | 17 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0595 | QA/QC | Test Package Review | Check package completeness | Medium | 2026-03-28 | 2026-04-09 | 2026-04-02 |  | In Progress | 10 | QC-C | 1 | Pending | 2026-04-02 | 595 | Valid | Incomplete | Valid |  |  |  | 142 | Yes | Overdue | Clean | 1 | Unique
ACT-0596 | Engineering | Material Review | Validate material specification | Medium | 2026-07-25 | 2026-07-29 | 2026-07-25 |  | In Progress | 70 | ENG-C | 2 | Pending | 2026-08-06 | 596 | Valid | Incomplete | Valid |  |  |  | 28 | Yes | Overdue | Clean | 1 | Unique
ACT-0597 | QA/QC | Testing | Complete system testing | Critical | 2026-02-05 | 2026-02-21 | 2026-02-07 |  | In Progress | 90 | QA-A | 4 | N/A | 2026-02-18 | 597 | Valid | Incomplete | Valid |  |  |  | 196 | Yes | Overdue | Clean | 1 | Unique
ACT-0598 | Engineering | Technical Query | Respond to engineering query | Medium | 2026-05-11 | 2026-05-24 |  |  | Not Started | 0 | ENG-A | 1 | N/A | 2026-05-17 | 598 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0599 | Engineering | Material Review | Review material submittal | High | 2026-05-30 | 2026-06-17 | 2026-06-01 | 2026-06-17 | Completed | 100 | ENG-C | 2 | Approved | 2026-06-19 | 599 | Valid | Valid | Valid | 46190 | 16 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0600 | Engineering | Design Review | Review engineering drawing | Medium | 2026-05-30 | 2026-06-08 | 2026-05-28 |  | In Progress | 90 | ENG-C | 0 | Rejected | 2026-06-14 | 600 | Valid | Incomplete | Valid |  |  |  | 86 | Yes | Overdue | Clean | 1 | Unique
ACT-0601 | QA/QC | Test Package Review | Review test package | Critical | 2026-06-18 | 2026-06-21 | 2026-06-17 | 2026-07-11 | Completed | 100 | QA-B | 0 | Approved | 2026-07-26 | 601 | Valid | Valid | Valid | 46214 | 24 | 20 |  | No | Late | Clean | 1 | Unique
ACT-0602 | Construction | Installation | Execute planned installation | Medium | 2026-03-17 | 2026-04-01 | 2026-03-18 | 2026-04-18 | Completed | 100 | CONST-C | 3 | N/A | 2026-04-18 | 602 | Valid | Valid | Valid | 46130 | 31 | 17 |  | No | Late | Clean | 2 | Duplicate
ACT-0602 | QA/QC | Test Package Review | Review test package | Critical | 2026-02-24 | 2026-03-03 | 2026-03-03 | 2026-03-14 | Completed | 100 | QA-B | 1 | Approved | 2026-03-24 | 603 | Valid | Valid | Valid | 46095 | 11 | 11 |  | No | Late | Clean | 2 | Duplicate
ACT-0604 | QA/QC | Test Package Review | Review test package | Critical | 2026-01-18 | 2026-01-30 | 2026-01-20 | 2026-02-09 | Completed | 100 | QC-C | 1 | Approved | 2026-02-23 | 604 | Valid | Valid | Valid | 46062 | 20 | 10 |  | No | Late | Clean | 1 | Unique
ACT-0605 | Engineering | Design Review | Review engineering drawing | Medium | 2026-07-01 | 2026-07-05 | 2026-07-09 | 2026-07-15 | Completed | 100 | ENG-C | 1 | Approved | 2026-07-18 | 605 | Valid | Valid | Valid | 46218 | 6 | 10 |  | No | Late | Clean | 1 | Unique
ACT-0606 | Engineering | Design Review | Check design compliance | High | 2026-04-17 | 2026-04-22 | 2026-04-15 |  | In Progress | 70 | ENG-B | 1 | Approved | 2026-04-18 | 606 | Valid | Incomplete | Valid |  |  |  | 129 | Yes | Overdue | Clean | 1 | Unique
ACT-0607 | Planning | Schedule Update | Refresh progress schedule | Medium | 2026-06-04 | 2026-06-12 | 2026-06-09 | 2026-06-12 | Completed | 100 | PLAN-A | 3 | N/A | 2026-06-30 | 607 | Valid | Valid | Valid | 46185 | 3 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0608 | Construction | Site Preparation | Complete site readiness activity | Medium | 2026-07-09 | 2026-07-25 | 2026-07-08 | 2026-08-08 | Completed | 100 | CONST-B | 1 | N/A | 2026-08-20 | 608 | Valid | Valid | Valid | 46242 | 31 | 14 |  | No | Late | Clean | 1 | Unique
ACT-0609 | Construction | Punch List | Close punch item | Medium | 2026-06-08 | 2026-06-20 | 2026-06-11 |  | In Progress | 90 | CONST-A | 2 | N/A | 2026-06-12 | 609 | Valid | Incomplete | Valid |  |  |  | 72 | Yes | Overdue | Clean | 1 | Unique
ACT-0610 | Construction | Installation | Install project component | Medium | 2026-02-25 | 2026-03-05 | 2026-02-25 |  | In Progress | 80 | CONST-C | 2 | N/A | 2026-03-15 | 610 | Valid | Incomplete | Valid |  |  |  | 178 | Yes | Overdue | Clean | 1 | Unique
ACT-0611 | Document Control | Transmittal | Issue transmittal record | Medium | 2026-01-31 | 2026-02-16 | 2026-02-06 |  | In Progress | 10 | DOC-A | 2 | Pending | 2026-02-20 | 611 | Valid | Incomplete | Valid |  |  |  | 197 | Yes | Overdue | Clean | 1 | Unique
ACT-0612 | QA/QC | NCR Follow-up | Review corrective evidence | Medium | 2026-04-17 | 2026-04-24 | 2026-04-19 | 2026-05-01 | Completed | 100 | QA-B | 1 | N/A | 2026-05-05 | 612 | Valid | Valid | Valid | 46143 | 12 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0613 | Construction | Site Preparation | Prepare work area | Critical | 2026-02-24 | 2026-03-04 | 2026-02-27 | 2026-03-20 | Completed | 100 | CONST-A | 3 | N/A | 2026-03-27 | 613 | Valid | Valid | Valid | 46101 | 21 | 16 |  | No | Late | Clean | 1 | Unique
ACT-0614 | Engineering | Drawing Revision | Update drawing comments | Critical | 2026-01-10 | 2026-01-16 | 2026-01-12 |  | In Progress | 30 | ENG-C | 1 | Pending | 2026-01-17 | 614 | Valid | Incomplete | Valid |  |  |  | 222 | Yes | Overdue | Clean | 1 | Unique
ACT-0615 | Document Control | Approval Tracking | Update approval register | Low | 2026-02-10 | 2026-02-16 | 2026-02-10 | 2026-02-15 | Completed | 100 | DOC-A | 1 | Rejected | 2026-02-22 | 615 | Valid | Valid | Valid | 46068 | 5 | -1 |  | No | On Time | Clean | 1 | Unique
ACT-0616 | Procurement | Vendor Follow-up | Coordinate supplier action | Medium | 2026-02-12 | 2026-02-24 | 2026-02-18 |  | In Progress | 25 | PROC-B | 3 | N/A | 2026-03-08 | 616 | Valid | Incomplete | Valid |  |  |  | 185 | Yes | Overdue | Clean | 1 | Unique
ACT-0617 | QA/QC | Inspection | Verify completed installation | High | 2026-06-11 | 2026-06-15 | 2026-06-09 |  | In Progress | 75 | QC-C | 1 | N/A | 2026-06-19 | 617 | Valid | Incomplete | Valid |  |  |  | 74 | Yes | Overdue | Clean | 1 | Unique
ACT-0618 | QA/QC | Test Package Review | Validate test records | Critical | 2026-05-06 | 2026-05-16 | 2026-05-13 |  | In Progress | 90 | QA-B | 0 | Pending | 2026-05-19 | 618 | Valid | Incomplete | Valid |  |  |  | 101 | Yes | Overdue | Clean | 1 | Unique
ACT-0619 | Document Control | Approval Tracking | Track pending approval | Medium | 2026-04-11 | 2026-05-01 | 2026-04-14 | 2026-04-30 | Completed | 100 | DOC-B | 2 | Approved | 2026-05-16 | 619 | Valid | Valid | Valid | 46142 | 16 | -1 |  | No | On Time | Clean | 1 | Unique
ACT-0620 | QA/QC | Inspection | Verify completed installation | Medium | 2026-04-01 | 2026-04-16 | 2026-03-31 | 2026-04-26 | Completed | 100 | QA-A | 0 | N/A | 2026-04-26 | 620 | Valid | Valid | Valid | 46138 | 26 | 10 |  | No | Late | Clean | 1 | Unique
ACT-0621 | Construction | Site Preparation | Coordinate access preparation | Low | 2026-01-26 | 2026-02-06 | 2026-01-24 |  | In Progress | 20 | CONST-A | 0 | N/A | 2026-02-04 | 621 | Valid | Incomplete | Valid |  |  |  | 210 | Yes | Overdue | Clean | 1 | Unique
ACT-0622 | Construction | Site Preparation | Prepare work area | High | 2026-03-10 | 2026-03-21 | 2026-03-12 |  | In Progress | 30 | CONST-C | 2 | N/A | 2026-03-16 | 622 | Valid | Incomplete | Valid |  |  |  | 163 | Yes | Overdue | Clean | 1 | Unique
ACT-0623 | Planning | Lookahead Planning | Prepare lookahead plan | High | 2026-03-18 | 2026-03-31 | 2026-03-16 | 2026-04-07 | Completed | 100 | PLAN-A | 2 | N/A | 2026-04-22 | 623 | Valid | Valid | Valid | 46119 | 22 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0624 | Document Control | Revision Control | Update document revision | High | 2026-02-27 | 2026-03-16 | 2026-02-25 | 2026-03-15 | Completed | 100 | DOC-A | 3 | N/A | 2026-03-25 | 624 | Valid | Valid | Valid | 46096 | 18 | -1 |  | No | On Time | Clean | 1 | Unique
ACT-0625 | QA/QC | Testing | Perform pressure test | High | 2026-07-02 | 2026-07-17 | 2026-06-30 | 2026-07-27 | Completed | 100 | QA-B | 1 | N/A | 2026-07-31 | 625 | Valid | Valid | Valid | 46230 | 27 | 10 |  | No | Late | Clean | 1 | Unique
ACT-0626 | Document Control | Document Submission | Prepare document for submission | High | 2026-04-05 | 2026-04-17 | 2026-04-03 |  | In Progress | 40 | DOC-A | 0 | Pending | 2026-04-04 | 626 | Valid | Incomplete | Valid |  |  |  | 141 | Yes | Overdue | Clean | 1 | Unique
ACT-0627 | Engineering | Technical Query | Respond to engineering query | High | 2026-06-08 | 2026-06-28 | 2026-06-12 |  | In Progress | 60 | ENG-A | 0 | N/A | 2026-06-24 | 627 | Valid | Incomplete | Valid |  |  |  | 71 | Yes | Overdue | Clean | 1 | Unique
ACT-0628 | Construction | Site Preparation | Coordinate access preparation | Critical | 2026-06-17 | 2026-06-28 | 2026-06-24 | 2026-07-14 | Completed | 100 | CONST-A | 2 | N/A | 2026-07-29 | 628 | Valid | Valid | Valid | 46217 | 20 | 16 |  | No | Late | Clean | 1 | Unique
ACT-0629 | Engineering | Design Review | Check design compliance | Medium | 2026-03-05 | 2026-03-16 | 2026-03-07 | 2026-03-22 | Completed | 100 | ENG-B | 0 | Approved | 2026-04-04 | 629 | Valid | Valid | Valid | 46103 | 15 | 6 |  | No | Late | Clean | 1 | Unique
ACT-0630 | Engineering | Design Review | Review engineering drawing | Medium | 2026-05-07 | 2026-05-11 | 2026-05-10 |  | In Progress | 95 | ENG-B | 2 | Pending | 2026-05-28 | 630 | Valid | Incomplete | Valid |  |  |  | 104 | Yes | Overdue | Clean | 1 | Unique
ACT-0631 | Construction | Rework | Complete required rework | Medium | 2026-02-10 | 2026-02-26 |  |  | Not Started | 0 | CONST-C | 1 | N/A | 2026-02-17 | 631 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0632 | QA/QC | Test Package Review | Check package completeness | Medium | 2026-01-15 | 2026-01-19 | 2026-01-15 |  | In Progress | 95 | QC-C | 3 | Approved | 2026-01-27 | 632 | Valid | Incomplete | Valid |  |  |  | 219 | Yes | Overdue | Clean | 1 | Unique
ACT-0633 | Procurement | Vendor Follow-up | Check vendor document status | Medium | 2026-06-12 | 2026-06-27 | 2026-06-18 | 2026-07-06 | Completed | 100 | PROC-A | 1 | N/A | 2026-07-07 | 633 | Valid | Valid | Valid | 46209 | 18 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0634 | Document Control | Revision Control | Check revision history | High | 2026-05-22 | 2026-06-02 | 2026-05-29 |  | In Progress | 60 | DOC-A | 5 | N/A | 2026-06-15 | 634 | Valid | Incomplete | Valid |  |  |  | 85 | Yes | Overdue | Clean | 1 | Unique
ACT-0635 | Document Control | Document Submission | Submit project document | Medium | 2026-07-23 | 2026-08-04 | 2026-07-26 | 2026-08-08 | Completed | 100 | DOC-B | 0 | Approved | 2026-08-22 | 635 | Valid | Valid | Valid | 46242 | 13 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0636 | QA/QC | Test Package Review | Review test package | Medium | 2026-01-07 | 2026-01-17 | 2026-01-10 |  | In Progress | 95 | QC-C | 1 | Pending | 2026-01-12 | 636 | Valid | Incomplete | Valid |  |  |  | 224 | Yes | Overdue | Clean | 1 | Unique
ACT-0637 | Planning | Variance Review | Analyze schedule variance | Medium | 2026-03-17 | 2026-03-24 | 2026-03-19 | 2026-03-27 | Completed | 100 | PLAN-A | 1 | N/A | 2026-04-08 | 637 | Valid | Valid | Valid | 46108 | 8 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0638 | Engineering | Design Review | Review technical specification | Medium | 2026-04-27 | 2026-05-10 | 2026-04-27 | 2026-04-29 | Completed | 100 | ENG-C | 1 | Approved | 2026-05-15 | 638 | Valid | Valid | Valid | 46141 | 2 | -11 |  | No | On Time | Clean | 1 | Unique
ACT-0639 | Planning | Schedule Update | Refresh progress schedule | High | 2026-04-28 | 2026-05-01 | 2026-05-02 | 2026-05-06 | Completed | 100 | PLAN-A | 0 | N/A | 2026-05-13 | 639 | Valid | Valid | Valid | 46148 | 4 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0640 | Engineering | Material Review | Review material submittal | Critical | 2026-04-01 | 2026-04-09 | 2026-04-11 | 2026-04-21 | Completed | 100 | ENG-A | 3 | Approved | 2026-04-26 | 640 | Valid | Valid | Valid | 46133 | 10 | 12 |  | No | Late | Clean | 1 | Unique
ACT-0641 | Construction | Installation | Install project component | Medium | 2026-06-14 | 2026-06-22 | 2026-06-21 | 2026-06-28 | Completed | 100 | CONST-B | 0 | N/A | 2026-07-01 | 641 | Valid | Valid | Valid | 46201 | 7 | 6 |  | No | Late | Clean | 1 | Unique
ACT-0642 | QA/QC | Inspection | Verify completed installation | High | 2026-01-08 | 2026-01-22 | 2026-01-11 | 2026-02-09 | Completed | 100 | QA-A | 1 | N/A | 2026-02-10 | 642 | Valid | Valid | Valid | 46062 | 29 | 18 |  | No | Late | Clean | 1 | Unique
ACT-0643 | Document Control | Approval Tracking | Follow up document approval | High | 2026-05-12 | 2026-05-17 | 2026-05-15 | 2026-05-04 | Completed | 100 | DOC-B | 0 | Approved | 2026-05-14 | 643 | Valid | Check | Check |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0644 | Planning | Progress Review | Validate reported progress | Medium | 2026-07-18 | 2026-07-30 | 2026-07-18 | 2026-07-30 | Completed | 100 | PLAN-B | 4 | N/A | 2026-08-13 | 644 | Valid | Valid | Valid | 46233 | 12 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0645 | Construction | Punch List | Resolve outstanding punch item | High | 2026-01-08 | 2026-01-17 |  |  | Not Started | 0 | CONST-B | 2 | N/A | 2026-01-11 | 645 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0646 | QA/QC | Test Package Review | Review test package | High | 2026-01-20 | 2026-01-26 | 2026-01-21 | 2026-02-06 | Completed | 100 | QC-C | 0 | Pending | 2026-02-20 | 646 | Valid | Valid | Valid | 46059 | 16 | 11 |  | No | Late | Clean | 1 | Unique
ACT-0647 | Document Control | Revision Control | Check revision history | Medium | 2026-07-25 | 2026-07-28 | 2026-08-01 | 2026-07-30 | Completed | 100 | DOC-B | 0 | N/A | 2026-08-09 | 647 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0648 | QA/QC | Inspection | Conduct quality inspection | Critical | 2026-07-29 | 2026-08-07 | 2026-07-29 |  | On Hold | 70 | QA-A | 1 | N/A | 2026-08-04 | 648 | Valid | Incomplete | Valid |  |  |  | 24 | Yes | Overdue | Clean | 1 | Unique
ACT-0649 | Construction | Punch List | Close punch item | Medium | 2026-02-18 | 2026-03-10 | 2026-02-23 |  | In Progress | 75 | CONST-B | 0 | N/A | 2026-03-09 | 649 | Valid | Incomplete | Valid |  |  |  | 180 | Yes | Overdue | Clean | 1 | Unique
ACT-0650 | Engineering | Drawing Revision | Revise issued drawing | Medium | 2026-06-09 | 2026-06-18 | 2026-06-07 | 2026-06-14 | Completed | 100 | ENG-B | 3 | Approved | 2026-06-25 | 650 | Valid | Valid | Valid | 46187 | 7 | -4 |  | No | On Time | Clean | 1 | Unique
ACT-0651 | QA/QC | Test Package Review | Check package completeness | Medium | 2026-06-10 | 2026-06-25 | 2026-06-15 | 2026-06-20 | Completed | 100 | QC-C | 1 | Approved | 2026-06-29 | 651 | Valid | Valid | Valid | 46193 | 5 | -5 |  | No | On Time | Clean | 1 | Unique
ACT-0652 | Construction | Punch List | Verify punch completion | Medium | 2026-03-24 | 2026-04-09 | 2026-03-24 | 2026-04-15 | Completed | 100 | CONST-A | 2 | N/A | 2026-04-21 | 652 | Valid | Valid | Valid | 46127 | 22 | 6 |  | No | Late | Clean | 1 | Unique
ACT-0653 | Document Control | Document Submission | Submit project document | High | 2026-07-10 | 2026-07-23 | 2026-07-19 |  | In Progress | 70 | DOC-B | 0 | Rejected | 2026-07-21 | 653 | Valid | Incomplete | Valid |  |  |  | 34 | Yes | Overdue | Clean | 1 | Unique
ACT-0654 | Document Control | Document Submission | Prepare document for submission | Critical | 2026-02-15 | 2026-02-23 | 2026-02-13 |  | In Progress | 95 | DOC-A | 0 | Pending | 2026-02-24 | 654 | Valid | Incomplete | Valid |  |  |  | 190 | Yes | Overdue | Clean | 1 | Unique
ACT-0655 | Planning | Variance Review | Review delayed activity | Medium | 2026-05-07 | 2026-05-10 | 2026-05-05 | 2026-05-22 | Completed | 100 | PLAN-B | 2 | N/A | 2026-05-26 | 655 | Valid | Valid | Valid | 46164 | 17 | 12 |  | No | Late | Clean | 1 | Unique
ACT-0656 | Construction | Punch List | Verify punch completion | Medium | 2026-06-02 | 2026-06-09 |  |  | Not Started | 0 | CONST-B | 2 | N/A | 2026-06-14 | 656 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0657 | Planning | Schedule Update | Update milestone tracker | Critical | 2026-04-23 | 2026-04-30 | 2026-04-23 |  | In Progress | 60 | PLAN-A | 1 | N/A | 2026-05-06 | 657 | Valid | Incomplete | Valid |  |  |  | 121 | Yes | Overdue | Clean | 1 | Unique
ACT-0658 | Engineering | Technical Query | Resolve site technical query | Medium | 2026-02-27 | 2026-03-13 | 2026-03-04 | 2026-03-22 | Completed | 100 | ENG-C | 0 | N/A | 2026-04-04 | 658 | Valid | Valid | Valid | 46103 | 18 | 9 |  | No | Late | Clean | 1 | Unique
ACT-0659 | Construction | Site Preparation | Coordinate access preparation | Medium | 2026-02-19 | 2026-03-04 | 2026-02-26 | 2026-03-04 | Completed | 100 | CONST-A | 0 | N/A | 2026-03-22 | 659 | Valid | Valid | Valid | 46085 | 6 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0660 | Engineering | Design Review | Review technical specification | Medium | 2026-07-18 | 2026-07-26 | 2026-07-20 |  | In Progress | 90 | ENG-A | 4 | Pending | 2026-07-25 | 660 | Valid | Incomplete | Valid |  |  |  | 33 | Yes | Overdue | Clean | 1 | Unique
ACT-0661 | QA/QC | Test Package Review | Review test package | Medium | 2026-04-02 | 2026-04-04 | 2026-03-31 | 2026-04-12 | Completed | 100 | QC-C | 0 | Approved | 2026-04-12 | 661 | Valid | Valid | Valid | 46124 | 12 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0662 | Construction | Installation | Complete field installation | Medium | 2026-07-26 | 2026-07-28 | 2026-07-24 | 2026-08-04 | Completed | 100 | CONST-C | 1 | N/A | 2026-08-14 | 662 | Valid | Valid | Valid | 46238 | 11 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0663 | Construction | Site Preparation | Coordinate access preparation | High | 2026-03-26 | 2026-04-04 | 2026-03-27 | 2026-04-07 | Completed | 100 | CONST-A | 1 | N/A | 2026-04-17 | 663 | Valid | Valid | Valid | 46119 | 11 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0664 | Engineering | Material Review | Check technical datasheet | High | 2026-02-09 | 2026-02-11 | 2026-02-12 |  | In Progress | 50 | ENG-C | 1 | Pending | 2026-02-27 | 664 | Valid | Incomplete | Valid |  |  |  | 191 | Yes | Overdue | Clean | 1 | Unique
ACT-0665 | Construction | Punch List | Close punch item | Critical | 2026-03-28 | 2026-03-30 | 2026-03-28 |  | In Progress | 95 | CONST-A | 0 | N/A | 2026-04-11 | 665 | Valid | Incomplete | Valid |  |  |  | 147 | Yes | Overdue | Clean | 1 | Unique
ACT-0666 | Construction | Rework | Rectify field discrepancy | High | 2026-01-25 | 2026-02-07 | 2026-02-05 |  | In Progress | 20 | CONST-C | 2 | N/A | 2026-02-14 | 666 | Valid | Incomplete | Valid |  |  |  | 198 | Yes | Overdue | Clean | 1 | Unique
ACT-0667 | Engineering | Drawing Revision | Prepare revised drawing | High | 2026-07-24 | 2026-08-11 |  |  | Not Started | 0 | ENG-B | 1 | Pending | 2026-08-10 | 667 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0668 | Engineering | Material Review | Review material submittal | Medium | 2026-05-23 | 2026-06-01 | 2026-05-21 | 2026-06-17 | Completed | 100 | ENG-A | 0 | Rejected | 2026-06-17 | 668 | Valid | Valid | Valid | 46190 | 27 | 16 |  | No | Late | Clean | 1 | Unique
ACT-0669 | Document Control | Transmittal | Issue transmittal record | High | 2026-03-02 | 2026-03-12 | 2026-03-02 |  | In Progress | 90 | DOC-A | 0 | Pending | 2026-03-17 | 669 | Valid | Incomplete | Valid |  |  |  | 173 | Yes | Overdue | Clean | 1 | Unique
ACT-0670 | Procurement | Delivery Tracking | Track material delivery | Critical | 2026-07-20 | 2026-07-24 | 2026-07-20 |  | In Progress | 90 | PROC-A | 2 | N/A | 2026-08-02 | 670 | Valid | Incomplete | Valid |  |  |  | 33 | Yes | Overdue | Clean | 1 | Unique
ACT-0671 | QA/QC | Inspection | Verify completed installation | Low | 2026-01-27 | 2026-02-08 | 2026-02-02 |  | In Progress | 20 | QA-B | 1 | N/A | 2026-02-06 | 671 | Valid | Incomplete | Valid |  |  |  | 201 | Yes | Overdue | Clean | 1 | Unique
ACT-0672 | Document Control | Document Submission | Prepare document for submission | Low | 2026-05-22 | 2026-05-30 | 2026-05-26 | 2026-06-02 | Completed | 100 | DOC-A | 2 | Approved | 2026-06-18 | 672 | Valid | Valid | Valid | 46175 | 7 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0673 | Engineering | Design Review | Review technical specification | High | 2026-03-26 | 2026-04-01 | 2026-03-26 |  | In Progress | 40 | ENG-C | 0 | Pending | 2026-03-27 | 673 | Valid | Incomplete | Valid |  |  |  | 149 | Yes | Overdue | Clean | 1 | Unique
ACT-0674 | QA/QC | Inspection | Verify completed installation | Critical | 2026-07-04 | 2026-07-24 | 2026-07-09 |  | In Progress | 95 | QA-B | 4 | N/A | 2026-07-10 | 674 | Valid | Incomplete | Valid |  |  |  | 44 | Yes | Overdue | Clean | 1 | Unique
ACT-0675 | Engineering | Drawing Revision | Prepare revised drawing | Critical | 2026-03-03 | 2026-03-06 | 2026-03-05 |  | In Progress | 90 | ENG-C | 4 | Pending | 2026-03-05 | 675 | Valid | Incomplete | Valid |  |  |  | 170 | Yes | Overdue | Clean | 1 | Unique
ACT-0676 | QA/QC | Test Package Review | Validate test records | Medium | 2026-04-04 | 2026-04-18 | 2026-04-02 | 2026-04-22 | Completed | 100 | QA-A | 0 | Approved | 2026-05-04 | 676 | Valid | Valid | Valid | 46134 | 20 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0677 | Engineering | Design Review | Review technical specification | Medium | 2026-06-21 | 2026-06-28 | 2026-06-28 | 2026-06-17 | Completed | 100 | ENG-C | 0 | Approved | 2026-06-23 | 677 | Valid | Check | Check |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0678 | Planning | Lookahead Planning | Update short-term plan | High | 2026-01-31 | 2026-02-06 | 2026-02-01 |  | In Progress | 25 | PLAN-B | 4 | N/A | 2026-02-04 | 678 | Valid | Incomplete | Valid |  |  |  | 202 | Yes | Overdue | Clean | 1 | Unique
ACT-0679 | Document Control | Revision Control | Update document revision | Low | 2026-05-16 | 2026-05-28 | 2026-05-22 | 2026-05-29 | Completed | 100 | DOC-B | 0 | N/A | 2026-06-05 | 679 | Valid | Valid | Valid | 46171 | 7 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0680 | Construction | Punch List | Resolve outstanding punch item | High | 2026-07-22 | 2026-07-26 | 2026-07-29 | 2026-07-27 | Completed | 100 | CONST-A | 2 | N/A | 2026-08-07 | 680 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0681 | Engineering | Design Review | Review engineering drawing | Medium | 2026-06-25 | 2026-07-13 | 2026-06-23 | 2026-07-06 | Completed | 100 | ENG-A | 2 | Approved | 2026-07-24 | 681 | Valid | Valid | Valid | 46209 | 13 | -7 |  | No | On Time | Clean | 1 | Unique
ACT-0682 | QA/QC | Test Package Review | Check package completeness | Medium | 2026-01-30 | 2026-02-11 |  |  | Not Started | 0 | QA-B | 3 | Approved | 2026-02-04 | 682 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0683 | Procurement | Material Request | Validate requested quantity | Medium | 2026-05-22 | 2026-06-09 | 2026-05-21 |  | In Progress | 20 | PROC-A | 2 | Pending | 2026-05-24 | 683 | Valid | Incomplete | Valid |  |  |  | 93 | Yes | Overdue | Clean | 1 | Unique
ACT-0684 | Document Control | Revision Control | Update document revision | Medium | 2026-07-28 | 2026-08-09 | 2026-07-28 | 2026-08-14 | Completed | 100 | DOC-A | 1 | N/A | 2026-08-15 | 684 | Valid | Valid | Valid | 46248 | 17 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0685 | Document Control | Transmittal | Issue transmittal record | Critical | 2026-02-17 | 2026-03-04 | 2026-02-20 |  | In Progress | 10 | DOC-B | 4 | Pending | 2026-03-01 | 685 | Valid | Incomplete | Valid |  |  |  | 183 | Yes | Overdue | Clean | 1 | Unique
ACT-0686 | Engineering | Material Review | Check technical datasheet | Medium | 2026-04-05 | 2026-04-24 | 2026-04-05 | 2026-04-19 | Completed | 100 | ENG-A | 0 | Approved | 2026-04-25 | 686 | Valid | Valid | Valid | 46131 | 14 | -5 |  | No | On Time | Clean | 1 | Unique
ACT-0687 | Construction | Punch List | Resolve outstanding punch item | Medium | 2026-02-06 | 2026-02-21 |  |  | Not Started | 0 | CONST-C | 0 | N/A | 2026-02-18 | 687 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0688 | Document Control | Approval Tracking | Follow up document approval | Low | 2026-03-11 | 2026-03-26 | 2026-03-14 |  | In Progress | 90 | DOC-A | 2 | Pending | 2026-03-25 | 688 | Valid | Incomplete | Valid |  |  |  | 161 | Yes | Overdue | Clean | 1 | Unique
ACT-0689 | Construction | Punch List | Verify punch completion | Critical | 2026-04-26 | 2026-05-10 |  |  | Not Started | 0 | CONST-B | 1 | N/A | 2026-04-28 | 689 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0690 | Engineering | Design Review | Review technical specification | Medium | 2026-01-21 | 2026-02-02 | 2026-01-24 | 2026-02-03 | Completed | 100 | ENG-A | 3 | Approved | 2026-02-03 | 690 | Valid | Valid | Valid | 46056 | 10 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0691 | QA/QC | Testing | Perform pressure test | Critical | 2026-07-24 | 2026-07-29 | 2026-07-29 |  | In Progress | 70 | QC-C | 0 | N/A | 2026-08-09 | 691 | Valid | Incomplete | Valid |  |  |  | 24 | Yes | Overdue | Clean | 1 | Unique
ACT-0692 | Construction | Site Preparation | Coordinate access preparation | Medium | 2026-01-30 | 2026-02-02 | 2026-02-06 | 2026-02-09 | Completed | 100 | CONST-C | 2 | N/A | 2026-02-26 | 692 | Valid | Valid | Valid | 46062 | 3 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0693 | Construction | Rework | Complete required rework | High | 2026-03-12 | 2026-03-14 | 2026-03-13 | 2026-03-13 | Completed | 100 | CONST-A | 1 | N/A | 2026-03-21 | 693 | Valid | Valid | Valid | 46094 | 0 | -1 |  | No | On Time | Clean | 1 | Unique
ACT-0694 | Document Control | Transmittal | Track transmittal response | High | 2026-06-27 | 2026-07-12 | 2026-07-03 |  | In Progress | 40 | DOC-B | 4 | Pending | 2026-07-10 | 694 | Valid | Incomplete | Valid |  |  |  | 50 | Yes | Overdue | Clean | 1 | Unique
ACT-0695 | Construction | Installation | Install project component | Medium | 2026-03-26 | 2026-03-30 | 2026-04-09 | 2026-04-09 | Completed | 100 | CONST-C | 1 | N/A | 2026-04-11 | 695 | Valid | Valid | Valid | 46121 | 0 | 10 |  | No | Late | Clean | 1 | Unique
ACT-0696 | QA/QC | Test Package Review | Review test package | Critical | 2026-04-23 | 2026-05-11 | 2026-04-27 | 2026-05-06 | Completed | 100 | QA-B | 2 | Approved | 2026-05-09 | 696 | Valid | Valid | Valid | 46148 | 9 | -5 |  | No | On Time | Clean | 1 | Unique
ACT-0697 | Engineering | Drawing Revision | Prepare revised drawing | Low | 2026-04-23 | 2026-05-12 | 2026-04-24 | 2026-05-15 | Completed | 100 | ENG-C | 3 | Pending | 2026-05-31 | 697 | Valid | Valid | Valid | 46157 | 21 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0698 | Construction | Rework | Correct installation issue | High | 2026-07-19 | 2026-08-06 | 2026-07-17 | 2026-08-13 | Completed | 100 | CONST-B | 1 | N/A | 2026-08-14 | 698 | Valid | Valid | Valid | 46247 | 27 | 7 |  | No | Late | Clean | 1 | Unique
ACT-0699 | Construction | Punch List | Verify punch completion | Critical | 2026-04-01 | 2026-04-10 | 2026-04-05 |  | In Progress | 40 | CONST-B | 0 | N/A | 2026-04-14 | 699 | Valid | Incomplete | Valid |  |  |  | 139 | Yes | Overdue | Clean | 1 | Unique
ACT-0700 | QA/QC | Test Package Review | Review test package | Critical | 2026-06-18 | 2026-07-06 | 2026-06-24 |  | In Progress | 50 | QA-B | 0 | Pending | 2026-07-03 | 700 | Valid | Incomplete | Valid |  |  |  | 59 | Yes | Overdue | Clean | 1 | Unique
ACT-0701 | Engineering | Technical Query | Respond to engineering query | Medium | 2026-04-05 | 2026-04-07 | 2026-04-07 | 2026-04-20 | Completed | 100 | ENG-B | 0 | N/A | 2026-04-23 | 701 | Valid | Valid | Valid | 46132 | 13 | 13 |  | No | Late | Clean | 1 | Unique
ACT-0702 | Engineering | Technical Query | Resolve site technical query | Medium | 2026-04-10 | 2026-04-21 | 2026-04-14 |  | In Progress | 40 | ENG-C | 0 | N/A | 2026-04-28 | 702 | Valid | Incomplete | Valid |  |  |  | 130 | Yes | Overdue | Clean | 1 | Unique
ACT-0703 | Procurement | Vendor Follow-up | Follow up vendor response | Medium | 2026-04-26 | 2026-04-28 | 2026-05-01 | 2026-05-06 | Completed | 100 | PROC-B | 0 | N/A | 2026-05-18 | 703 | Valid | Valid | Valid | 46148 | 5 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0704 | Procurement | Material Request | Prepare material request | High | 2026-05-07 | 2026-05-17 | 2026-05-07 |  | In Progress | 60 | PROC-A | 1 | Approved | 2026-05-19 | 704 | Valid | Incomplete | Valid |  |  |  | 107 | Yes | Overdue | Clean | 1 | Unique
ACT-0705 | Engineering | Design Review | Review engineering drawing | Medium | 2026-04-03 | 2026-04-21 |  |  | Not Started | 0 | ENG-B | 2 | Pending | 2026-04-13 | 705 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0706 | Document Control | Document Submission | Prepare document for submission | Medium | 2026-03-18 | 2026-04-04 | 2026-03-19 | 2026-03-30 | Completed | 90 | DOC-B | 0 | Approved | 2026-04-02 | 706 | Valid | Valid | Valid | 46111 | 11 | -5 |  | No | On Time | Clean | 1 | Unique
ACT-0707 | Document Control | Revision Control | Maintain revision register | High | 2026-02-24 | 2026-03-13 | 2026-02-22 |  | In Progress | 75 | DOC-A | 1 | N/A | 2026-02-28 | 707 | Valid | Incomplete | Valid |  |  |  | 181 | Yes | Overdue | Clean | 1 | Unique
ACT-0708 | QA/QC | Testing | Perform pressure test | Low | 2026-02-23 | 2026-03-01 | 2026-02-24 | 2026-03-05 | Completed | 100 | QC-C | 1 | N/A | 2026-03-14 | 708 | Valid | Valid | Valid | 46086 | 9 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0709 | Construction | Punch List | Close punch item | Medium | 2026-05-07 | 2026-05-10 | 2026-05-08 | 2026-05-14 | Completed | 100 | CONST-C | 0 | N/A | 2026-05-25 | 709 | Valid | Valid | Valid | 46156 | 6 | 4 |  | No | Late | Clean | 1 | Unique
ACT-0710 | Construction | Site Preparation | Prepare work area | Medium | 2026-01-05 | 2026-01-08 | 2026-01-06 | 2026-01-23 | Completed | 90 | CONST-A | 1 | N/A | 2026-02-05 | 710 | Valid | Valid | Valid | 46045 | 17 | 15 |  | No | Late | Clean | 1 | Unique
ACT-0711 | QA/QC | Test Package Review | Check package completeness | Medium | 2026-02-02 | 2026-02-07 | 2026-02-02 | 2026-02-02 | Completed | 100 | QC-C | 1 | Approved | 2026-02-20 | 711 | Valid | Valid | Valid | 46055 | 0 | -5 |  | No | On Time | Clean | 1 | Unique
ACT-0712 | Construction | Punch List | Resolve outstanding punch item | Medium | 2026-06-03 | 2026-06-17 | 2026-06-10 |  | On Hold | 60 | CONST-C | 3 | N/A | 2026-06-16 | 712 | Valid | Incomplete | Valid |  |  |  | 73 | Yes | Overdue | Clean | 1 | Unique
ACT-0713 | Construction | Installation | Complete field installation | Critical | 2026-06-12 | 2026-06-24 | 2026-06-18 | 2026-07-04 | Completed | 100 | CONST-A | 0 | N/A | 2026-07-08 | 713 | Valid | Valid | Valid | 46207 | 16 | 10 |  | No | Late | Clean | 1 | Unique
ACT-0714 | Construction | Site Preparation | Coordinate access preparation | Critical | 2026-04-08 | 2026-04-24 | 2026-04-07 | 2026-04-25 | Completed | 90 | CONST-A | 1 | N/A | 2026-05-11 | 714 | Valid | Valid | Valid | 46137 | 18 | 1 |  | No | Late | Clean | 1 | Unique
ACT-0715 | Engineering | Technical Query | Respond to engineering query | Critical | 2026-03-20 | 2026-03-23 | 2026-03-23 | 2026-04-02 | Completed | 100 | ENG-C | 3 | N/A | 2026-04-17 | 715 | Valid | Valid | Valid | 46114 | 10 | 10 |  | No | Late | Clean | 1 | Unique
ACT-0716 | Construction | Installation | Complete field installation | Medium | 2026-05-15 | 2026-05-29 | 2026-05-17 | 2026-06-03 | Completed | 100 | CONST-A | 0 | N/A | 2026-06-21 | 716 | Valid | Valid | Valid | 46176 | 17 | 5 |  | No | Late | Clean | 1 | Unique
ACT-0717 | Construction | Installation | Execute planned installation | Medium | 2026-07-05 | 2026-07-23 | 2026-07-06 |  | In Progress | 40 | CONST-A | 1 | N/A | 2026-07-11 | 717 | Valid | Incomplete | Valid |  |  |  | 47 | Yes | Overdue | Clean | 1 | Unique
ACT-0718 | Engineering | Drawing Revision | Update drawing comments | Low | 2026-02-11 | 2026-02-21 | 2026-02-11 |  | In Progress | 30 | ENG-C | 1 | Pending | 2026-02-22 | 718 | Valid | Incomplete | Valid |  |  |  | 192 | Yes | Overdue | Clean | 1 | Unique
ACT-0719 | Construction | Site Preparation | Complete site readiness activity | Low | 2026-07-04 | 2026-07-23 | 2026-07-14 | 2026-08-07 | Completed | 100 | CONST-B | 5 | N/A | 2026-08-07 | 719 | Valid | Valid | Valid | 46241 | 24 | 15 |  | No | Late | Clean | 1 | Unique
ACT-0720 | QA/QC | NCR Follow-up | Follow up corrective action | Medium | 2026-01-09 | 2026-01-28 | 2026-01-09 |  | In Progress | 80 | QC-C | 0 | N/A | 2026-01-21 | 720 | Valid | Incomplete | Valid |  |  |  | 225 | Yes | Overdue | Clean | 1 | Unique
ACT-0721 | QA/QC | Testing | Perform pressure test | Medium | 2026-03-14 | 2026-03-22 | 2026-03-18 | 2026-03-17 | Completed | 100 | QA-B | 0 | N/A | 2026-03-30 | 721 | Valid | Check | Valid |  |  |  |  | No | Completed - Date Issue | Review Required | 1 | Unique
ACT-0722 | Engineering | Material Review | Review material submittal | Medium | 2026-05-02 | 2026-05-09 | 2026-05-05 |  | In Progress | 40 | ENG-B | 0 | Pending | 2026-05-10 | 722 | Valid | Incomplete | Valid |  |  |  | 109 | Yes | Overdue | Clean | 1 | Unique
ACT-0723 | Planning | Progress Review | Review weekly progress | Medium | 2026-04-24 | 2026-05-03 | 2026-04-29 |  | In Progress | 95 | PLAN-A | 1 | N/A | 2026-04-29 | 723 | Valid | Incomplete | Valid |  |  |  | 115 | Yes | Overdue | Clean | 1 | Unique
ACT-0724 | QA/QC | Inspection | Perform site inspection | High | 2026-07-19 | 2026-07-22 | 2026-07-21 |  | In Progress | 10 | QC-C | 4 | N/A | 2026-07-24 | 724 | Valid | Incomplete | Valid |  |  |  | 32 | Yes | Overdue | Clean | 1 | Unique
ACT-0725 | Planning | Lookahead Planning | Update short-term plan | Low | 2026-02-09 | 2026-02-26 | 2026-02-07 |  | In Progress | 40 | PLAN-A | 0 | N/A | 2026-02-11 | 725 | Valid | Incomplete | Valid |  |  |  | 196 | Yes | Overdue | Clean | 1 | Unique
ACT-0726 | Engineering | Technical Query | Respond to engineering query | Medium | 2026-01-10 | 2026-01-13 | 2026-01-10 |  | In Progress | 30 | ENG-B | 0 | N/A | 2026-01-23 | 726 | Valid | Incomplete | Valid |  |  |  | 224 | Yes | Overdue | Clean | 1 | Unique
ACT-0727 | Engineering | Technical Query | Resolve site technical query | Critical | 2026-06-29 | 2026-07-13 | 2026-07-05 |  | In Progress | 70 | ENG-A | 0 | N/A | 2026-07-08 | 727 | Valid | Incomplete | Valid |  |  |  | 48 | Yes | Overdue | Clean | 1 | Unique
ACT-0728 | Engineering | Technical Query | Clarify design requirement | Low | 2026-03-31 | 2026-04-05 | 2026-04-03 | 2026-04-08 | Completed | 100 | ENG-C | 0 | N/A | 2026-04-21 | 728 | Valid | Valid | Valid | 46120 | 5 | 3 |  | No | Late | Clean | 1 | Unique
ACT-0729 | QA/QC | Testing | Complete system testing | Medium | 2026-06-24 | 2026-07-05 | 2026-06-24 | 2026-07-27 | Completed | 100 | QA-B | 1 | N/A | 2026-08-07 | 729 | Valid | Valid | Valid | 46230 | 33 | 22 |  | No | Late | Clean | 1 | Unique
ACT-0730 | Procurement | Material Request | Prepare material request | High | 2026-02-12 | 2026-02-18 | 2026-02-12 |  | In Progress | 20 | PROC-A | 0 | Pending | 2026-02-20 | 730 | Valid | Incomplete | Valid |  |  |  | 191 | Yes | Overdue | Clean | 1 | Unique
ACT-0731 | Engineering | Drawing Revision | Revise issued drawing | High | 2026-04-05 | 2026-04-17 | 2026-04-10 | 2026-05-02 | Completed | 100 | ENG-B | 2 | Approved | 2026-05-09 | 731 | Valid | Valid | Valid | 46144 | 22 | 15 |  | No | Late | Clean | 1 | Unique
ACT-0732 | Construction | Rework | Rectify field discrepancy | Medium | 2026-05-21 | 2026-06-09 | 2026-05-23 | 2026-06-11 | Completed | 100 | CONST-C | 1 | N/A | 2026-06-18 | 732 | Valid | Valid | Valid | 46184 | 19 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0733 | Engineering | Technical Query | Resolve site technical query | Medium | 2026-01-09 | 2026-01-22 | 2026-01-09 |  | In Progress | 10 | ENG-A | 4 | N/A | 2026-01-20 | 733 | Valid | Incomplete | Valid |  |  |  | 225 | Yes | Overdue | Clean | 1 | Unique
ACT-0734 | QA/QC | Testing | Complete system testing | Critical | 2026-04-22 | 2026-05-01 | 2026-04-25 | 2026-05-21 | Completed | 100 | QA-B | 2 | N/A | 2026-05-25 | 734 | Valid | Valid | Valid | 46163 | 26 | 20 |  | No | Late | Clean | 1 | Unique
ACT-0735 | Planning | Variance Review | Investigate progress variance | Low | 2026-02-01 | 2026-02-21 |  |  | Not Started | 0 | PLAN-A | 3 | N/A | 2026-02-06 | 735 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0736 | Engineering | Drawing Revision | Revise issued drawing | Medium | 2026-01-08 | 2026-01-28 | 2026-01-06 | 2026-02-08 | Completed | 100 | ENG-B | 0 | Approved | 2026-02-17 | 736 | Valid | Valid | Valid | 46061 | 33 | 11 |  | No | Late | Clean | 1 | Unique
ACT-0737 | Construction | Site Preparation | Complete site readiness activity | High | 2026-07-01 | 2026-07-03 | 2026-07-08 | 2026-07-26 | Completed | 100 | CONST-A | 2 | N/A | 2026-08-11 | 737 | Valid | Valid | Valid | 46229 | 18 | 23 |  | No | Late | Clean | 1 | Unique
ACT-0738 | Engineering | Material Review | Check technical datasheet | Critical | 2026-05-01 | 2026-05-20 | 2026-05-02 | 2026-06-04 | Completed | 100 | ENG-A | 0 | Pending | 2026-06-12 | 738 | Valid | Valid | Valid | 46177 | 33 | 15 |  | No | Late | Clean | 1 | Unique
ACT-0739 | Construction | Punch List | Resolve outstanding punch item | Medium | 2026-06-12 | 2026-06-15 | 2026-06-18 | 2026-07-07 | Completed | 100 | CONST-B | 3 | N/A | 2026-07-21 | 739 | Valid | Valid | Valid | 46210 | 19 | 22 |  | No | Late | Clean | 1 | Unique
ACT-0740 | QA/QC | Test Package Review | Check package completeness | Medium | 2026-07-29 | 2026-08-11 | 2026-07-31 | 2026-08-21 | Completed | 100 | QA-A | 1 | Approved | 2026-08-21 | 740 | Valid | Valid | Valid | 46255 | 21 | 10 |  | No | Late | Clean | 1 | Unique
ACT-0741 | QA/QC | Inspection | Perform site inspection | Medium | 2026-01-07 | 2026-01-18 | 2026-01-12 | 2026-02-11 | Completed | 100 | QC-C | 0 | N/A | 2026-03-01 | 741 | Valid | Valid | Valid | 46064 | 30 | 24 |  | No | Late | Clean | 1 | Unique
ACT-0742 | Engineering | Material Review | Review material submittal | Low | 2026-01-28 | 2026-02-08 |  |  | Not Started | 0 | ENG-C | 1 | Pending | 2026-02-09 | 742 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0743 | Engineering | Material Review | Check technical datasheet | Medium | 2026-02-07 | 2026-02-12 | 2026-02-12 | 2026-02-12 | Completed | 100 | ENG-B | 2 | Approved | 2026-02-24 | 743 | Valid | Valid | Valid | 46065 | 0 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0744 | Construction | Installation | Install project component | Medium | 2026-06-28 | 2026-07-14 |  |  | Not Started | 0 | CONST-A | 1 | N/A | 2026-07-05 | 744 | Valid | Incomplete | Valid |  |  |  |  | Yes | Overdue | Clean | 1 | Unique
ACT-0745 | Procurement | Vendor Follow-up | Coordinate supplier action | Medium | 2026-05-13 | 2026-05-31 | 2026-05-13 |  | In Progress | 25 | PROC-B | 0 | N/A | 2026-05-24 | 745 | Valid | Incomplete | Valid |  |  |  | 101 | Yes | Overdue | Clean | 1 | Unique
ACT-0746 | Engineering | Material Review | Review material submittal | Medium | 2026-06-10 | 2026-06-14 | 2026-06-09 | 2026-06-22 | Completed | 100 | ENG-C | 0 | Approved | 2026-07-01 | 746 | Valid | Valid | Valid | 46195 | 13 | 8 |  | No | Late | Clean | 1 | Unique
ACT-0747 | Document Control | Document Submission | Prepare document for submission | Low | 2026-03-26 | 2026-04-02 | 2026-03-27 | 2026-04-04 | Completed | 100 | DOC-B | 0 | Approved | 2026-04-18 | 747 | Valid | Valid | Valid | 46116 | 8 | 2 |  | No | Late | Clean | 1 | Unique
ACT-0748 | Document Control | Transmittal | Issue transmittal record | High | 2026-02-09 | 2026-02-14 | 2026-02-14 | 2026-02-14 | Completed | 100 | DOC-B | 1 | Approved | 2026-02-18 | 748 | Valid | Valid | Valid | 46067 | 0 | 0 |  | No | On Time | Clean | 1 | Unique
ACT-0749 | QA/QC | NCR Follow-up | Verify NCR closure | Low | 2026-04-20 | 2026-05-08 | 2026-04-24 |  | In Progress | 10 | QC-C | 1 | N/A | 2026-04-25 | 749 | Valid | Incomplete | Valid |  |  |  | 120 | Yes | Overdue | Clean | 1 | Unique
ACT-0750 | Procurement | Material Request | Prepare material request | High | 2026-03-20 | 2026-04-03 | 2026-03-22 | 2026-04-16 | Completed | 100 | PROC-B | 1 | Approved | 2026-04-30 | 750 | Valid | Valid | Valid | 46128 | 25 | 13 |  | No | Late | Clean | 1 | Unique